## Sheet1
TX SET Meeting Notes / Action Items
June 17 - 18, 2015
Agenda Item: | Decision / Resolution | Action Items :
April 2015 Meeting Notes | There were two typo corrections to the meeting notes. | Texas SET Chair to have the notes posted to the April Meeting Page.
Mass Transition/Default-POLR Rule | • RMS assignment to discuss Mass Transition— Possible POLR Rule change from two days out to one day out.
AMWG Update
Other discussion
Market Test Flight 0214 Update | ERCOT to provide flight update No update received
TX SET Procedures | On Hold-Discuss reline changes sent to the TXSET listserv for review | Leave current issue process in tact and continue to review document to identify where additional process improvements can be made
RMS Updates
668NPRR-01 Updates to Texas SET Implementation Guide Process—TAC Approved at the May 2015 meeting. The ERCOT Board will vote at their June 9, 2015 meeting. | No Action
RMGRR130, Alignment of Section 7, Market Processes, with TDSP Terms and Conditions Tariff Effective 01/15/2015—RMS approved. TAC will vote at their June 25, 2015 meeting. | No Action
Adhoc Testing and Penny Test Experiences Incurred During Flight 0215 Discussion--Changes made to the Adhoc testing signup deadline and other related changes were approved at RMS. Changes took affect in Flight 0615. | No Action
RMGRR132, NOIE Disconnect and Reconnect Process—RMS voted to table and refer to TX SET for discussion. | • Tom Burke with Golden Spread Electric Cooperative (GSEC) provided background information for RMGRR132. • Texas SET worked with Mr. Burke to develop a new Retail Market Guide Section as an alternative to the changes originally made to Section 7 by RMGRR132. • The draft language for new Section 12, External Load Serving Entities (ELSE) Market Processes was created and will be sent to the Texas SET list serve for review and comments. • The TDSPs will review the proposed language internally to determine any tariff impacts this change may have and report the findings at the Texas SET July 21st meeting. • Texas SET will continue discussions at the July 21st Texas SET meeting where comments will be developed for RMGRR132. | The Texas SET chair to send the new section language to the Texas SET list serve.
814_PC, Maintain Customer Information Request--Timing and Required EDI Segments Discussion | o Kyle Patrick with NRG requested clarification on the timing required for sending the 814_PC. o Mr. Patrick also requested clarification on the use and content required in the N1~FJ (First Contact) loop of the 814PC. o Texas SET revisited the 814_PC implementation guide that determined that the CR must wait until they receive their 867_04 to send the 814_PC and discontinue sending any 814_PC’s after they receive their 86703 final. o Texas SET verified that the N1~FJ is a required loop and that the PER segment with the telephone information is required.  NRG companies are not always able to obtain a telephone number from the customer and therefore do not have the information to send to the TDSP in the transaction.  Texas SET attendees proposed that NRG companies fill the data element with either zeros or nines to fulfill the requirement and avoid rejection from the TDSP. o It was decided that Mr. Patrick will review the options discussed at Texas SET with NRG and that no further action will be required from Texas SET at this time. | No further action needed from Texas SET.
Flight 0615 Update
ERCOT | ERCOT presented Flight 0615 Statistics
Texas Market Test Plan Review
• Review ERCOT updates • Review prior, during and after responsibility Sections • General Document Review | Texas SET continued to review and reorganize the Texas Market Test Plan. | Kyle Patrick, NRG to continue to reorganize the outline for Section 2. Flight Requirments. Paul Yockey, ERCOT to review the Flight Admin section to determine where each item needs to be placed.
RMS assignments On Held--Discuss Approach and Requirements
• New Entrant Documentation—Procedures and Documentation Location | No action taken
• Add Master Customer List (MCL) guide back to the Texas SET Guides | No action taken
Discussion Items on Hold
Texas SET Release Discussion | No action taken
RMG Safety Net timelines | No action taken
REP Certification Matrix—Long-term solution | No action taken
Next Meeting | Changed -- July 20th -21st Rm 168 ERCOT Met Center -- Please note that the meeting will began at 11:00 AM on July 20th
Attendees
Diana Rehfeldt TNMP | Kathryn Thurman ERCOT | Sarah Heselmeyer ERCOT
Jim Lee AEP | Tom Burke GSEC | Taylor Woodruff ONCOR
Kathy Scott CNP | Kyle Patrick NRG | Paul Yockey ERCOT
WebEx
Connie Hermes STEC | Laura Aldis AP&G | Amy Rafferty ESG
Barbara Goubeaud EC Infosystems | Becky Taylor CNP | Lindsay Butterfield ERCOT
Paula Shadle STEC | Clint Sandridge Nobel | Ivan Velasquez ONCOR
Jasmine Tom CES | M. Sickling | Veronica Bahcianji
Carolyn Reed CNP | Ted Hailu ERCOT