## Slide 1
Project Update and Summary of Project Priority List (PPL) Activity
RMS
August 4, 2015

## Slide 2: 2015 Retail Project Update – Agenda
  Project Portfolio Update p. 3-8
    Retail Project Highlights
    2015 Release Targets
    2016 Release Targets
    2015 Project Spending Update
    2016-2017 Project Funding
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index

## Slide 3: Retail Project Highlights
RMGRR126 – Additional ERCOT Validations for CBCI File Not Started
  August start planned
  December go-live target (to be confirmed during Planning)
ERCOT Flight Certification Website In Flight
  Upgrade/enhance current Retail Cert environment
    Interfaces, workflows/processes, validations, browser compatibility, etc.
  Gated to Planning phase last week
  Project expected to take 2-3 years
SCR786 – Retail Market Test Environment IA In Progress
  Language approved at PRS on July 16, 2015
  IA is underway
    Targeting September PRS for IA completion
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2015 Release Targets – Board-Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
NPRR589(b) – S&B portion
SCR774(b) – Addition of Comments field
(a), (b), etc. indicates multiple phases
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
February 2/2 – 2/12 | March 3/23 – 3/27 | June |  | August 8/17 – 8/21 | September 9/21 – 9/25 | December 12/7 – 12/11
NPRR500 SCR772 | SCR778 SCR779 | NPRR559 NPRR597 NPRR601 NPRR639 | NPRR543 NPRR626 NPRR645 NPRR665 SCR774(b) SCR775 OBD (Shadow Price Caps) | SCR771 | NPRR553 NPRR588 NPRR589(b) NPRR615 NPRR698 | NPRR419 NPRR556 NPRR573 RMGRR126 RRGRR003
2 | 2 | 11 |  | 1 | 5 | 5
2015 TBD Items (and month they became “TBD”)
E
E
P
E
P
P
NS
NS
I
NS
NS
Project Status Codes: NS = Not Started, I = Initiation, P = Planning, E = Execution, H = On Hold
Aug 2014 | Oct 2014 | Dec 2014 | Jan 2015 | Mar 2015 | Apr 2015 | Jun 2015
NOGRR084 | NPRR327 H | NPRR272, SCR777 H | NPRR210, NPRR664 | NPRR256 | NPRR568-ph2, NPRR644 | NPRR686
Late May
6/13 (CMM)
6/22 – 6/26

## Slide 5: 2016 Release Targets – Board-Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
NPRR484(Ph1b) – Remaining Phase 1 items
NPRR484(Ph2) – S&B portion of NPRR
(a), (b), etc. indicates multiple phases
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
February Dates TBD | March Dates TBD | June Dates TBD | August Dates TBD | September Dates TBD | December Dates TBD
NPRR495 NPRR515 NPRR617 NPRR680 | NPRR620 NPRR662 NPRR679 NPRR683 | NPRR519 |  | NPRR219 NPRR439 SCR783 | NOGRR084 NPRR210 NPRR256 NPRR272 NPRR484(1b) NPRR484(2) NPRR493 SCR777 SCR781
4 | 4 | 2 | 0 | 3 | 8
Project Status Codes: NS = Not Started, I = Initiation, P = Planning, E = Execution, H = On Hold
I
NS
I
NS
NS
NS
NS
NS
NS
NS
H
P
NS
NS
NS
NS
NS
NS
NS
NS
NS

## Slide 6: 2015 Project Spending Update
2015 project budget = $21.65M
Reason: Minor Capital, Program Control and Common Infrastructure projects were re-allocated to areas who use those funds

## Slide 7: 2016 – 2017 Project Funding
On 6/9/2015, the Board approved ERCOT’s 2016/2017 budget request that included additional project funds for a data center hardware refresh
    $20M for data center hardware refresh (each year)
“PPL” funds remain consistent with recent years
  $4M for revision requests (each year)
  ~$2M for regulatory (each year)
  Remaining project funds ($14M-$16M each year) for:
    Internal Enhancements
    Other Tech Foundation (software upgrades, etc.)

## Slide 8: 2015 Retail Project Update
  Questions?