## Slide 1
Project Update and Summary of Project Priority List (PPL) Activity
August 13, 2015

## Slide 2: 2015 Project Update – Agenda
  Project Portfolio Update p. 3-6
    Recent/Upcoming Project Highlights
    2015 Release Targets
    2016 Release Targets
    2015 Project Spending Update
  Appendix
    Project Portfolio Gantt Chart p. 7-14
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index

## Slide 3: Recent / Upcoming Project Highlights
2015 August Release – Week of 8/17/2015 In Flight
  SCR771 – ERCOT System Change Allowing Independent Master QSE to Represent Split Generation Resources
2015 September Release – Week of 9/21/2015 In Flight
  NPRR589(b) – Ancillary Service Offers in the SASM
  NPRR698 – Clarifications to NPRR595, RRS Load Resource Treatment In ORDC
2015 October Release – Week of 10/19/2015 In Flight
  NPRR588 – Clarifications for PV Generation Resources
  NPRR615 – PVGR Forecasting
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2015 Release Targets – Board-Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
NPRR589(b) – S&B portion
SCR774(b) – Addition of Comments field
(a), (b), etc. indicates multiple phases
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
February 2/2 – 2/12 | March 3/23 – 3/27 | June |  | August 8/17 – 8/21 | September 9/21 – 9/25 | December 12/7 – 12/11
NPRR500 SCR772 | SCR778 SCR779 | NPRR559 NPRR597 NPRR601 NPRR639 | NPRR543 NPRR626 NPRR645 NPRR665 SCR774(b) SCR775 OBD (Shadow Price Caps) | SCR771 | NPRR553 NPRR588 NPRR589(b) NPRR615 NPRR698 NPRR588 NPRR615 | NPRR419 NPRR556 NPRR573 RMGRR126 RRGRR003
2 | 2 | 11 |  | 1 | 4 | 5
2015 TBD Items (and month they became “TBD”)
E
NS
I
I
NS
NS
Project Status Codes: NS = Not Started, I = Initiation, P = Planning, E = Execution, H = On Hold
Aug 2014 | Oct 2014 | Dec 2014 | Jan 2015 | Mar 2015 | Apr 2015 | Jun 2015
NOGRR084 | NPRR327 H | NPRR272, SCR777 H | NPRR210, NPRR664 | NPRR256 | NPRR568-ph2, NPRR644 | NPRR686
Late May
6/13 (CMM)
6/22 – 6/26
E
E
P
P
October
10/19 – 10/23

## Slide 5: 2016 Release Targets – Board-Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
NPRR484(Ph1b) – Remaining Phase 1 items
NPRR484(Ph2) – S&B portion of NPRR
(a), (b), etc. indicates multiple phases
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
February Dates TBD | March Dates TBD | June Dates TBD | August Dates TBD | September Dates TBD | December Dates TBD
NPRR495 NPRR515 NPRR553 NPRR617 NPRR680 | NPRR620 NPRR662 NPRR679 NPRR683 | NPRR493 NPRR519 | NPRR495 | NPRR219 NPRR439 SCR783 | SCR781
4 | 4 | 1 | 1 | 3 | 1
Project Status Codes: NS = Not Started, I = Initiation, P = Planning, E = Execution, H = On Hold
I
NS
I
P
P
E
NS
NS
NS
NS
NS
NS
NS
2016 TBD Items (and month they became “TBD”)
July 2015 | 
NPRR256, NPRR455, NPRR493 | 
NS

## Slide 6: 2015 Project Spending Update
2015 project budget = $21.65M
Reason: Minor Capital, Program Control and Common Infrastructure projects were re-allocated to areas who use those funds

## Slide 7: Business Integration Update – Appendix
  Appendix
    7/31/2015 Project Gantt
      In-flight items sorted by Project End Date
      “On Hold” projects listed separately
      “Not Started” items sorted by Project Start Date

## Slide 8
Project Portfolio Status – as of 7/31/2015

## Slide 9
Project Portfolio Status – as of 7/31/2015

## Slide 10
Project Portfolio Status – as of 7/31/2015

## Slide 11
Project Portfolio Status – as of 7/31/2015

## Slide 12
Project Portfolio Status – as of 7/31/2015

## Slide 13
Project Portfolio Status – as of 7/31/2015

## Slide 14
Project Portfolio Status – as of 7/31/2015