## Meeting Notes
TDTWG Meeting Notes / Action Items
2015-07-15
Agenda Item: | Decision / Resolution | Action Items :
June Meeting Notes | Reviewed June meeting notes | Isabelle will make revision/updates to the notes and send out to the listserv
ERCOT System Instances (Outages and Failure) review November and December | Review Dave Pagliai with ERCOT provided the System Instances (Outages and Failure) for June. 06/05/15 – Find Transaction for historic searches (greater than 1 year) unavailable 23 minute 06/18/15 – Find Transaction for historic searches (greater than 1 year) unavailable 11 minutes 06/25/15 – MIS Find ESIID and Find Transaction slow response times for 120 minutes w/transactions still available | ERCOT will present the report the June metrics at RMS in August
Review MarkeTrak Monthly Performance | API Query list - 12 due to database upgrade.API update 14.672 Ercot is looking at the tool to determine source of impact. GUI response continues to be good. | ERCOT is looking at the tool to determine source of impact. At the end of July ERCOT will review the data and discuss new methods to collect and report the data
MarkeTrak Premature Transition Issue Update - Action Item from May | ERCOT provided answers in the MTTF meeting held on July 13th. ERCOT confirmed no change to R5 only to begin supporting IE11 and to confirguarion guide. ERCOT will confirm if any additional updates will be provided at TAC for IE | No new issues to report. Vendor suggests considering an upgrade of their product. Although the vendor support will continue, the last upgrade performed was in 2009 which was the latest stable version at that time.
MarkeTrak Upgrade Discussion | Dave Pagliai presented the slide deck discussed at the July 13, 2015 MTTF meeting. No current system risk if not updated to latest version. Detailed analysis required to determine impacts to user base | MarkeTrak TF would like to stay with current version/implementation Revisit upgrade discussion in 6-12 months
ERCOT Test Environment | SCR - Posted with SCR #786 went and has been submitted via PRS list. and will be at next months PRS for language review. Updates on the SCR can be obtain by joining PRS listserv Next steps: • PRS on 7/16 language review • PRS on 8/13 for IA review • TAC on 8/27 • ERCOT Board on 10/13 • **Effective date 11/1/15". Next steps: • PRS on 7/16 language review • PRS on 8/13 for IA review • TAC on 8/27 • ERCOT Board on 10/13 • **Effective date 11/1/15". | TDTWG leadership to Add as topic to the Agenda monthly under the **Ad hoc items
NAESB Upgrade Recommendation | Catherine -provided a presentation with background of the initial focus NAESB upgrade and ERCOT's recommendation to post poning the effort until regulatory,security or technology requirements necessitate the change. At that time a new SCR should be submitted to upgrade the latest version of NAESB (current version is 3.0). Note : if the market feels that the benefits outweight the cost, then ERCOT will be happy to faciliate the creation of the new SCR. | Recommendation to NAESB upgrade was withdrawn on August 7, 2014 and presented to RMS for withdrawal on August 5, 2014. Isabelle will confirm with RMS leadership if there needs to be any additional formal withdrawl of the recommendation
Ad Hoc items | No additional items to discuss.
Next Meeting | August 18, 2015 Face to Face
Attendees- WebEx
Vikrum Gupta ERCOT
Isabelle Durham CNP
Lindsay Butterfield
Monica Jones NRG/Reliant
Dave Pagliai (ERCOT)
Diane Rehfeldt (TNMP)
Catherine Meiners (ERCOT)
Dave Michelsen