## Sheet1
TX SET Meeting Notes / Action Items
July 20 - 21, 2015
Agenda Item: | Decision / Resolution | Action Items :
June 2015 Meeting Notes | No changes were made to the meeting notes | Diana to have the final posted to the June meeting page.
Mass Transition/Default-POLR Rule | • RMS assignment to discuss Mass Transition— Possible POLR Rule change from two days out to one day out.
AMWG Update
Other discussion
Market Test Flight 0214 Update | ERCOT to provide flight update No update received
TX SET Procedures | On Hold-Discuss reline changes sent to the TXSET listserv for review | Leave current issue process in tact and continue to review document to identify where additional process improvements can be made
Texas Market Test Plan Review
• Review ERCOT updates • Review prior, during and after responsibility Sections • General Document Review | Texas SET continued to review, organize and modify the language in the TMTP. | o ERCOT to begin building content for the Pre-Flight Activities, Flight Responsibilities and Flight Requirements sections.  CRs Adding a DUNS +4  New TDSP  Existing TDSP  Flight Breakdown  NOIE o Kyle Patrick, NRG to begin building content for the Flight Requirements, New MP section.
RMS Updates
RMGRR130, Alignment of Section 7, Market Processes, with TDSP Terms and Conditions Tariff Effective 01/15/2015—RMS approved. TAC will vote at their July 30, 2015 meeting. | The Texas SET Chair reminded Texas SET members of the governance timeline for the RMGRR
Flight 0615 Update | ERCOT provided a brief update on Flight 0615 and stated that the Flight is almost complete.
ERCOT
RMS assignments
RMGRR132, NOIE Disconnect and Reconnect Process—Review changes made at June meeting and make final recommendation to RMS. | o Texas SET members expressed concern that some issues surrounding the RMGRR should be addressed by the PUCT and ERCOT as opposed to Texas SET.  One Member stated that there are PUCT rules that allow TDSPs to disconnect Competitive Retailers’ customers, but could find nothing that allows the TDSPs to disconnect NOIEs’ customers.  Some Texas SET members stated that the specific scenario in question also contains reliability issues because the customer also produces load that feeds into ERCOT transmission lines. | The Texas SET Chair will request that RMS leave this RMGRR tabled and referred to Reliability and Operations Subcommittee (ROS). • ERCOT stated that they will file comments to request the reliability question be referred to ROS if it is the wish of RMS.
New Entrant Documentation—Procedures and Documentation Location | No action
Add Master Customer List (MCL) guide back to the Texas SET Guides | No action
Discussion Items on Hold
Texas SET Release Discussion | No action
RMG Safety Net timelines | No action
REP Certification Matrix—Long-term solution | No action
Next Meeting | August 19th Rm 168 ERCOT Met Center August 20th Rm 101 ERCOT Met Center
Attendees
Diana Rehfelt TNMP | Kathryn Thurman ERCOT` | Becky Taylor CNP
Taylor Woodruff ONCOR | Kathy Scott CNP | Rob Bevil NRG
Kyle Patrick NRG | Sarah Heselmeyer ERCOT | Carolyn Reed CNP
Paul Yockey ERCOT | Jim Lee AEP | Lindsay Butterfield ERCOT
WebEx
Barbara Goubeaud EC Infosystems | Connie Hermes NEC | Jasmine Thom (CES)
Amy Rafferty ESG | Mary Sithihao Stream Energy | Susan Young DE
Stephen Wilson SU | Teresa Rodriquez Stream Energy | Veronica Bahcivanji GEXA