| Flight Schedule for Version 4.0 Flights in 2016 | 0216 |
| --- | --- |
| Activity | Calendar Date |
| Notice from ERCOT Retail Client Services of the next flight for Retail Market Testing sent to ERCOT lists.ercot.com distribution | Dec. 16, 2015 |
| Signup begins | Jan. 13, 2016 |
| IN-FLIGHT SIGNUP DEADLINE The following 4 steps must be completed by 5pm CPT on the deadline for New MPs: CR must have submitted ERCOT LSE Application and Application Fee CR must have filed for PUC REP Certification TW updated on ERCOT Retail Testing Website Send an e-mail of intent to test to ERCOT at: RetailMarketTesting@ercot.com The following steps must be completed by 5pm CPT on the deadline for Current MPs: TW updated on ERCOT Retail Testing Website Send an email of intent to test to ERCOT at: RetailMarketTesting@ercot.com | Jan. 20, 2016 |
| ADHOC SIGNUP DEADLINE (Current MPs Only, subject to Flight Administrator and TDSPs’ Approval) The following steps must be completed by 5pm CPT on the deadline for current MPs: TW updated on ERCOT Retail Testing Website Send an email of intent to test to ERCOT at: RetailMarketTesting@ercot.com Market Participant is required to complete their connectivity and/or penny tests by 5:00 PM CPT March 25, 2016. All scripts are expected to be completed by 5:00 PM CPT April 8, 2016. | Mar. 18, 2016 |
| ERCOT Retail Client Services verifies that each new Testing Participant has completed Registration testing requirements with ERCOT | Jan. 22, 2016 |
| Verification and communication from PUCT Staff that Testing Participants intending to test have applied for REP Certification | Jan. 22, 2016 |
| Communication from ERCOT Flight Administrator of Testing Participants to each TDSP | Jan. 22, 2016 |
| MPs to start scheduling connectivity | Jan. 25, 2016 |
| TDSPs and ERCOT have completed communication of connectivity testing schedule to each Trading Partner | Jan. 26, 2016 |
| Black out period, as defined in the TMTP, ends | Jan. 26, 2016 |
| Connectivity and Penny (if applicable) Testing begins for all Testing Participants | Jan. 26, 2016 |
| TDSPs communicate Test bed load to Trading Partners and ERCOT | Feb. 16, 2016 |
| Day 1 Transactions flow | Feb. 22, 2016 |
| Flight tentatively scheduled to conclude | Mar. 4, 2016 |
| Contingency/Adhoc Period begins (Adhoc Testing only available for Current MPs) | Mar. 7, 2016 |
| Contingency/Adhoc Testing scheduled to conclude for Flight (black out period, as defined in the TMTP, starts) | Apr. 22, 2016 |

| Flight Schedule for Version 4.0 Flights in 2016 | 0616 |
| --- | --- |
| Activity | Calendar Date |
| Notice from ERCOT Retail Client Services of the next flight for Retail Market Testing sent to ERCOT lists.ercot.com distribution | Apr. 15, 2015 |
| Signup begins | May 18, 2016 |
| IN-FLIGHT SIGNUP DEADLINE The following 4 steps must be completed by 5pm CPT on the deadline for New MPs: CR must have submitted ERCOT LSE Application and Application Fee CR must have filed for PUC REP Certification TW updated on ERCOT Retail Testing Website Send an e-mail of intent to test to ERCOT at: RetailMarketTesting@ercot.com The following steps must be completed by 5pm CPT on the deadline for Current MPs: TW updated on ERCOT Retail Testing Website Send an email of intent to test to ERCOT at: RetailMarketTesting@ercot.com | May 25, 2016 |
| ADHOC SIGNUP DEADLINE (Current MPs Only, subject to Flight Administrator and TDSPs’ Approval) The following steps must be completed by 5pm CPT on the deadline for current MPs: TW updated on ERCOT Retail Testing Website Send an email of intent to test to ERCOT at: RetailMarketTesting@ercot.com Market Participant is required to complete their connectivity and/or penny tests by 5:00 PM CPT July 15, 2016. All scripts are expected to be completed by 5:00 PM CPT July 29, 2016. | July 08, 2015 |
| ERCOT Retail Client Services verifies that each new Testing Participant has completed Registration testing requirements with ERCOT | May 27, 2016 |
| Verification and communication from PUCT Staff that Testing Participants intending to test have applied for REP Certification | May 27, 2016 |
| Communication from ERCOT Flight Administrator of Testing Participants to each TDSP | May 27, 2016 |
| MPs to start scheduling connectivity | May 31, 2016 |
| TDSPs and ERCOT have completed communication of connectivity testing schedule to each Trading Partner | May 31, 2016 |
| Black out period, as defined in the TMTP, ends | May 31, 2016 |
| Connectivity and Penny (if applicable) Testing begins for all Testing Participants | May 31, 2016 |
| TDSPs communicate Test bed load to Trading Partners and ERCOT | June 13, 2016 |
| Day 1 Transactions flow | June 20, 2016 |
| Flight tentatively scheduled to conclude | July 1, 2016 |
| Contingency/Adhoc Period begins (Adhoc Testing only available for Current MPs) | July 5, 2016 |
| Contingency/Adhoc Testing scheduled to conclude for Flight (black out period, as defined in the TMTP, starts) | Aug. 12, 2015 |

| Flight Schedule for Version 4.0 Flights in 2016 | 1016 |
| --- | --- |
| Activity | Calendar Date |
| Notice from ERCOT Retail Client Services of the next flight for Retail Market Testing sent to ERCOT lists.ercot.com distribution | Aug. 10, 2016 |
| Signup begins | Sept. 7, 2016 |
| IN-FLIGHT SIGNUP DEADLINE The following 4 steps must be completed by 5pm CPT on the deadline for New MPs: CR must have submitted ERCOT LSE Application and Application Fee CR must have filed for PUC REP Certification TW updated on ERCOT Retail Testing Website Send an e-mail of intent to test to ERCOT at: RetailMarketTesting@ercot.com The following steps must be completed by 5pm CPT on the deadline for Current MPs: TW updated on ERCOT Retail Testing Website Send an email of intent to test to ERCOT at: RetailMarketTesting@ercot.com | Sept. 14, 2016 |
| ADHOC SIGNUP DEADLINE (Current MPs Only, subject to Flight Administrator and TDSPs’ Approval) The following steps must be completed by 5pm CPT on the deadline for current MPs: TW updated on ERCOT Retail Testing Website Send an email of intent to test to ERCOT at: RetailMarketTesting@ercot.com Market Participant is required to complete their connectivity and/or penny tests by 5:00 PM CPT November 4, 2016. All scripts are expected to be completed by 5:00 PM CPT November 18, 2016. | Oct. 28, 2016 |
| ERCOT Retail Client Services verifies that each new Testing Participant has completed Registration testing requirements with ERCOT | Sept. 16, 2016 |
| Verification and communication from PUCT Staff that Testing Participants intending to test have applied for REP Certification | Sept. 16, 2016 |
| Communication from ERCOT Flight Administrator of Testing Participants to each TDSP | Sept. 16, 2016 |
| MPs to start scheduling connectivity | Sept. 19, 2016 |
| TDSPs and ERCOT have completed communication of connectivity testing schedule to each Trading Partner | Sept. 19, 2016 |
| Black out period, as defined in the TMTP, ends | Sept. 20, 2016 |
| Connectivity and Penny (if applicable) Testing begins for all Testing Participants | Sept. 20, 2016 |
| TDSPs communicate Test bed load to Trading Partners and ERCOT | Oct. 3, 2016 |
| Day 1 Transactions flow | Oct. 10, 2016 |
| Flight tentatively scheduled to conclude | Oct. 21, 2016 |
| Contingency/Adhoc Period begins (Adhoc Testing only available for Current MPs) | Oct. 24, 2016 |
| Contingency Testing scheduled to conclude for Flight (black out period, as defined in the TMTP, starts) | Nov. 23, 2016 |