## Sheet1
TX SET Meeting Notes / Action Items
August 19 - 20, 2015
Agenda Item: | Decision / Resolution | Action Items :
July 2015 Meeting Notes | No Changes were made to the notes | Leadership to have the notes posted to the meeting page key documents.
Mass Transition/Default-POLR Rule | • RMS assignment to discuss Mass Transition— Possible POLR Rule change from two days out to one day out.
AMWG Update
Other discussion
Market Test Flight 0214 Update | ERCOT to provide flight update No update received
TX SET Procedures | On Hold-Discuss reline changes sent to the TXSET listserv for review | Leave current issue process in tact and continue to review document to identify where additional process improvements can be made
Texas Market Test Plan Review
• CERT TEST SIM Date Discussion as requested by TDTWG | TDTWG leadership and ERCOT requested that TX SET review the CERT Testing simulated date practice to determine if continuation of this practice is necessary. | Texas SET members are to discuss this question internally and provide feedback. Leadership will conduct a WebEx only call on August 31st from 11 AM to Noon for further discussion; then provide the findings to TDTWG leadership.
• Review ERCOT updates o Pre-Flight Activities Content o Flight Responsibilities Content o Flight Requirements Content  CRs Adding a DUNS +4  New TDSP  Existing TDSP  Flight Breakdown • NRG Content Review o Flight Requirements Content o New MP Section Content • Other Changes Review | Texas SET continued to review language and update the document where necessary. Texas SET saved the document as a blackline to be updated going forward as an original document until a hard draft is complete. | Leadership to send both the redlined and blacklined document to the meeting attendees. NRG to build content for: Flight Breakdown Flight Schedule ERCOT to build content for: Escalation Procedures Test to Production Checklist NOIE
RMS Updates
RMGRR130, Alignment of Section 7, Market Processes, with TDSP Terms and Conditions Tariff Effective 01/15/2015—TAC approved. | Leadership provided an update.
RMGRR132, NOIE Disconnect and Reconnect Process—RMS tabled and Golden Spread will continue to work with ERCOT and other parties to determine a solution. The issue is no longer assigned to Texas SET. | Leadership provided an update.
Flight 1015 Update
ERCOT | ERCOT provided an update of the current flight progress.
RMS assignments | No Action on any items
New Entrant Documentation—Procedures and Documentation Location
Add Master Customer List (MCL) guide back to the Texas SET Guides
Discussion Items on Hold | No Action on any items
Texas SET Release Discussion
RMG Safety Net timelines
REP Certification Matrix—Long-term solution
Next Meeting | September 16th Rm 168 ERCOT Met Center September 17th Rm 101 ERCOT Met Center
Attendees
Diana Rehfeldt TNMP | Kathryn Thurman ERCOT | Sarah Heselmeyer ERCOT
Paul Yockjey ERCOT | Kaci Jacobs TXU | Catherine Meiners ERCOT
Lindsay Butterfield ERCOT | Taylor Woodruff ONCOR | Jim Lee AEP
Kathy Scott CNP | Kyle Patrick NRG | Carolyn Reed CNP
Becky Taylor CNP
WebEx
Amy Rafferty ESG | Barbara Goubeaud EC Inforsystems | Carla Marquez CES
Mike Woolsey ONCOR | Suzanne Clark Liberty Power | Paula Shadle NEC
Teresa Rodriquez SGE | Rakhee Gupta TNMP | Deborah Croce
Sharon Galvin SGE