|  |  |  |  |  | System Planning |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | Monthly Status Report September 2015 |  |  |
|  |  |  | Report Highlights |  |  |  |  |  |  |
|  |  | - ERCOT is currently reviewing proposed transmission improvements with a total cost of $1.1 Billion. - Transmission Projects endorsed in 2015 total $319.8 Million. - All projects (in engineering, routing, licensing and construction) total approximately $6.66 Billion. - Transmission Projects energized in 2015 total about $429.7 Million. |  |  |  |  |  |  |  |

Table of Contents

1.	Regional Planning Group Project Reviews	1

2.	Planning Model Activities	2

3.	Other Notable Activities	3

# Regional Planning Group Project Reviews

- Duke-American Transmission Company has submitted the Phoenix project. This is a Tier 2 project that is estimated to cost $39 million. This project is currently under ERCOT independent review.

- Garland Power & Light has submitted the Greenville 138 kV tie project. This is a Tier 2 project that is estimated to cost $27 million. This project is currently under ERCOT independent review.

- AEPSC has submitted the Live Oak Transmission project. This is a Tier 2 project that is estimated to cost $33 million. This project has completed the ERCOT independent review and will be presented to ERCOT BOD in October.

- AEPSC has submitted the LRGV Area Transmission Improvements project. This is a Tier 1 project that is estimated to cost $621.5 million. This project is currently under ERCOT independent review.

- Oncor has submitted the Big Brown – Navarro 345 kV double-circuit upgrade project. This is a Tier 3 project that is estimated to cost $10.2 million. This project has been submitted for RPG comments.

- AEPSC has submitted the Hidalgo-Starr Transmission project. This is a Tier 1 project that is estimated to cost $151.1 million. This project is currently under ERCOT independent review.

- Lone Star has submitted the North Central 345 kV transmission project. This is a Tier 1 project that is estimated to cost $83.1 million. This is currently in the study mode.

- CPS Energy and Sharyland Utilities have jointly submitted the LRGV Import project. This is a Tier 1 project that is estimated to cost $643.7 million. This project is submitted for RPG comments.

- Sharyland Utilities has submitted the Panhandle Loop project. This is a Tier 1 project that is estimated to cost $145 million. This project is submitted for RPG comments.

# Planning Model Activities

The short term calendar of major planning model events follows:

- Aug 29, 2015	Began 2015 Update 1

- Oct 15, 2015	Complete 2015 Update 1 and Post TPIT

- Nov 6, 2015	Post Contingencies and Planning Data Dictionary

The following table shows updates since last month of interconnection projects that met Planning Guide section 6.9 (1) and were either modeled or not modeled based on submitted RARF data in accordance with Planning Guide section 6.9 (2).  A non-null value in the Project ID column signifies that the project was modeled and a null value means it was not modeled.  The Notes column may provide further explanation.

# Other Notable Activities

- ERCOT has completed the basecase reliability analysis of the 2015 Regional Transmission Plan (RTP). The resulting reliability cases and project list have been posted on the MIS Secure. ERCOT has also completed the short circuit analysis for the 2015 RTP. Results of the analysis have been communicated to affected TPs. ERCOT is currently working on preparation of sensitivity cases, and performing further studies such as multiple element outage analysis on the base cases.  Additionally, ERCOT is working with TSPs on Congestion Management Plans for identified reliability criteria violations for which a transmission project is identified but is not expected to be in place in time.  In addition to the reliability analysis, ERCOT is working on completing its economic project evaluation as part of the 2014 RTP Economic Analysis.

- ERCOT commenced stakeholder discussions on the 2016 Long Term System Assessment (LTSA) at the April RPG meeting. ERCOT facilitated its second and third 2016 LTSA scenario development workshops on July 13th and 14th, 2015. Stakeholders have identified eight potential scenarios that will be studied further in the 2016 LTSA.

- ERCOT has completed PUCT Panhandle transfer capability analysis and submitted the study report to PUCT on Septemer 18, 2015.

- ERCOT has completed the 2018 Future Year flat start case build on September 4, 2015.