## Sheet1
TX SET Meeting Notes / Action Items
September 16 - 17, 2015
Agenda Item: | Decision / Resolution | Action Items :
August 2015 Meeting Notes | No changes were made. | The Texas SET Chair will send to ERCOT to post to the August meeting page key documents.
Mass Transition/Default-POLR Rule | • RMS assignment to discuss Mass Transition— Possible POLR Rule change from two days out to one day out.
AMWG Update
Other discussion
Market Test Flight 0214 Update | ERCOT to provide flight update No update received
TX SET Procedures | On Hold-Discuss reline changes sent to the TXSET listserv for review | Leave current issue process in tact and continue to review document to identify where additional process improvements can be made
Texas Market Test Plan Review
• Review ERCOT updates o Pre-Flight Activities Content o Flight Responsibilities Content o Flight Requirements Content  Escalation Procedures  Test To Production Checklist  NOIE • NRG Content Review o Flight Breakdown o Flight Schedule • Other Changes Review | • Texas SET completed the draft Texas Market Test Plan (TMTP) changes. | The Texas SET Chair will send the draft language to ERCOT for formatting and language consistency.
| o ERCOT requested that the TDSPs provide feedback regarding a change to testing requirements for a Competitive Retailer (CR) that has successfully completed Flight Testing with some of the TDSPs and is requesting to add another TDSP’s service territory to that certification.  CRs currently have to complete a full set of test scripts during the “In-Flight” period of a Flight Test.  ERCOT is proposing that the CRs be allowed to complete a reduced amount of test scripts during the Ad-Hoc period of the Flight Test. | The Texas SET Chair will send an email to all the TDSPs requesting feedback by October 1st; then forward the results to ERCOT to make further changes to the TMTP if needed.
• Updated MSTK01—NEC | o The ERCOT Flight Administrator presented the updated MSTK01 testing script with changes suggested by Nueces Electric Cooperative (NEC).  Texas SET reviewed, made the changes and approved the script to be implemented in Flight 1015. | The ERCOT Flight Administrator will update the scripts on the ERCOT testing website.
RMS Updates
TAC / TAC Subcommittee Structural and Procedural Review update | The Texas SET Chair and RMS Chair provided some highlights of TAC's Review
2016 Market Meeting Calendar | Texas SET reviewed possible 2016 meeting dates and discussed the need for two-day meetings. | o Texas SET will revisit the meeting calendar in the 2nd quarter to determine if some of the meetings can be shortened to one day or held as WebEx only. o The Texas SET Chair will send the proposed dates to ERCOT to determine room and time availability.
Flight 1015 Update | ERCOT presented an update of the Flight 1015 statistics and timelines.
2016 Flight Schedule Review--ERCOT | Texas SET reviewed and made updates to the proposed 2016 Flight Schedule. | o The Texas SET Chair will send the proposed schedule to ERCOT to post for the October 6th RMS meeting. o Texas SET will request approval at that RMS meeting.
Texas SET Accomplishments Year Ending 2015
Preliminary discussion | • Texas SET reviewed and made changes to a preliminary list of 2015 Texas SET Accomplishments. | Texas SET will revisit the list at their November meeting to make further changes if needed.
Tampering Rebilling--Process Questions to TDSPs--NRG
• If tampering is discovered that spans six months or more how does your TDSP choose the 6 months that will be retracted and rebilled? Past  Present? Or Present  Past?
• Can you confirm the steps for tampering?
• Tampering is confirmed TDSP will:
1. Disconnect and restore meter back to normal condition 650_01 & 650_02 2. Reconnect after restoration  650_01 & 650_02 3. Switch Hold applied  814_20 & ESI will be included in FTP file 4. Tampering charged to customer  810_02
• Will every tampering customer receive a standalone 810_02 tampering charge? When would that standalone 810_02 with a tampering charge be sent to the CR? Before next periodic read? | o The Texas SET Chair sent an email prior to the meeting requesting feedback from the TDSPs on their individual processes. o The Texas SET Chair created a matrix with each TDSP’s feedback. o Texas SET determined there was no need to review the list of questions and answers at the meeting. | The Texas SET Chair will send the matrix to NRG, TXU and the TDSPs.
TNMP CIS Migration Outage Discussion
| TNMP personnel addressed concerns expressed by NRG and TXU; then provided clarifying information regarding the type of upgrade that is to be migrated during the September 26th through 27th outage. | o TNMP agreed to send an additional notice clarifying the type of upgrade to the market. o The RMS Chair requested that TNMP provide the same clarifying information to the market at the October 6th RMS meeting.
o Texas SET discussed various types of system changes that may require Market Testing. o Texas SET attendees stated that the market should use the notification timing requirements listed in the Commercial Operations Guide to determine how far in advance a Market notice should be sent.
TDSP Retire ESI ID Process discussion
• TXU requested clarification of TDSP procedures used to retire ESI IDs at ERCOT and how quickly the update to ERCOT is sent after the ESI ID is retired. o Texas SET discussed the need, if any, to place timing requirements in the RMG. o The TDSPs stated that the process use to retire an ESI ID is TDSP specific. o Texas SET determined that no changes should be made to the RMG.
NRG Date Change / Cancellation One-Day Window discussion
| NRG discussed the desire to remove the One-Day window for Date Changes and Cancellations for AMSR metered ESI IDs only. o ERCOT processes currently reject Date Changes or Cancellations if they are received the day before a switch, move-in or move-out is scheduled to complete. | Texas SET requested that NRG submit an issue to ERCOT for discussion at a future Texas SET meeting.
RMS assignments
New Entrant Documentation—Procedures and Documentation Location
Add Master Customer List (MCL) guide back to the Texas SET Guides
Discussion Items on Hold
Texas SET Release Discussion
RMG Safety Net timelines-- The RMS Chair provided an update of the PUCT feedback received related to the Safety NET Rule and Retail Market Guide (RMG) Safety Net process changes. | The PUCT Rule §25.487 does nothing to restrict a tighter timeline for submitting safety nets in the market. | Texas SET will revisit the changes needed to update the Safety NET Section of the RMG using the redline document from January 22, 2015 at their October 19th – 20th meeting.
REP Certification Matrix—Long-term solution
Next Meeting | October 19th Rm 168 ERCOT Met Center October 20th Rm 102 ERCOT Met Center
Attendees
Diana Rehfeldt TNMP | Kathryn Thurman ERCOT | Sarah Heselmeyer ERCOT
Paul Yockey ERCOT | Kaci Jacobs TXU | Becky Taylor CNP
Taylor Woodruff ONCOR | Jim Lee AEP | Kyle Patrick NRG
Kathy Scott CNP | Carolyn Reed CNP | Lindsay Butterfield ERCOT
WebEx Only
Carla Markez CES | Sheryl Mejia | Amy Rafferty ESG
Barbara Goubeaud EC Infosystems | Mike Wissink Softsmiths | Cliff Crouch PUCT
Tracee