## Current
Item # | Short Description | Notes | Deliverable | New/ Modification/ Delete | Source | Date Added | Assigned to | Priority | Status
1 | 60-Day Disclosure data | Offer curves in report have zero values that ought to be nulls | ext/rpt | Modification | MISUG | 2015-06-25 |  | HIGH | CR 56057, slated for R1 2016
2 | Load Forecast Distribution Factor report | What changes need to be made in this report? | ext/rpt | Modification | MISUG | 2015-06-25 |  | HIGH | CR 56082, slated for R6 2015.

## Closed
Item # | Short Description | Notes | Deliverable | New/ Modification/ Delete | Source | Date Added | Assigned to | Priority | Status
1 | DCTIE schedules - Historical information | Closed until NPRR is approved | ext/rpt | New | MISUG | 2015-06-25 |  |  | Active Power Investments has expressed interest in bringing forward an NPRR for this information
2 | List of marginal units | Closed until NPRR is approved | ext/rpt | New | Active Power Investments LLC | 2015-06-25 |  |  | Active Power Investments has expressed interest in bringing forward an NPRR for this information
3 | AS capacity monitor - Historical Information | Closed until NPRR is approved |  | New | MISUG | 2015-06-25 |  |  | Active Power Investments has expressed interest in bringing forward an NPRR for this information