## Slide 1
Project Update and Summary of Project Priority List (PPL) Activity
November 12, 2015

## Slide 2: 2015 Project Update – Agenda
  Project Portfolio Update p. 3-6
    Recent/Upcoming Project Highlights
    2015 Release Targets
    2016 Release Targets
    2015 Project Spending Update
    2016 Project Spending – Initial Forecast
  Appendix
    Project Portfolio Gantt Chart p. 7-13
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index

## Slide 3: Recent / Upcoming Project Highlights
2015 October Release – Week of 10/19/2015 Complete
  NPRR556 – Resource Adequacy During Transmission Equipment Outage
  NPRR595 – RRS Load Resource Treatment In ORDC
  NPRR698 – Clarifications to NPRR595, RRS Load Resource Treatment In ORDC
  NPRR706 – Restore the ability to use Physical Responsive Reserve Capability as an Indicator of Available Frequency-Responsive Capacity
  NPRR710 – Removal of ORDC Phase 2 Language and Modification to HASL Calculation
2015 December Release – Week of 12/7/2015 In Flight
  NPRR680 – Allow QSEs to Self-Arrange AS Quantities Greater Than Their AS Obligation
  NPRR686 – Changing the IRR Forecast from Next 48 Hours to Next 168 Hours
    Wind elements
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2015 Release Targets – Board-Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
NPRR589(b) – S&B portion
NPRR686(a) – Wind portion
SCR774(b) – Addition of Comments field
(a), (b), etc. indicates multiple phases
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
February 2/2 – 2/12 | March 3/23 – 3/27 | June |  | September 9/7 – 9/11 | October 10/19 – 10/23 | December 12/7 – 12/11
NPRR500 SCR772 | SCR778 SCR779 | NPRR559 NPRR597 NPRR601 NPRR639 | NPRR543 NPRR626 NPRR645 NPRR665 SCR774(b) SCR775 OBD (Shadow Price Caps) | SCR771 NPRR589(b) NPRR701 | NPRR556 NPRR595 NPRR698 NPRR706 NPRR710 | NPRR680 NPRR686(a)
2 | 2 | 11 |  | 3 | 5 | 2
2015 TBD Items (and month they became “TBD”)
E
E
Project Status Codes: NS = Not Started, I = Initiation, P = Planning, E = Execution, H = On Hold
Aug 2014 | Oct 2014 | Dec 2014 | Jan 2015 | Jun 2015
NOGRR084 | NPRR327 H | NPRR272, SCR777 H | NPRR210, NPRR664 | 
Late May
6/13 (CMM)
6/22 – 6/26
E
E
E
E
E
September
9/21 – 9/25

## Slide 5: 2016 Release Targets – Board-Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
NPRR484(Ph1b) – Remaining Phase 1 items
NPRR484(Ph2) – S&B portion of NPRR
NPRR686(b) – Solar portion
(a), (b), etc. indicates multiple phases
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
February Dates TBD | March Dates TBD | June Dates TBD | August Dates TBD | September Dates TBD | December Dates TBD
NPRR515 NPRR553 NPRR588 NPRR615 NPRR686(b) NPRR700 RMGRR126 | NPRR515 NPRR617 NPRR620 NPRR662 NPRR679 NPRR700 RRGRR003 EMS Upgrade | NPRR419 RMGRR126 | NPRR495 NPRR662 | NPRR219 NPRR573 NPRR714 SCR783 | NPRR210 NPRR272 RRGRR003 RRGRR006 SCR781
4 | 4 | 2 | 2 | 4 | 5
Project Status Codes: NS = Not Started, I = Initiation, P = Planning, E = Execution, H = On Hold
I
H
NS
I
NS
NS
NS
NS
P
E
E
E
E
E
I
NS
I
I
NS
2016 TBD Items (and month they became “TBD”)
July 2015 | September 2015 | October 2015
 |  | NPRR439 I, NPRR519 I, NPRR620 I, NPRR683 I
NS
NS
May
5/23 – 5/27
EMS Upgrade “Chill”
CMM Bundle
Release Date TBD

## Slide 6: 2015 Project Spending Update
2015 Project Budget = $21.65M
Any excess spending in 2015 will be offset by equal reductions in 2016 spending (ERCOT projects only)
December includes a Data Center Refresh hardware purchase that will be offset by 2016 Data Center funding

## Slide 7: 2016 Project Spending – Initial Forecast
2016 PPL Budget = $22.5M
“Potential Demand” includes internal ERCOT projects that have not been fully approved as well as 2015 excess project spending

## Slide 8: 2015 Project Update – Appendix
  Appendix
    10/31/2015 Project Gantt
      In-flight items sorted by Project End Date
      “On Hold” projects listed separately
      “Not Started” items sorted by Project Start Date

## Slide 9
Project Portfolio Status – as of 10/31/2015

## Slide 10
Project Portfolio Status – as of 10/31/2015

## Slide 11
Project Portfolio Status – as of 10/31/2015

## Slide 12
Project Portfolio Status – as of 10/31/2015

## Slide 13
Project Portfolio Status – as of 10/31/2015

## Slide 14
Project Portfolio Status – as of 10/31/2015