## Slide 1: SMT Update To AMWG
November 19, 2015

## Slide 2: Status Update of AMWG Change Requests

## Slide 3: Status of AMWG Change Requests
Delivered | To Be Delivered Zero $$ | Approved Awaiting Project Packaging | AMWG Reporting Options Under Review | RMS Approved Awaiting Categorization | JDOA Estimated Awaiting AMWG Review | Tabled RMS | AMWG Delayed | RMS Remanded back to AMWG | Pushed Back as Defect
2013 002 | 2013 014 | 2013 015 | 2013 001 | 2015 033 |  | 2014 018 | 2015 029 |  | 2015 022
2013 005 |  | 2015 019 | 2013 003 |  |  |  | 2015 030 |  | 
2013 006 |  | 2015 020 | 2013 004 |  |  |  | 2015 031 |  | 
2013 007 |  | 2015 023 | 2013 008 |  |  |  | 2015 032 |  | 
2013 009 |  | 2015 025 | 2013 010 |  |  |  | 2015 034 |  | 
2013 012 |  | 2015 026 | 2013 011 |  |  |  | 2015 038 |  | 
2013 013 |  | 2015 027 |  |  |  |  | 2015 040 |  | 
2013 016 |  | 2015 028 |  |  |  |  | 2015 041 |  | 
2013 017 |  | 2015 035 |  |  |  |  |  |  | 
2015 024 |  | 2015 036 |  |  |  |  |  |  | 
 |  | 2015 037 |  |  |  |  |  |  | 
 |  | 2015 039 |  |  |  |  |  |  | 
 |  | 2015 021 |  |  |  |  |  |  | 
 |  | 2015 042 |  |  |  |  |  |  | 
Total 10 | Total 1 | Total 14 | Total 6 | Total 1 | Total 0 | Total 1 | Total 8 | Total 0 | Total 1

## Slide 4
AMWG Change Request | AMWG CR Document | Status | Categorization and Estimated Delivery Date | Estimated Cost
AMWG CR 2013 001 – Report for AMWG Data Monitoring – Data Completeness Measurements |  | Estimate Complete & RMS Approved 3/3/15 | Reporting Options Under Review | Small (20-40)
AMWG CR 2013 002 – Reports for AMWG Data Monitoring – Data Timeliness Measurements |  | Implemented | Q2 2014 Delivered | Included in Maintenance Contract
AMWG CR 2013 003 – Reports for AMWG Data Monitoring – Measurement of Percentage of Actual Meter Reads |  | Estimate Complete & RMS Approved 3/3/15 | Reporting Options Under Review | Small (20-40)
AMWG CR 2013 004 – Reports for AMWG Data Monitoring – Measurement of Estimates |  | Estimate Complete & RMS Approved 3/3/15 | Reporting Options Under Review | Medium (40-60)
AMWG CR 2013 005 – Reports for AMWG Data Monitoring – Number of SMT Help Desk Tickets Monthly by Ticket Type |  | Implemented | Q2 2014 Delivered | Included in Maintenance Contract
AMWG CR 2013 006 – Reports for AMWG Data Monitoring – Availability of SMT API |  | Implemented | Q2 2014 Delivered | Included in Maintenance Contract
AMWG CR 2013 007 – Reports for AMWG Data Monitoring – Availability of SMT FTPS |  | Implemented | Q2 2014 Delivered | Included in Maintenance Contract
AMWG CR 2013 008 – Reports for AMWG Data Monitoring – Average Time to Deliver HAN Messages |  | Estimate Complete & RMS Approved 3/3/15 | Reporting Options Under Review | Small (20-40)
AMWG CR 2013 009 – Reports for AMWG Data Monitoring – Number of Accounts by Type |  | Implemented | Q2 2014 Delivered | Included in Maintenance Contract
AMWG CR 2013 010 – Reports for AMWG Data Monitoring – Number of Reports Requested by GUI (Portal) and Number of FTPS Accesses |  | Estimate Complete & RMS Approved 5/6/15 | Reporting Options Under Review | Medium (40-60)
AMWG Change Requests

## Slide 5
AMWG Change Request | AMWG CR Document | Status | Categorization and Estimated Delivery Date | Estimated Cost
AMWG CR 2013 011 – Average Time from HAN Provision Request to Meter Ready Status |  | Estimate Complete & RMS Approved 3/3/15 | Reporting Options Under Review | Small (20-40)
AMWG CR 2013 012 – Bypass redundant screen for Users with only one meter when accessing HAN device information |  | Implemented | Q4 2014 Delivered | Included in Third-Party
AMWG CR 2013 013 – Timeout on SMT takes user to “incorrect login” screen |  | Implemented | Q4 2014 Delivered | Included in Third-Party
AMWG CR 2013 014 – Allow SMT user to toggle between 15-Minute Reads and Daily Reads without having to reset the date range |  | Designed | December 2015 Next Release | Included in Usability
AMWG CR 2013 015 – Expand Daily Usage Graph to show 35 days of daily usage on the SMT GUI |  | Estimate Complete & RMS Approved 3/3/15 | 2 Important Awaiting Packaging | Medium (40-60)
AMWG CR 2013 016 – Capability for RORs to grant access to vendors on their behalf to the ROR’s customers via API (energy usage, HAN messaging , and HAN provisioning) and FTPS files |  | Implemented | Q3 2014 Delivered | Included in Maintenance Contract
AMWG CR 2013 017 – REP API for Energy Usage on SMT (Backfill of Historical Usage Data for Existing Customers- “Interim” Older infrastructure prior to May 2015 unable to meet required CR 017 volume ) | See Below CR 2013 017 FINAL | Implemented with performance less than requested in CR | Q4 2013 Delivered | Included in SMT Maintenance Contract
AMWG CR 2013 017 – REP API for Energy Usage on SMT (Subscription for New Customer Historical Usage – “Interim” Older infrastructure prior to May 2015 unable to meet required CR 017 volume ) | See Below CR 2013 017 FINAL | Implemented with performance less than requested in CR | Q2 2014 Delivered | Included in Maintenance Contract
AMWG CR 2013 017 – REP API for Energy Usage on SMT – FINAL - On May 2015 the new SMT infrastructure was implemented which enabled SMT to support the required CR 017 volumes) |  | New SMT infrastructure meets performance requirements in the CR | Q2 2015 Delivered | Delivered 2015
AMWG CR 2014 018 – Add Generation Data to the SMT Portal View |  | JDOA Estimate Completed | RMS Tabled 6/2/15 RMS Tabled 8/4/15 | Medium (40-60) Graph and Table Small (20-40) Table Only
AMWG Change Requests (Cont.)

## Slide 6
AMWG Change Request | AMWG CR Document | Status | Categorization and Estimated Delivery Date | Estimated Cost
AMWG CR 2015 019 – Relocate Various SMT User Guides from the Authenticated Site to the Unauthenticated Site |  | JDOA Estimate Completed | 2 Important Awaiting Packaging | Small (20-40)
AMWG CR 2015 020 – Add Customer Type in the Customer Information Section in the View / Edit Agreement Page |  | JDOA Estimate Completed | 3 Nice to Have Awaiting Packaging | Medium (40-60)
AMWG CR 2015 021 – Improve REP of Record Search Criteria During the Customer Registration Process |  | Estimate Complete & RMS Approved 5/6/15 | 1 Critical Awaiting Packaging | Medium,(40-60)
AMWG CR 2015 022 – Keep Selected ROR Visible During Customer Registration |  | JDOA Estimate Completed | Push Back as Defect | Small (20-40)
AMWG CR 2015 023 – Allow Entry of Multiple ESIIDs During Customer Registration Process |  | JDOA Estimate Completed | 3 Nice to Have Awaiting Packaging | High (60-120)
AMWG CR 2015 024 – Third Party Access Renew Energy Data Agreement After One Year |  | JDOA Estimate Completed | Q4 2015 Delivered | 0 Dollar
AMWG CR 2015 025 – Third Party User Experience Add Identifying Data Fields in the Report Request Status Page |  | JDOA Estimate Completed | 2 Important Awaiting Packaging | High (60-120)
AMWG CR 2015 026 – SMT Functionality Display Portal Message when Report Can Not be Displayed in the SMT Portal Page |  | JDOA Estimate Completed | 2 Important Awaiting Packaging | Minor (0-20)
AMWG CR 2015 027 – SMT Functionality Allow Specific Date Entry on the Export Report Screen |  | JDOA Estimate Completed | 3 Nice to Have Awaiting Packaging | Small (20-40)
AMWG CR 2015 028 – SMT Functionality Allow ESIIDs to be Copied and Pasted into the ESIID Box on the Usage Page |  | JDOA Estimate Completed | 3 Nice to Have Awaiting Packaging | Minor (0-20)
AMWG CR 2015 029 – This Party Allow Third Parties to Utilize an API for On Demand Data Requests |  | Estimate Complete & RMS Approved | AMWG Delayed | High (60-120)
AMWG Change Requests (Cont.)

## Slide 7
AMWG Change Request | AMWG CR Document | Status | Categorization and Estimated Delivery Date | Estimated Cost
AMWG CR 2015 030 – Support multiple RORs during CSV file meter upload |  | JDOA Estimate Completed | AMWG Delayed | High (60-120)
AMWG CR 2015 031 – Allow only current ROR for account registration validation and meter add validation |  | JDOA Estimate Completed | AMWG Delayed | High (60-120)
AMWG CR 2015 032 – Support SFTP protocol for SMT integration |  | Investigation Complete | AMWG Delayed | High (60-120)
AMWG CR 2015 033 – Provide user id and password rules up front on UI registration page |  | JDOA Estimate Completed | RMS Approved Awaiting AMWG Categorization | Minor (0-20)
AMWG CR 2015 034 – Display the day of the week in addition to the date on usage reports |  | JDOA Estimate Completed | AMWG Delayed | Medium (40-60)
AMWG CR 2015 035 - Provide a customer-selected option to receive a monthly usage report via email |  | Estimate Complete & RMS Approved | 2 Important Awaiting Packaging | Medium (40-60)
AMWG CR 2015 036 – Rename Overview tab to Home |  | Estimate Complete & RMS Approved | 2 Important Awaiting Packaging | Minor (0-20)
AMWG CR 2015 037 – Remove SMT Demo from Private Site for REPs, TDSPs, and Third Parties |  | Estimate Complete & RMS Approved | 2 Important Awaiting Packaging | Minor (0-20)
AMWG CR 2015 038 – Provide a “Hold” capability on Third Party accounts to reactivate usage until the Third Party has integrated with FTPS and API |  | JDOA Estimate Completed | AMWG Delayed | High (60-120)
AMWG CR 2015 039 – Provide more detail for Third Party Agreement Invitation Error Messages |  | Estimate Complete & RMS Approved | 2 Important Awaiting Packaging | Medium (40-60)
AMWG CR 2015 040 – Improve SMT Administration Functionality for TDSPs, RORs, Third Parties, and Businesses |  | JDOA Estimate Completed | AMWG Delayed | 5 Functions Small, Small, Zero, Medium, High
AMWG Change Requests (Cont.)

## Slide 8
AMWG Change Request | AMWG CR Document | Status | Categorization and Estimated Delivery Date | Estimated Cost
AMWG CR 2015 041 – Allow Enrollment for New Customer 12 Month History for Third Parties |  | RMS Remanded back to AMWG for Further Discussion | AMWG Delayed | Medium (40-60)
AMWG CR 2015 042 – Automate Machine to Machine Consumption of Third Party Agreement Information |  | RMS Approved 8/4/15 | 2 Important Awaiting Packaging | Med / High (80)
AMWG Change Requests (Cont.)

## Slide 9: Rough Order Of Magnitude (ROM) Estimate of Effort Classification
These are rough order of magnitudes and do not include project ramp-up and testing effort (SIT & UAT) and only assumes unit testing.
Actual estimates could vary significantly depending on requirements.
Ramp-up and testing would be 20 to 40% of the overall effort
Overall project cost will vary based on efficiency gains from packaging like functionality
Change Type | ROM
MINOR | 0 – 20 K
SMALL | 20 – 40 K
MEDUIM | 40 – 60 K
HIGH | 60 – 120 K
VERY HIGH | Over 120 K

## Slide 10: Update on SMT December 2015 Minor Release to Correct Deficiencies and Usability Defects

## Slide 11: SMT Minor Release to Correct Deficiencies and Usability Defects December, 2015
Planned Release for December 2015 SMT to include the following:
Third Party scheduled report expiration alignment with customer energy data agreement
  In October 2015 SMT corrected the defect that energy data agreements could not be extended / renewed further out than a total of one year. Prior to this defect fix energy data agreements had to be requested again after one year.
  Currently Third Party Scheduled Reports for receipt of customer usage data contain an end date that will expire all scheduled reports within the previous one year limit
  Currently every single report would have to be individually re-scheduled one by one
  Scheduled Reports should automatically align themselves with the end date of the agreement
Invalid Request
  Currently an SMT user can receive an Invalid Request message for pressing keys while waiting for the landing page to load after entering log in credentials
  The message “It may take a few moments to authenticate your information and obtain your usage data” will be displayed after a user enters their log in credentials while they are waiting on the SMT landing page to be displayed
ROR validation simplification with friendly company name inputs from ERCOT –
  Currently SMT is receiving multiple help desk calls from customers trying to register but they cannot find their ROR in the drop search box down list
  SMT utilizes the ERCOT certified REP listing table and sometimes the legal name in that list does not match the brand name recognized by the customer
  SMT will be adding the ERCOT REP “friendly” / switch name table to the SMT customer ROR search function
  The customer can either select the legal name or brand name and both will allow the registration process to continue

## Slide 12: SMT Minor Release to Correct Deficiencies and Usability Defects December, 2015
Planned Release for December 2015 SMT to include the following:
Residential export report button incorrectly named
  Currently the Residential export report button for receiving usage reports is named Export Report in Excel
  The reports are actually exported in CSV format
  All other export report buttons are named correctly Export Report in CSV
  The Residential export report button will be renamed correctly to Export Report in CSV
Toggle between daily usage view and the interval read view on the SMT website without having to change the date range
  This is AMWG CR 2013 014 that was supposed to be delivered with the Third Party release in 2014
  Currently for usage views the SMT website utilizes the default of most recent day data
  If a user enters a date range in a usage view and then moves to another view that date range is lost and the default of most recent day data is inserted
  SMT will now maintain user entered date ranges across usage views on the website

## Slide 13: SMT Minor Release to Correct Deficiencies and Usability Defects December, 2015
Planned Release for December 2015 SMT to include the following:
Browser experience session management for SMT Login page
  Currently when a user is logged into SMT and opens another tab in the same browser to utilize a second session of SMT they must re-enter their log in credentials again into the new tab
  Per better industry practice when a user is already logged into a website and they open another tab for that same website they should not have to log in again
  SMT will be corrected so that if a user is already logged into SMT and they open a tab in the same browser for a second SMT session they will not have to enter login credentials. The user will be taken directly to the SMT landing page.

## Slide 14: Q&A Monthly SMT Reports to AMWG Data Through August 2015