|  |  |  |  |  | System Planning |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | Monthly Status Report October 2015 |  |  |
|  |  |  | Report Highlights |  |  |  |  |  |  |
|  |  | - ERCOT is currently reviewing proposed transmission improvements with a total cost of $1.02 Billion. - Transmission Projects endorsed in 2015 total $413.3 Million. - All projects (in engineering, routing, licensing and construction) total approximately $6.74 Billion. - Transmission Projects energized in 2015 total about $652.9 Million. |  |  |  |  |  |  |  |

Table of Contents

1.	Regional Planning Group Project Reviews	1

2.	Planning Model Activities	2

3.	Other Notable Activities	2

# Regional Planning Group Project Reviews

- Duke-American Transmission Company has submitted the Phoenix project. This is a Tier 2 project that is estimated to cost $39 million. This project is currently under ERCOT independent review.

- Garland Power & Light has submitted the Greenville 138 kV tie project. This is a Tier 2 project that is estimated to cost $19 million. This project has completed the independent review and ERCOT will issue the RPG approval letter.

- AEPSC has submitted the Live Oak Transmission project. This is a Tier 1 project that is estimated to cost $74.5 million. This project has completed the ERCOT independent review and the project was endorsed by the Board of Directors on Oct. 13, 2015.

- AEPSC has submitted the LRGV Area Transmission Improvements project. This is a Tier 1 project that is estimated to cost $621.5 million. This project is currently under ERCOT independent review.

- Oncor has submitted the Big Brown – Navarro 345 kV double-circuit upgrade project. This is a Tier 3 project that is estimated to cost $10.2 million. This project has been submitted for RPG comments.

- AEPSC has submitted the Hidalgo-Starr Transmission project. This is a Tier 1 project that is estimated to cost $151.1 million. This project is currently under ERCOT independent review.

- Lone Star has submitted the North Central 345 kV transmission project. This is a Tier 1 project that is estimated to cost $83.1 million. This is currently in study mode.

- CPS Energy and Sharyland Utilities have jointly submitted the LRGV Import project. This is a Tier 1 project that is estimated to cost $643.7 million. This is currently in study mode.

- Sharyland Utilities has submitted the Panhandle Loop project. This is a Tier 1 project that is estimated to cost $145 million. This is currently in study mode.

# Planning Model Activities

The short term calendar of major planning model events follows:

- Oct 15, 2015	Complete 2015 Update 1 SSWG cases and Post TPIT

- Nov 6, 2015	Post Contingencies and Planning Data Dictionary

- Dec 30, 2015	Extract Topology Processor output for 2015 Update 2 SSWG cases

The following table shows updates since last month of interconnection projects that met Planning Guide section 6.9 (1) and were either modeled or not modeled based on submitted RARF data in accordance with Planning Guide section 6.9 (2).  A non-null value in the Project ID column signifies that the project was modeled and a null value means it was not modeled.  The Notes column may provide further explanation.

# Other Notable Activities

- ERCOT has completed the reliability analysis of the 2015 Regional Transmission Plan (RTP). The resulting reliability cases and project list have been posted on the MIS Secure. The Congestion Management Plans to address any identified criteria violations for which a transmission project can not be implemented in time have been developed in collaboration with TPs.  ERCOT has also completed the short circuit analysis for the 2015 RTP. Results of the analysis have been communicated to affected TPs. ERCOT is currently performing multiple element outage analysis on the base and sensitivity cases.  In addition to the reliability analysis, ERCOT has completed its economic project evaluation as part of the 2015 RTP economic analysis. The results of this analysis are posted on the MIS Secure.

- ERCOT commenced stakeholder discussions on the 2016 Long Term System Assessment (LTSA) at the April RPG meeting. ERCOT facilitated its second and third 2016 LTSA scenario development workshops on July 13th and 14th, 2015. Stakeholders have identified eight potential scenarios that will be studied further in the 2016 LTSA.