## Slide 1: ERCOT Retail Market Training Task Force
Update to RMS
December 9th, 2015

## Slide 2: Retail 101 Progress
Retail Market 101 Training
Develop training in sections (not necessarily in the order of presentation)
Introduction , Roles & Responsibilities
Retail Transactions
Advanced Meter Technology – final review 1/11/16
History – final review 1/11/16
Market Rules – initial review 1/12/16
Data Transparency – initial review 1/12/16
GOAL: First instructor led class February 9th, 2016 aligned with flight testing

## Slide 3: MarkeTrak On-line Training Series Update
MarkeTrak on-line training – 4 modules complete! Updated Market Notice sent out on 12/4/2015 announcing …
  General Overview
  Switch Hold Removal
  Cancel With/Without Approvals
  Inadvertent Gains/Losses & Rescissions
  Usage & Billing – Finalizing Scripting
  Other D2D Subtypes
  GUI Reporting
  Bulk Insert
  Background Reporting
  Data Extract Variances (DEV) LSE Subtypes
  Data Extract Variances (DEV) Non-LSE Subtypes
  Emails and Notifications
  MarkeTrak Admin Functionality

## Slide 4: MarkeTrak On-line Training Series Success via ERCOT Learning Management System
How many market participants have viewed the three training modules*?
Which segment of the market do the viewers represent?
*via ERCOT LMS and does not include training outside of LMS
MT Module | # of Viewers
Overview | 39
Switch Hold | 27
Cancels | 25
IAGs | 5
TOTAL | 96
Market Segment | # of Viewers
LSE/REP | 35
TDSP | 37
QSE | 4
Other | 20
TOTAL | 96

## Slide 5: MarkeTrak On-line Training Series
How do I sign up?
Go to the ERCOT Training Website at http://www.ercot.com/services/training/
Select the course you are interested in attending
On the ‘Schedule/Registration’ tab, select the ‘enroll online’ link under ‘Registration’ to register for the course.
If you find the course is not listed under the Web-based training…
Go to ERCOT Training Website as shown above
Select the ‘ERCOT Learning Management System’ (LMS) link in the upper right hand corner under RELATED CONTENT
If necessary, set up a log on
Once in LMS, follow drop downs for ‘web-based training’ and ‘retail market’. Available modules will appear
Select ‘start course’

## Slide 6: Next Meeting Dates
January 11th & 12th , 2016
10:00 am to 4:00 pm 1/11, Mon
9:30 am 1/12, Tues
ERCOT Met Center

## Slide 7
Questions