## PROJECTS
Generator Interconnection Status Report | December 2015
Date: 1/4/2016 2:42:40 PM

## New Units
New Resources Approved for Synchronization
INR | Project | MW | County | Part2 Synch Apprv
New Resources Approved for Commercial Operation
INR | Project | MW | County | Part3 Commercial Apprv
13INR0052 | Los Vientos III | 200 | Starr | 2015-12-28
15INR0036 | Downie Ranch Solar | 95 | Uvalde | 2015-12-22
11INR0079a | Shannon Wind | 200 | Clay | 2015-12-23
12INR0068 | Sendero Wind | 78 | Jim Hogg | 2015-12-22
13INR0055 | Javelina Wind | 250 | Zapata | 2015-12-23

## Summary of GIR
Summary of Generation Interconnection Requests |  | Fuel Type | Screening Study (MW)* | Screening Study w/ PL (MW)** | Full Study (MW)* | Full Study w/ PL (MW)** | IA Executed (MW)** | IA Executed FIS Pending (MW)** | Grand Total (MW)
Currently tracking 255 generation interconnection or change requests |  |  | 1612 | 0 | 6967 | 0 | 2226 | 1067 | 11872
GENERATION INTERCONNECTION REQUESTS CURRENTLY UNDER REVIEW |  |  | 1435 | 0 | 5979 | 0 | 6685 | 1715 | 15814
December 2015 | Total | Total Gas | 3047 | 0 | 12946 | 0 | 8911 | 2782 | 27686
Security Screening Study (SSS) Underway | 3 | Nuclear | 0 | 0 | 0 | 0 | 0 | 0 | 0
SSS Completed | 21 | Coal | 0 | 0 | 0 | 0 | 240 | 0 | 240
Full Interconnect Study (FIS) Underway | 131 | Wind | 1585 | 0 | 12120 | 0 | 3352 | 7038 | 24095
FIS Completed | 10 | Solar | 1598 | 0 | 5144 | 0 | 948 | 819 | 8509
Interconnection Agreement Executed -> FIS Pending | 44 | Biomass | 0 | 0 | 0 | 0 | 0 | 0 | 0
Interconnection Agreement Executed | 46 | Storage | 0 | 0 | 290 | 0 | 324 | 0 | 614
Total Interconnection Requests | 255 | Petroleum Coke | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cancelled Studies (since last month) | 6 | Total | 6230 | 0 | 30500 | 0 | 13775 | 10639 | 61144
Total Capacity Under Study, MW | 61144 | * Confidential project interconnection requests
Total Wind Capacity, MW | 24095 | ** Public project interconnection requests; waiver of confidential information received by ERCOT ("Public Letter') or IA executed.
Interconnection Agreement Executed, MW | 13775
Cancelled Capacity, MW (since last month) | 1506

## IA Table
Generation Interconnection Agreements as of December 2015
Planning Guide Section 6.9 Requirements
GINR Reference Number | Project Name | County | Projected Date | Fuel | MW For Grid | Changes From Last Report | Meets All Requirements | Sufficient Financial Security Received by TSP | Air Permit | Water Rights | FIS completion
12INR0059b | Barilla Solar 1B | Pecos | 2015-11-01 | SOLAR | 7 | Projected Date | Yes | Yes | N/A | N/A | Complete
11INR0057 | Cameron County Wind | Cameron | 2016-01-01 | WIND | 165 | Projected Date | Yes | Yes | N/A | N/A | Complete
15INR0021 | Los Vientos V | Starr | 2016-03-01 | WIND | 110 |  | Yes | Yes | N/A | N/A | Complete
06INR0022c | Baffin Wind | Kenedy | 2016-01-01 | WIND | 202 | Projected Date | Yes | Yes | N/A | N/A | Complete
14INR0038 | PHR Peakers | Galveston | 2016-03-01 | GAS | 390 |  | Yes | Yes | Yes | N/A | Complete
13INR0028 | Antelope & Elk 1 | Hale | 2016-04-01 | GAS | 369 | Project Name, Projected Date, MW For Grid | Yes | Yes | Yes | Yes | Complete
15INR0032 | Elk 2 | Hale | 2016-04-01 | GAS | 202 | Projected Date | Yes | Yes | Yes | Yes | Incomplete
15INR0033 | Elk 3 | Hale | 2016-04-01 | GAS | 202 | Projected Date | Yes | Yes | Yes | Yes | Incomplete
16INR0057 | Sky Global Power One | Colorado | 2016-04-01 | GAS | 51 | Project Name, Projected Date | Yes | Yes | Yes | N/A | Complete
14INR0012b | Miami Wind G3 | Gray | 2016-05-01 | WIND | 111 | Project Name | No | No | N/A | N/A | Complete
14INR0025b | South Plains II Phase a | Floyd | 2016-05-01 | WIND | 152 | Project Name, Projected Date | Yes | Yes | N/A | N/A | Complete
14INR0025c | South Plains II Phase b | Floyd | 2016-05-01 | WIND | 148 | Project Name, Projected Date, SFS, PG Section 6.9 | Yes | Yes | N/A | N/A | Incomplete
13INR0010a | Mariah Wind A | Parmer | 2016-06-01 | WIND | 232 |  | No | No | N/A | N/A | Incomplete
13INR0010b | Mariah Wind B | Parmer | 2016-06-01 | WIND | 230 |  | No | No | N/A | N/A | Incomplete
14INR0031 | Baytown Chiller | Chambers | 2016-06-01 | GAS | 270 |  | Yes | Yes | Yes | N/A | Complete
14INR0040 | Redgate G | Hidalgo | 2016-06-01 | GAS | 225 |  | Yes | Yes | Yes | N/A | Complete
14INR0057 | Buckthorn Wind 1 | Erath | 2016-06-01 | WIND | 96 | NEW | Yes | Yes | N/A | N/A | Complete
14INR0066 | Lamar Power Upgrade | Lamar | 2016-06-01 | GAS | 130 |  | Yes | Yes | Yes | N/A | Complete
15INR0061 | SolaireHolman 1 | Brewster | 2016-06-01 | SOLAR | 50 | NEW | No | No | N/A | N/A | Incomplete
16INR0048 | RE Roserock Solar | Pecos | 2016-06-01 | SOLAR | 160 | Projected Date, MW For Grid | Yes | Yes | N/A | N/A | Complete
08INR0018 | Gunsight Mt W | Howard | 2016-08-01 | WIND | 120 |  | Yes | Yes | N/A | N/A | Complete
14INR0047 | Wake Wind | Dickens | 2016-08-01 | WIND | 300 | Projected Date | Yes | Yes | N/A | N/A | Complete
15INR0050 | Unity Wind | Deaf Smith | 2016-08-01 | WIND | 203 |  | No | No | N/A | N/A | Incomplete
15INR0074 | Happy Whiteface W | Deaf Smith | 2016-08-01 | WIND | 157 | SFS, PG Section 6.9 | Yes | Yes | N/A | N/A | Complete
16INR0052 | Solara Solar | Haskell | 2016-08-01 | SOLAR | 110 | Project Name, Projected Date | Yes | Yes | N/A | N/A | Incomplete
16INR0065B | SP-TX-12-Phase B | Upton | 2016-08-01 | SOLAR | 120 | NEW | No | No | N/A | N/A | Complete
14INR0045a | Torrecillas Wind A | Webb | 2016-09-01 | WIND | 200 |  | Yes | Yes | N/A | N/A | Incomplete
14INR0045b | Torrecillas Wind B | Webb | 2016-09-01 | WIND | 200 |  | Yes | Yes | N/A | N/A | Incomplete
15INR0037 | Los Vientos IV | Starr | 2016-09-01 | WIND | 200 |  | Yes | Yes | N/A | N/A | Incomplete
15INR0070_1 | West Texas Solar | Pecos | 2016-09-01 | SOLAR | 110 | Project Name, Projected Date | Yes | Yes | N/A | N/A | Complete
16INR0049 | Nazareth Solar | Castro | 2016-09-01 | SOLAR | 201 |  | No | No | N/A | N/A | Incomplete
14INR0060 | Horse Creek Wind | Haskell | 2016-10-01 | WIND | 200 |  | No | No | N/A | N/A | Complete
14INR0060b | Willow Springs Wind | Haskell | 2016-10-01 | WIND | 200 |  | No | No | N/A | N/A | Complete
15INR0045 | Riggins Solar | Pecos | 2016-10-01 | SOLAR | 150 | Project Name, Projected Date, MW For Grid | Yes | Yes | N/A | N/A | Incomplete
15INR0070_1b | Pearl Solar | Pecos | 2016-10-01 | SOLAR | 50 | NEW | No | No | N/A | N/A | Complete
15INR0079 | Pullman Road | Randall | 2016-10-01 | WIND | 300 |  | No | No | N/A | N/A | Incomplete
15INR0085 | Muenster Wind | Cooke | 2016-10-01 | WIND | 118 |  | No | No | N/A | N/A | Incomplete
16INR0024 | Hidalgo & Starr Wind | Hidalgo | 2016-10-01 | WIND | 250 |  | Yes | Yes | N/A | N/A | Incomplete
16INR0062 | Electra Wind | Wilbarger | 2016-10-01 | WIND | 360 |  | Yes | Yes | N/A | N/A | Incomplete
11INR0082a | Val Verde Wind | Val Verde | 2016-11-01 | WIND | 180 | Projected Date | Yes | Yes | N/A | N/A | Complete
11INR0054 | Midway Wind | San Patricio | 2016-12-01 | WIND | 161 |  | Yes | Yes | N/A | N/A | Complete
11INR0062 | Patriot Wind | Nueces | 2016-12-01 | WIND | 180 |  | Yes | Yes | N/A | N/A | Complete
12INR0029 | Comanche Run Wind | Swisher | 2016-12-01 | WIND | 500 |  | No | No | N/A | N/A | Complete
12INR0059c | Barilla Solar 2 | Pecos | 2016-12-01 | SOLAR | 21 |  | No | No | N/A | N/A | Complete
13INR0005b | Colbeck's Corner W | Carson | 2016-12-01 | WIND | 200 |  | Yes | Yes | N/A | N/A | Incomplete
13INR0005c | Grandview W 3 | Carson | 2016-12-01 | WIND | 188 |  | Yes | Yes | N/A | N/A | Incomplete
13INR0038 | Swisher Wind | Swisher | 2016-12-01 | WIND | 300 |  | Yes | Yes | N/A | N/A | Incomplete
14INR0013 | San Roman Wind 1 | Cameron | 2016-12-01 | WIND | 103 |  | Yes | Yes | N/A | N/A | Incomplete
14INR0023b | Longhorn South | Briscoe | 2016-12-01 | WIND | 160 | Projected Date | Yes | Yes | N/A | N/A | Complete
14INR0030c | Panhandle Wind 3 | Carson | 2016-12-01 | WIND | 248 |  | No | No | N/A | N/A | Incomplete
14INR0041a | Redfish W 2a | Willacy | 2016-12-01 | WIND | 115 |  | Yes | Yes | N/A | N/A | Incomplete
14INR0041b | Redfish W 2b | Willacy | 2016-12-01 | WIND | 115 |  | Yes | Yes | N/A | N/A | Incomplete
14INR0062 | Salt Fork 1 Wind | Gray | 2016-12-01 | WIND | 200 |  | Yes | Yes | N/A | N/A | Incomplete
15INR0049 | Albercas Wind | Zapata | 2016-12-01 | WIND | 250 | NEW | No | No | N/A | N/A | Incomplete
16INR0019 | Capricorn Ridge Solar | Coke | 2016-12-01 | SOLAR | 100 | NEW | No | No | N/A | N/A | Incomplete
16INR0023 | BNB Lamesa Solar | Dawson | 2016-12-01 | SOLAR | 200 |  | No | No | N/A | N/A | Complete
16INR0037 | Blanco Canyon Wind 1 | Floyd | 2016-12-01 | WIND | 50 | NEW | Yes | Yes | N/A | N/A | Incomplete
16INR0037b | Blanco Canyon Wind 2 | Floyd | 2016-12-01 | WIND | 150 | Project Name, MW For Grid | Yes | Yes | N/A | N/A | Incomplete
16INR0055 | Chapman Ranch Wind I | Nueces | 2016-12-01 | WIND | 250 |  | Yes | Yes | N/A | N/A | Incomplete
16INR0065 | SP-TX-12 | Upton | 2016-12-01 | SOLAR | 180 | County, Projected Date, SFS, PG Section 6.9 | Yes | Yes | N/A | N/A | Complete
16INR0073 | East Pecos Solar | Pecos | 2016-12-01 | SOLAR | 100 |  | Yes | Yes | N/A | N/A | Incomplete
16INR0082 | Salt Fork 2 Wind | Carson | 2016-12-01 | WIND | 200 |  | No | No | N/A | N/A | Incomplete
16INR0087 | RTS Wind | McCulloch | 2016-12-01 | WIND | 200 | NEW | Yes | Yes | N/A | N/A | Complete
16INR0091 | Santa Rita Wind | Reagan | 2016-12-01 | WIND | 300 | NEW | No | No | N/A | N/A | Incomplete
16INR0114 | Upton Solar | Upton | 2016-12-01 | SOLAR | 100 | NEW | No | No | N/A | N/A | Complete
10INR0009 | Caprock Wind | Castro | 2017-02-01 | WIND | 300 |  | No | No | N/A | N/A | Incomplete
12INR0018 | Pampa Wind | Gray | 2017-03-01 | WIND | 500 |  | No | No | N/A | N/A | Incomplete
13INR0056 | Fluvanna Renewable 1 | Scurry | 2017-03-01 | WIND | 240 | NEW | No | No | N/A | N/A | Incomplete
13INR0049 | Friendswood G | Harris | 2017-04-01 | GAS | 129 | Projected Date, MW For Grid , SFS, PG Section 6.9 | Yes | Yes | Yes | Yes | Complete
15INR0023 | Indeck Wharton | Wharton | 2017-04-01 | GAS | 700 |  | No | No | Yes | Yes | Complete
13INR0045 | Changing Winds | Castro | 2017-05-01 | WIND | 288 | Projected Date | No | No | N/A | N/A | Incomplete
16INR0003 | Freeport LNG | Brazoria | 2017-06-01 | GAS | 11 |  | Yes | Yes | Yes | N/A | Complete
13INR0010d | Scandia Wind D | Parmer | 2017-07-01 | WIND | 200 | Projected Date | No | No | N/A | N/A | Incomplete
13INR0010e | Scandia Wind E | Parmer | 2017-07-01 | WIND | 200 | Projected Date | No | No | N/A | N/A | Incomplete
13INR0010f | Scandia Wind F | Parmer | 2017-07-01 | WIND | 200 | Projected Date | No | No | N/A | N/A | Incomplete
17INR0009 | Wolf Hollow 2 | Hood | 2017-07-01 | GAS | 1042 | NEW | Yes | Yes | Yes | Yes | Complete
10INR0022 | Pondera King G | Harris | 2017-08-01 | GAS | 925 |  | No | No | Yes | Yes | Complete
15INR0059 | Pecos Solar I | Pecos | 2017-10-01 | SOLAR | 108 | Projected Date | Yes | Yes | N/A | N/A | Incomplete
13INR0020b | Rattlesnake W 2 | Glasscock | 2017-11-01 | WIND | 158 | Projected Date | No | No | N/A | N/A | Complete
16INR0006 | Pinecrest G | Angelina | 2017-11-01 | GAS | 785 |  | No | No | Yes | Yes | Complete
16INR0004 | LaPaloma G | Cameron | 2018-02-01 | GAS | 730 |  | No | No | Yes | Yes | Complete
16INR0010 | FGE Texas 1 | Mitchell | 2018-04-01 | GAS | 799 |  | No | No | Yes | Yes | Complete
18INR0001 | Rockwood G | Colorado | 2018-04-01 | GAS | 1122 | NEW | No | No | Yes | No | Complete
17INR0010 | FGE Texas II | Mitchell | 2018-05-01 | GAS | 799 |  | No | No | Yes | No | Incomplete
14INR0027 | Guadalupe II | Guadalupe | 2018-06-01 | GAS | 362 | Projected Date | No | No | Yes | No | Complete
17INR0003 | SPC Jackson G | Jackson | 2018-06-01 | GAS | 916 |  | No | No | No | No | Incomplete
15INR0013 | Bethel CAES | Anderson | 2018-12-01 | STORAGE | 324 |  | No | No | Yes | Yes | Complete
16INR0005 | Brownsville G | Cameron | 2018-12-01 | GAS | 871 |  | No | No | Yes | No | Complete
16INR0008 | Tenaska Roans Prairie | Grimes | 2019-04-01 | GAS | 663 | Projected Date | No | No | Yes | No | Incomplete
13INR0023 | Texas Clean C | Ector | 2019-12-01 | COAL | 240 | Projected Date | No | No | Yes | Yes | Complete

## Full Study Table
GINR Reference Number | County | Fuel | Capacity to Grid (MW) | Projected Date (as specified by the resource developer) | Public Letter
15INR0033 | Hale | Gas | 202 | 2016-04-01
15INR0032 | Hale | Gas | 202 | 2016-04-01
14INR0025c | Floyd | Wind | 148 | 2016-05-31
16INR0050 | Brewster | Solar | 50 | 2016-06-01
16INR0035 | Nueces | Gas | 82 | 2016-06-01
16INR0034 | Bosque | Gas | 124 | 2016-06-01
16INR0045 | Henderson | Gas | 432 | 2016-06-01
16INR0044 | Wharton | Gas | 419 | 2016-06-01
13INR0010b | Parmer | Wind | 230 | 2016-06-01
13INR0010a | Parmer | Wind | 232 | 2016-06-01
15INR0061 | Brewster | Solar | 50 | 2016-06-30
16INR0094 | Culberson | Solar | 280 | 2016-08-01
16INR0052 | Haskell | Solar | 110 | 2016-08-01
15INR0050 | Deaf Smith | Wind | 203 | 2016-08-01
16INR0009 | Calhoun | Gas | 494 | 2016-08-30
16INR0072 | Pecos | Solar | 50 | 2016-09-01
16INR0049 | Castro | Solar | 201 | 2016-09-01
15INR0037 | Starr | Wind | 200 | 2016-09-01
14INR0045b | Webb | Wind | 200 | 2016-09-01
14INR0045a | Webb | Wind | 200 | 2016-09-01
16INR0080 | Brewster | Solar | 56 | 2016-09-15
16INR0079 | Brewster | Solar | 56 | 2016-09-15
16INR0093 | Reeves | Solar | 48 | 2016-10-01
16INR0089 | Andrews | Solar | 60 | 2016-10-01
15INR0054 | Reeves | Gas | 123 | 2016-10-01
15INR0053 | Winkler | Gas | 123 | 2016-10-01
15INR0040 | Presidio | Solar | 60 | 2016-10-01
16INR0085 | Mills | Wind | 300 | 2016-10-01
16INR0062 | Wilbarger | Wind | 360 | 2016-10-01
16INR0024 | Hidalgo | Wind | 250 | 2016-10-01
16INR0121 | Carson | Wind | 24 | 2016-10-03
15INR0045 | Pecos | Solar | 150 | 2016-10-15
16INR0120 | Dallas | Storage | 20 | 2016-10-31
15INR0047 | Presidio | Solar | 42 | 2016-10-31
14INR0033 | Armstrong | Wind | 500 | 2016-10-31
14INR0020 | Floyd | Wind | 150 | 2016-10-31
12INR0002a | Briscoe | Wind | 200 | 2016-10-31
15INR0085 | Cooke | Wind | 118 | 2016-10-31
15INR0079 | Randall | Wind | 300 | 2016-10-31
15INR0064 | Glasscock | Wind | 240 | 2016-11-30
15INR0063 | Castro | Wind | 200 | 2016-11-30
14INR0009 | Kent | Wind | 248 | 2016-11-30
16INR0117 | Briscoe | Wind | 200 | 2016-12-01
16INR0060 | Upton | Solar | 150 | 2016-12-01
16INR0018 | Upton | Solar | 40 | 2016-12-01
14INR0026 | Presidio | Solar | 30 | 2016-12-01
12INR0060 | Schleicher | Wind | 201 | 2016-12-01
16INR0091 | Reagan | Wind | 300 | 2016-12-01
16INR0073 | Pecos | Solar | 100 | 2016-12-01
16INR0019 | Coke | Solar | 100 | 2016-12-01
14INR0041b | Willacy | Wind | 115 | 2016-12-01
14INR0041a | Willacy | Wind | 115 | 2016-12-01
13INR0005b | Carson | Wind | 200 | 2016-12-01
16INR0115 | Pecos | Solar | 182 | 2016-12-15
16INR0074 | Brazoria | Wind | 150 | 2016-12-15
16INR0058 | Brewster | Solar | 88 | 2016-12-15
15INR0082 | Comanche | Wind | 400 | 2016-12-15
15INR0062 | Hale | Wind | 200 | 2016-12-15
13INR0026 | Oldham | Wind | 201 | 2016-12-15
13INR0005c | Carson | Wind | 188 | 2016-12-15
15INR0073 | Armstrong | Wind | 201 | 2016-12-30
14INR0014 | Val Verde | Solar | 100 | 2016-12-30
14INR0030c | Carson | Wind | 248 | 2016-12-30
16INR0119 | Crosby | Solar | 150 | 2016-12-31
16INR0112 | La Salle | Wind | 200 | 2016-12-31
16INR0111 | Starr | Wind | 200 | 2016-12-31
16INR0106 | Andrews | Solar | 150 | 2016-12-31
16INR0105 | Jim Hogg | Wind | 300 | 2016-12-31
16INR0100 | Brewster | Solar | 150 | 2016-12-31
16INR0099 | Brewster | Solar | 50 | 2016-12-31
16INR0098 | Brewster | Solar | 50 | 2016-12-31
16INR0092 | Brewster | Solar | 50 | 2016-12-31
16INR0086 | Concho | Wind | 150 | 2016-12-31
16INR0076 | Brazoria | Gas | 135 | 2016-12-31
16INR0070 | Winkler | Solar | 150 | 2016-12-31
16INR0037c | Floyd | Wind | 200 | 2016-12-31
16INR0031 | Starr | Wind | 100 | 2016-12-31
16INR0029 | Hill | Wind | 100 | 2016-12-31
16INR0027 | Grayson | Wind | 100 | 2016-12-31
15INR0090 | Travis | Solar | 120 | 2016-12-31
15INR0086 | Uvalde | Solar | 45 | 2016-12-31
15INR0081 | Mason | Wind | 62 | 2016-12-31
15INR0044 | Webb | Solar | 200 | 2016-12-31
14INR0048_1 | Wilbarger | Wind | 114 | 2016-12-31
16INR0082 | Carson | Wind | 200 | 2016-12-31
16INR0055 | Nueces | Wind | 250 | 2016-12-31
16INR0037b | Floyd | Wind | 150 | 2016-12-31
16INR0037 | Floyd | Wind | 50 | 2016-12-31
15INR0049 | Zapata | Wind | 250 | 2016-12-31
14INR0062 | Gray | Wind | 200 | 2016-12-31
14INR0013 | Cameron | Wind | 103 | 2016-12-31
13INR0038 | Swisher | Wind | 300 | 2016-12-31
10INR0009 | Castro | Wind | 300 | 2017-02-28
16INR0054 | Harris | Gas | 12 | 2017-03-01
15INR0057 | Wharton | Gas | 142 | 2017-03-01
13INR0056 | Scurry | Wind | 240 | 2017-03-01
15INR0071 | Deaf Smith | Wind | 199 | 2017-03-31
15INR0068 | Sterling | Solar | 20 | 2017-03-31
15INR0035 | Kenedy | Wind | 200 | 2017-03-31
15INR0034 | San Patricio | Wind | 201 | 2017-03-31
14INR0043 | Sterling | Solar | 40 | 2017-03-31
12INR0045 | Kleberg | Wind | 135 | 2017-03-31
13INR0025 | Randall | Wind | 150 | 2017-03-31
12INR0018 | Gray | Wind | 500 | 2017-03-31
18INR0004 | Hill | Gas | 928 | 2017-04-01
16INR0063 | Pecos | Solar | 98 | 2017-04-30
17INR0024 | Nolan | Gas | 350 | 2017-05-02
16INR0022 | Borden | Solar | 100 | 2017-05-30
17INR0035 | Willacy | Wind | 227 | 2017-05-31
16INR0039 | Reeves | Solar | 100 | 2017-05-31
15INR0055 | Austin | Gas | 142 | 2017-05-31
13INR0045 | Castro | Wind | 288 | 2017-05-31
16INR0104 | Crockett | Wind | 400 | 2017-06-01
16INR0036 | Nolan | Gas | 280 | 2017-06-01
17INR0022 | Harris | Gas | 11 | 2017-06-22
16INR0014 | Castro | Wind | 200 | 2017-07-01
14INR0074 | Williamson | Gas | 92 | 2017-07-01
13INR0010f | Parmer | Wind | 200 | 2017-07-01
13INR0010e | Parmer | Wind | 200 | 2017-07-01
13INR0010d | Parmer | Wind | 200 | 2017-07-01
17INR0007 | Wharton | Gas | 1128 | 2017-07-31
16INR0068 | Andrews | Solar | 100 | 2017-09-01
16INR0067 | Dawson | Solar | 100 | 2017-09-01
17INR0020 | Pecos | Solar | 500 | 2017-09-30
16INR0021 | Pecos | Solar | 150 | 2017-09-30
16INR0020 | Presidio | Solar | 55 | 2017-09-30
17INR0025 | Zapata | Wind | 202 | 2017-10-31
12INR0002b | Briscoe | Wind | 200 | 2017-10-31
15INR0059 | Pecos | Solar | 108 | 2017-10-31
15INR0064b | Glasscock | Wind | 120 | 2017-11-30
17INR0033 | Briscoe | Wind | 200 | 2017-12-01
17INR0027 | Scurry | Wind | 250 | 2017-12-01
16INR0061 | Hardeman | Wind | 200 | 2017-12-01
16INR0033 | Castro | Wind | 150 | 2017-12-01
16INR0015 | Wharton | Wind | 248 | 2017-12-01
16INR0014b | Castro | Wind | 200 | 2017-12-01
16INR0012 | Kenedy | Wind | 200 | 2017-12-01
15INR0072 | Pecos | Solar | 140 | 2017-12-01
15INR0069 | Pecos | Solar | 110 | 2017-12-01
15INR0067 | Reeves | Solar | 80 | 2017-12-01
15INR0051 | Castro | Wind | 200 | 2017-12-01
14INR0044 | Reeves | Solar | 100 | 2017-12-01
13INR0006 | Gray | Wind | 750 | 2017-12-01
08INR0019c | Gray | Wind | 250 | 2017-12-01
08INR0019b | Gray | Wind | 250 | 2017-12-01
08INR0019a | Gray | Wind | 250 | 2017-12-01
17INR0031 | Cameron | Wind | 150 | 2017-12-31
17INR0005 | Starr | Wind | 200 | 2017-12-31
16INR0097 | Upton | Solar | 200 | 2017-12-31
16INR0096 | Pecos | Solar | 102 | 2017-12-31
16INR0081 | Starr | Wind | 200 | 2017-12-31
16INR0075 | Culberson | Solar | 100 | 2017-12-31
16INR0040 | Reeves | Solar | 105 | 2017-12-31
14INR0056 | Mills | Wind | 101 | 2017-12-31
11INR0093 | San Patricio | Wind | 41 | 2017-12-31
16INR0066 | Mitchell | Solar | 150 | 2017-12-31
13INR0032 | Andrews | Solar | 100 | 2017-12-31
16INR0102 | Pecos | Solar | 130 | 2018-01-01
16INR0101 | Pecos | Solar | 57 | 2018-01-01
12INR0055 | Baylor | Wind | 40 | 2018-01-31
11INR0040 | Freestone | Gas | 640 | 2018-03-01
15INR0063b | Castro | Wind | 101 | 2018-04-18
13INR0056b | Scurry | Wind | 142 | 2018-05-01
15INR0062b | Hale | Wind | 122 | 2018-05-15
17INR0010 | Mitchell | Gas | 799 | 2018-05-15
17INR0018 | McLennan | Gas | 471 | 2018-06-01
17INR0017 | Guadalupe | Gas | 540 | 2018-06-01
16INR0038 | McLennan | Gas | 471 | 2018-06-01
15INR0042 | Hood | Gas | 460 | 2018-06-01
17INR0016 | Wilson | Gas | 540 | 2018-06-01
17INR0014 | Grayson | Gas | 548 | 2018-06-01
17INR0003 | Jackson | Gas | 916 | 2018-06-01
16INR0013 | Nacogdoches | Gas | 229 | 2018-07-01
14INR0011 | Swisher | Storage | 270 | 2018-07-01
18INR0009 | Cherokee | Gas | 1156 | 2018-08-01
14INR0028 | Live Oak | Wind | 300 | 2018-10-31
18INR0005 | Grayson | Gas | 541 | 2018-12-01
17INR0027b | Scurry | Wind | 250 | 2018-12-01
18INR0016 | McCulloch | Wind | 150 | 2018-12-31
17INR0030 | Deaf Smith | Solar | 100 | 2018-12-31
17INR0013 | Hill | Gas | 800 | 2019-04-01
16INR0008 | Grimes | Gas | 663 | 2019-04-01
18INR0002 | Tarrant | Gas | 853 | 2019-06-01
17INR0004 | Hale | Gas | 202 | 2019-06-01
17INR0002 | Henderson | Gas | 478 | 2019-06-01

## Wind Chart
INR | ProjectName | County | Status | Projected Date | IA Signed | Fuel | TypeCode | MWForGrid | Year
11INR0057 | Cameron County Wind | Cameron | PLANNED | 2016-01-01 | 2013-08-09 | WIND | WT | 165 | 2015
15INR0021 | Los Vientos V | Starr | PLANNED | 2016-03-01 | 2014-10-02 | WIND | WT | 110 | 2016
06INR0022c | Baffin Wind | Kenedy | PLANNED | 2016-01-31 | 2009-05-08 | WIND | WT | 202 | 2016
14INR0012b | Miami Wind G3 | Gray | PLANNED | 2016-05-01 | 2013-03-01 | WIND | WT | 111 | 2016
14INR0025b | South Plains II Phase a | Floyd | PLANNED | 2016-05-31 | 2014-01-02 | WIND | WT | 152 | 2016
14INR0025c | South Plains II Phase b | Floyd | PLANNED | 2016-05-31 | 2014-01-02 | WIND | WT | 148 | 2016
13INR0010a | Mariah Wind A | Parmer | PLANNED | 2016-06-01 | 2013-01-31 | WIND | WT | 232 | 2016
13INR0010b | Mariah Wind B | Parmer | PLANNED | 2016-06-01 | 2013-01-31 | WIND | WT | 230 | 2016
14INR0057 | Buckthorn Wind 1 | Erath | PLANNED | 2016-06-30 | 2015-09-10 | WIND | WT | 96 | 2016
08INR0018 | Gunsight Mt W | Howard | PLANNED | 2016-08-01 | 2007-11-12 | WIND | WT | 120 | 2016
14INR0047 | Wake Wind | Dickens | PLANNED | 2016-08-01 | 2014-03-17 | WIND | WT | 300 | 2016
15INR0050 | Unity Wind | Deaf Smith | PLANNED | 2016-08-01 | 2014-10-03 | WIND | WT | 203 | 2016
15INR0074 | Happy Whiteface W | Deaf Smith | PLANNED | 2016-08-01 | 2015-07-06 | WIND | WT | 157 | 2016
14INR0045a | Torrecillas Wind A | Webb | PLANNED | 2016-09-01 | 2015-01-30 | WIND | WT | 200 | 2016
14INR0045b | Torrecillas Wind B | Webb | PLANNED | 2016-09-01 | 2015-01-30 | WIND | WT | 200 | 2016
15INR0037 | Los Vientos IV | Starr | PLANNED | 2016-09-01 | 2014-10-02 | WIND | WT | 200 | 2016
14INR0060 | Horse Creek Wind | Haskell | PLANNED | 2016-10-01 | 2015-05-01 | WIND | WT | 200 | 2016
14INR0060b | Willow Springs Wind | Haskell | PLANNED | 2016-10-01 | 2015-05-01 | WIND | WT | 200 | 2016
16INR0024 | Hidalgo & Starr Wind | Hidalgo | PLANNED | 2016-10-01 | 2015-07-17 | WIND | WT | 250 | 2016
16INR0062 | Electra Wind | Wilbarger | PLANNED | 2016-10-01 | 2015-03-31 | WIND | WT | 360 | 2016
15INR0079 | Pullman Road | Randall | PLANNED | 2016-10-31 | 2014-05-29 | WIND | WT | 300 | 2016
15INR0085 | Muenster Wind | Cooke | PLANNED | 2016-10-31 | 2015-06-18 | WIND | WT | 118 | 2016
11INR0082a | Val Verde Wind | Val Verde | PLANNED | 2016-11-01 | 2015-08-12 | WIND | WT | 180 | 2016
13INR0005b | Colbeck's Corner W | Carson | PLANNED | 2016-12-01 | 2014-04-23 | WIND | WT | 200 | 2016
14INR0041a | Redfish W 2a | Willacy | PLANNED | 2016-12-01 | 2015-08-12 | WIND | WT | 115 | 2016
14INR0041b | Redfish W 2b | Willacy | PLANNED | 2016-12-01 | 2015-08-12 | WIND | WT | 115 | 2016
16INR0091 | Santa Rita Wind | Reagan | PLANNED | 2016-12-01 | 2015-11-24 | WIND | WT | 300 | 2016
13INR0005c | Grandview W 3 | Carson | PLANNED | 2016-12-15 | 2014-04-23 | WIND | WT | 188 | 2016
11INR0054 | Midway Wind | San Patricio | PLANNED | 2016-12-28 | 2012-09-24 | WIND | WT | 161 | 2016
11INR0062 | Patriot Wind | Nueces | PLANNED | 2016-12-30 | 2013-07-15 | WIND | WT | 180 | 2016
14INR0030c | Panhandle Wind 3 | Carson | PLANNED | 2016-12-30 | 2014-08-25 | WIND | WT | 248 | 2016
12INR0029 | Comanche Run Wind | Swisher | PLANNED | 2016-12-31 | 2013-07-24 | WIND | WT | 500 | 2016
13INR0038 | Swisher Wind | Swisher | PLANNED | 2016-12-31 | 2015-09-06 | WIND | WT | 300 | 2016
14INR0013 | San Roman Wind 1 | Cameron | PLANNED | 2016-12-31 | 2014-12-19 | WIND | WT | 103 | 2016
14INR0023b | Longhorn South | Briscoe | PLANNED | 2016-12-31 | 2012-12-10 | WIND | WT | 160 | 2016
14INR0062 | Salt Fork 1 Wind | Gray | PLANNED | 2016-12-31 | 2014-08-27 | WIND | WT | 200 | 2016
15INR0049 | Albercas Wind | Zapata | PLANNED | 2016-12-31 | 2015-12-30 | WIND | WT | 250 | 2016
16INR0037 | Blanco Canyon Wind 1 | Floyd | PLANNED | 2016-12-31 | 2015-08-03 | WIND | WT | 50 | 2016
16INR0037b | Blanco Canyon Wind 2 | Floyd | PLANNED | 2016-12-31 | 2015-08-03 | WIND | WT | 150 | 2016
16INR0055 | Chapman Ranch Wind I | Nueces | PLANNED | 2016-12-31 | 2015-07-16 | WIND | WT | 250 | 2016
16INR0082 | Salt Fork 2 Wind | Carson | PLANNED | 2016-12-31 | 2015-08-18 | WIND | WT | 200 | 2016
16INR0087 | RTS Wind | McCulloch | PLANNED | 2016-12-31 | 2015-10-14 | WIND | WT | 200 | 2016
10INR0009 | Caprock Wind | Castro | PLANNED | 2017-02-28 | 2014-10-31 | WIND | WT | 300 | 2017
13INR0056 | Fluvanna Renewable 1 | Scurry | PLANNED | 2017-03-01 | 2015-09-24 | WIND | WT | 240 | 2017
12INR0018 | Pampa Wind | Gray | PLANNED | 2017-03-31 | 2013-11-12 | WIND | WT | 500 | 2017
13INR0045 | Changing Winds | Castro | PLANNED | 2017-05-31 | 2015-02-27 | WIND | WT | 288 | 2017
13INR0010d | Scandia Wind D | Parmer | PLANNED | 2017-07-01 | 2014-04-25 | WIND | WT | 200 | 2017
13INR0010e | Scandia Wind E | Parmer | PLANNED | 2017-07-01 | 2014-04-25 | WIND | WT | 200 | 2017
13INR0010f | Scandia Wind F | Parmer | PLANNED | 2017-07-01 | 2014-04-25 | WIND | WT | 200 | 2017
13INR0020b | Rattlesnake W 2 | Glasscock | PLANNED | 2017-11-20 | 2013-06-28 | WIND | WT | 158 | 2017

## Solar Chart
INR | ProjectName | County | Status | Projected Date | IA Signed | Fuel | TypeCode | MWForGrid | Year
12INR0059b | Barilla Solar 1B | Pecos | PLANNED | 2015-11-10 | 2013-12-26 | SOLAR | PV | 7 | 2015
15INR0061 | SolaireHolman 1 | Brewster | PLANNED | 2016-06-30 | 2015-11-10 | SOLAR | PV | 50 | 2016
16INR0048 | RE Roserock Solar | Pecos | PLANNED | 2016-06-30 | 2015-11-19 | SOLAR | PV | 160 | 2016
16INR0052 | Solara Solar | Haskell | PLANNED | 2016-08-01 | 2015-04-09 | SOLAR | PV | 110 | 2016
16INR0065B | SP-TX-12-Phase B | Upton | PLANNED | 2016-08-15 | 2015-10-29 | SOLAR | PV | 120 | 2016
16INR0049 | Nazareth Solar | Castro | PLANNED | 2016-09-01 | 2015-05-15 | SOLAR | PV | 201 | 2016
15INR0070_1 | West Texas Solar | Pecos | PLANNED | 2016-09-30 | 2014-12-17 | SOLAR | PV | 110 | 2016
15INR0045 | Riggins Solar | Pecos | PLANNED | 2016-10-15 | 2015-01-26 | SOLAR | PV | 150 | 2016
15INR0070_1b | Pearl Solar | Pecos | PLANNED | 2016-10-30 | 2014-12-17 | SOLAR | PV | 50 | 2016
16INR0019 | Capricorn Ridge Solar | Coke | PLANNED | 2016-12-01 | 2015-08-19 | SOLAR | PV | 100 | 2016
16INR0065 | SP-TX-12 | Upton | PLANNED | 2016-12-01 | 2015-09-04 | SOLAR | PV | 180 | 2016
16INR0073 | East Pecos Solar | Pecos | PLANNED | 2016-12-01 | 2015-03-06 | SOLAR | PV | 100 | 2016
16INR0114 | Upton Solar | Upton | PLANNED | 2016-12-01 | 2015-12-04 | SOLAR | PV | 100 | 2016
12INR0059c | Barilla Solar 2 | Pecos | PLANNED | 2016-12-31 | 2013-12-26 | SOLAR | PV | 21 | 2016
16INR0023 | BNB Lamesa Solar | Dawson | PLANNED | 2016-12-31 | 2015-06-25 | SOLAR | PV | 200 | 2016
15INR0059 | Pecos Solar I | Pecos | PLANNED | 2017-10-31 | 2015-06-09 | SOLAR | PV | 108 | 2017

## ProjectMatrix
Note on CD15: Katheiser, Jenell: Frontera Chillers 5/17/2013
Note on CE15: Katheiser, Jenell: WA Parish Addition, Bryan Solar
Note on CF15: Murray, Douglas: Sandy Creek
Note on CH15: Murray, Douglas: Los vientos