## Slide 1
Stability Limit Management
Chad Thompson
Manager, Operations Support
Planning Working Group Meeting
ERCOT Public
January 20, 2016

## Slide 2: Issues
Transparency in Planning Studies with regards to stability limits
Deliverability issue currently at PLWG
Weak Grid shift factor issue currently at CMWG ($$)
Policy discussion of what should happen with an FIS, and the operational expectations of new generation sites

## Slide 3: Background
Increasing use of Generic Transmission Constraints
Increase in N-1 / N-1-1 stability issues identified in Full Interconnection Studies (FIS) due to turbine control instability
These stability issues can not be explicitly modeled in ERCOT systems

## Slide 4: ROS Recap
The FIS is just one checkpoint in the resource commissioning process
No requirements to address (or fix) issues identified in the FIS
  Thermal = “OK”
  Non-Thermal = “Not OK”
  FIS not always complete until just before commissioning begins
GTCs end up created near (or during) commissioning
Increased GTC use poses situational awareness risk

## Slide 5: So…
If an FIS identifies a stability problem, are there (or should there be) provisions to mitigate the stability issues laid out in the FIS before the generator begins commissioning?
  Who is on the hook?
Why would/should an FIS be approved if a proposed facility introduces stability issues?
What can be done to strengthen the interconnection process?

## Slide 6: Appendix
Commissioning Timeline
GTC Development
Resources

## Slide 7: Generation Interconnection Process

## Slide 8: Generation Interconnection Process

## Slide 9: The Challenge of a GTC
Complexity
  PI displays / ad-hoc operator tools
  Multi-limit tables
  Monitoring medium (VSAT, TSAT, EMS, etc)
Situational Awareness
  SCED and constraint visibility
Operator Training
Market Impacts
  Getting GTC modeled in time for CRR auctions
  GTC considerations in DAM prior to implementation in the network model

## Slide 10: Development of a GTC
The development of a new GTC is a muli-step process
Typically takes a minimum of one month to implement
  Can take more depending on the nature and complexity of the underlying stability problem

## Slide 11: Phases of GTC Development
Identification and Scope
NOMCR Submission
Development of Real-time Situational Awareness Tools
Development of GTC Documentation
Market Notice and Implementation
1. Identification /Scope
2. NOMCR
3. Situational Awareness Tools
4. GTC Documentation
5. Market Notice/ Implementation

## Slide 12: Phases of GTC Development
Stability studies conducted by ERCOT Planning identify type and scope of the stability problem requiring the GTC
Based on the study results…
  The lines comprising the interface covered by the GTC are identified
  It is determined whether the stability limit can be calculated in real-time using VSAT/TSAT or if a static table of values will be needed
1. Identification /Scope
2. NOMCR
3. Situational Awareness Tools
4. GTC Documentation
5. Market Notice/ Implementation

## Slide 13: Phases of GTC Development
A NOMCR is submitted to create the GTC in the ERCOT network operations model
Time from submission to implementation is typically 3-4 weeks
ERCOT cannot enforce the GTC until it is added to the model
1. Identification /Scope
2. NOMCR
3. Situational Awareness Tools
4. GTC Documentation
5. Market Notice/ Implementation

## Slide 14: Phases of GTC Development
If the stability limit for the GTC can be calculated in real-time, a new VSAT/TSAT case must be developed
  Once created, the case is tested using offline studies and validated against the existing planning studies
  PI tags must be created to allow for data capture and analysis
  Control room VSAT tools must also be updated to include the new GTC
1. Identification /Scope
2. NOMCR
3. Situational Awareness Tools
4. GTC Documentation
5. Market Notice/ Implementation

## Slide 15: Phases of GTC Development
If the stability limit for the GTC must be set using a static table:
  An automated PI display tool must be developed to alarm operators when the limit must be updated in real-time to a new value on the static table
  Displays vary in complexity. Some have had to monitor flows, breaker, and disconnect statuses for as many as 20 lines. All are based on significant amounts of Visual Basic code
1. Identification /Scope
2. NOMCR
3. Situational Awareness Tools
4. GTC Documentation
5. Market Notice/ Implementation

## Slide 16: Display Examples
1826 Lines of Code

## Slide 17: Display Examples
2259 Lines of Code

## Slide 18: Display Examples
4303 Lines of Code

## Slide 19: Phases of GTC Development
Development time for situational awareness tools varies depending on the complexity of the GTC
  Can be started before, but cannot be finished until after, GTC is added to the ERCOT model
ERCOT operator crews must also be trained on any new tools that are developed
1. Identification /Scope
2. NOMCR
3. Situational Awareness Tools
4. GTC Documentation
5. Market Notice/ Implementation

## Slide 20: Phases of GTC Development
A report is generated describing
  The underlying stability issue that led to the creation of the GTC
  The methodology for calculating the GTC in real-time
  Any static tables or the results of any offline stability studies that will be used to set the limit in real-time
ERCOT cannot begin enforcing the GTC until this report has been completed and posted to the MIS secure area
1. Identification /Scope
2. NOMCR
3. Situational Awareness Tools
4. GTC Documentation
5. Market Notice/ Implementation

## Slide 21: Phases of GTC Development
Once the GTC has been fully developed
  Information is provided to Market Operations Support to ensure the GTC is accurately represented in CRR auctions and the Day Ahead Market (DAM)
  A market notice is issued describing the new GTC. Depending on the timing of the notice, an OCN may also be issued
  ERCOT Operations will begin enforcing the GTC in real-time
1. Identification /Scope
2. NOMCR
3. Situational Awareness Tools
4. GTC Documentation
5. Market Notice/ Implementation

## Slide 22: Timing of GTC Development
The implementation of the NOMCR is typically the longest part of the GTC process at 3-4 weeks
However, this is not always the case
Some GTCs require the development of complex situational awareness tools that must be accompanied by extensive operator training
1. Identification /Scope
2. NOMCR
3. Situational Awareness Tools
4. GTC Documentation
5. Market Notice/ Implementation

## Slide 23: Resources
Resource Interconnection Handbook
http://www.ercot.com/content/services/rq/re/reg/Resource%20Interconnection%20Handbookv1.pdf
GTC Methodology
ERCOT MIS under Grid  Transmission  Generic Transmission Limits