## Sheet1
TX SET Meeting Notes / Action Items
2015-12-01
Agenda Item: | Decision / Resolution | Action Items :
October 2015 Meeting Notes | A minor change was made to the notes. | The Texas SET Chair will have these posted to the October 2015 meeting page key documents.
Mass Transition/Default-POLR Rule | • RMS assignment to discuss Mass Transition— Possible POLR Rule change from two days out to one day out.
AMWG Update
Other discussion
Market Test Flight 0214 Update | ERCOT to provide flight update No update received
TX SET Procedures | On Hold-Discuss reline changes sent to the TXSET listserv for review | Leave current issue process in tact and continue to review document to identify where additional process improvements can be made
RMS Updates
Texas Market Test Plan Approved at RMS November meeting | No Action needed.
FYI SCR786 Retail Market Testing Environment (MTTF / TDTMS) approved at PRS November 12th meeting | No Action needed.
Flight 1015 Update | • ERCOT provided a final update for Flight 2015 and reviewed the 2016 Flight schedule
RMG Safety Net timelines--Review and continue discussions.--Note: PUCT to review final draft prior to Texas SET submitting changes to RMS | • Texas SET continued discussions on the Safety Net / Priority spreadsheet timelines and how the process can be streamlined to reduce the number of duplicate ESI IDs that are included on the spreadsheets. Most of the Market Participants present agreed that the market can limit the work around requests for Priority NS or Standard Move Ins to a requested date of today. | o The Texas SET Chair will send a copy of the matrix to Sharyland to determine if they are in agreement to removing the group of Priority Move Ins with a requested date for tomorrow on a non-standard (NS) premise from the process.
Texas SET Swim Lanes Review
ERCOT Updated Swim Lanes CSA Create and Retire Move-Out Cancel and Date Change Move-In Cancel Reconnect for non-pay Move the Disconnect for non-pay swim lane from the Drop Scenario link to the Switch hold link. ERCOT update on how difficult it is to change the text on the website | Texas SET reviewed the Swimlanes that ERCOT created and made changes where needed. | The Swimlanes created for the Muni-EC TDSPs will be sent to Nueces for review after the other suggested changes have been made by ERCOT. TEXAS SET will complete a final review at the January meeting.
RMS assignments:
NPRR740 Retail Clarification and Cleanup Review Language for Completeness | • Texas SET reviewed NPRR740 Retail Clarification and Cleanup for accuracy and to provide feedback to RMS. No changes were noted and no comments will be filed. The TX SET Chair will report the findings to RMS.
New Entrant Documentation—Procedures and Documentation Location | No action.
Add Master Customer List (MCL) guide back to the Texas SET Guides | No action.
2016 Meeting Dates— | The Texas SET Chair reviewed the ERCOT confirmed 2016 meeting dates and times.
Texas SET Accomplishments Year Ending 2015 Complete Review and Update if needed | Texas SET reviewed and modified the 2015 TX SET Accomplishments as needed. | The TX SET Chair will present the accomplishments to RMS in January.
Cancel / Rebills for closed CR DUNS discussion | • ONCOR requested TDSP and CR feedback on how the TDSPs handle credits to CRs that are no longer in the market (i. e. DUNS closed). In other words, what do the TDSPs do with any refunds that might be due a CR where there is no market process to return the money to that CR? o Most of the TDSPs agreed that the issue could not be addressed with a market process because the DUNS is no longer valid in the market. o The Texas SET attendees agreed that any refunds due on a closed DUNS is an issue that needs to be addressed internally.
Discussion Items on Hold
Texas SET Release Discussion | No action
REP Certification Matrix—Long-term solution | No action
Next Meeting--ERCOT MET Center | January 20th RM 168
January 21st RM 102
Attendees
Diana Rehfeldt TNMP | Kathryn Thurman ERCOT | Paul Yockey ERCOT
Sarah Heselmeyer ERCOT | Kaci Jacobs TXU | Jim Lee AEP
Taylor Woodruff ONCOR | Kathy Scott Centerpoint Energy | Kyle Patrick NRG
Carolyn Reed Centerpoint Energy
WebEx Only
Amy Rafferty ESG | Connie Hermes NEC | Jasmine Thom CES
Barbara Goubeaud EC InfoSystems` | Lindsay Butterfield ERCOT