## Sheet1
TX SET Meeting Notes / Action Items
January 20th and 21st 2016
Agenda Item: | Decision / Resolution | Action Items :
Elections 2016 | Chair--Diana Rehfeldt TNMP Vice Chair-- Kyle Patrick NRG | Request that RMS confirm the leadership.
December 2015 Meeting Notes | Texas SET approved the December 1st meeting notes with one minor language change. | Texas SET Chair to have ERCOT post the final version on the December 1st 2015 meeting page.
Mass Transition/Default-POLR Rule | • RMS assignment to discuss Mass Transition— Possible POLR Rule change from two days out to one day out.
AMWG Update
Other discussion
Market Test Flight 0214 Update | ERCOT to provide flight update No update received
TX SET Procedures | On Hold-Discuss reline changes sent to the TXSET listserv for review | Leave current issue process in tact and continue to review document to identify where additional process improvements can be made
RMS Updates | No January Meeting
Flight 0216 Update | ERCOT provided the Flight 0216 statistics update.
IBANK03 or IBANK04 Discussion and Related Script Workbook Changes. | Texas SET reviewed the two scripts and agreed that IBANK03 could be used for the all the testing tracks that include IBANK03 and IBANK04. Texas SET and ERCOT identified the areas that will need to be updated with this change. Texas SET agreed to additional changes to the Script Workbook. Remove the Inventory List sheet from the Script workbook and place it in a separate workbook to be archived in the Texas SET documents. Remove the blank Sheet1. Remove the Additional Notes column on the IOU Testing Matrix. Correct the "X" location for the CBCI Column of the MOU Testing Matrix | ERCOT to update the documents for a final review at the next Texas SET meeting. The TDSPs will verify that they are in agreement with removing IBANK03 and only using IBANK04 for the Bank Change or Service Provider Change tracks.
ERCOT discussion of needed changes to the TMTP document. | ERCOT reviewed administrative changes that were missed when the changes were updated and approved for the Texas Market Test Plan. ERCOT requested that they update those changes and present these at the February 2nd 2016 RMS meeting. | Texas SET agreed and leadership will included the changes in the Update at the RMS meeting. Texas SET will also request that RMS vote on the changes.
Texas SET Swim Lanes Review
How to Re-group the Swim lanes? | Texas SET reviewed and made changes to the Swimlane groupings as needed. Texas SET agreed that ERCOT should add the date to the file names and included the date in the footer of each swimlane to document the version. | ERCOT to update the swimlanes and the groupings.
Texas SET 2016 Goals | Texas SET reviewed the Goals and made changes where needed. | The Texas SET Chair will present these at the February 2nd 2016 RMS meeting.
RMG Safety Net timelines--Review and continue discussions.--Note: PUCT to review final draft prior to Texas SET submitting changes to RMS | Texas SET reviewed the matrix and updated where needed. It was noted that the Priority and Safety Net spreadsheets would remain separate. It was noted that the matrix should include all meter types eliminating the need for multiple columns. ERCOT suggested that the criteria be changed to use the NAESB response timestamp as opposed to the 997 accept to confirm receipt of the 814_16. Texas SET continued to discuss the 3 PM cutoff time for submission; no changes were made.
| Texas SET reviewed and began updates to the Retail Market Guide (RMG) Safety NET language. | NRG is drafting language to be reviewed next month.
Cancellation Window Discussion
--- ERCOT Statistics --- If change needed, what method needed to obtain stakeholder approval (i. e. TX SET Release, Standalone NPRR)? | Texas SET and ERCOTdiscussed the MarkeTrak Cancel w/Approval statistics provided by ERCOT. Total for 2015--33959 Sub W/I the 1-Day window--22418 Remaining outside the window that should have used the 814_08 transaction-- approx. 6000
| Texas SET reviewed the Issue created by TXU and discussed the approach needed to try to reduce the numbers of MarkeTrak Issues. RMS Leadership suggested that the group determine how the 6000 outside the window can be reduced. Texas SET and ERCOT discussed the impacts of replacing the 1-Day window validation with not allowing backdated requests. ERCOT stated that the change would require an NPRR and related Impact Analysis. Texas SET and the TDSPs agreed that this should not impact the TDSP's processes. Texas SET also discussed the possiblity of changing the window validation for the Date Change Transaction as well. | The Texas SET Chair will send the Issue to ERCOT to obtain a number. The TDSPs will verify that there would be no impact to their systems.
Texas SET also discussed the possiblity of changing the window validation for the Date Change Transaction as well. This was included with the Issue submitted by TXU.
Retail Market Test Environment--Joint TDTMS Discussions
--Initial Analysis --SIM Date discussion | ERCOT and Texas SET discussed the SIM Date removal. The TDSPs reported that they will be able to support removing the SIM date by Flight 0616, but made sure that the change would only include the removal of the SIM Date without including any of the others changes from the SCR786 project. | ERCOT will update the Market Test material including the Flight Schedule to reflect this change.
| ERCOT, Texas SET and the TDTMS Leadership agreed that there are certain pieces of SCR786 that may require Texas SET input. All agreed that the two working groups will conduct a joint discussion at the second day of the Texas SET meeting for the next 3 or 4 months. Both groups will determine the need to continue this arrangement throughout the year. | The Texas SET Chair will request that ERCOT move the second day meeting to a larger room through the April meetings and that the end time of the meeting be published on the ERCOT meeting calendar. TDTMS Leadership will send agenda items as needed for the joint discussion to the Texas SET Leadership.
RMS assignments:
New Entrant Documentation—Procedures and Documentation Location
Add Master Customer List (MCL) guide back to the Texas SET Guides
Discussion Items on Hold
Texas SET Release Discussion | No action
REP Certification Matrix—Long-term solution | No action
Next Meeting--ERCOT MET Center | February 17th RM 168
February 18th RM 102
Attendees
Diana Rehfeldt TNMP | Kathryn Thurman ERCOT | Paul Yockey ERCOT
Kaci Jacobs TXU | Becky Taylor CNP | Kathy Scott CNP
Taylor Woodruff ONCOR | Kyle Patrick NRG | Michael Glass Sharyland Utillities
Lindsay Butterfield ERCOT | Jim Lee AEP | Monsherra Odanga ONCOR
Carolyn Reed CNP | Catherine Meiners ERCOT | Monica Jones Reliant
WebEx Only
Jasmine Thom CES | Daniel Bisutti ESG | Barbara Goubeaud EC Infosystems
Mary Sithiahao Stream Energy | Teresa Rodriques Stream Energy | Paula Shadle Nueces
Mike Woolsey ONCOR | Doug Somerville | Zahara Young Energy
Deborah Croce EC Infosystems