## Sheet1
Issue # | Date Entered | From Meeting | Type of issue | Active PGRR? (Y/N) | Description of Issue | Status | Key Planning Guide Sections | Leader | Target Date | Resolution
1 | 2016-02-10 | 2016-01-01 | Stability | N | What is the proper resolution of stability issues identified during the FIS? | Referred to PLWG by ROS Still identifying ROS Narrowed PLWG to review the Interconnection Timeline | 5.4.2 Full Interconnection Study 5.4.3 Steady State Aanlysis 5.4.5 Dynamic and Transient Stability (Unit Stability, Voltage, Subsynchronous Resonance) Analysis | Chad Thompson (ERCOT)
2 | 2016-02-10 | 2016-01-01 | Analysis Methodology | Y | Load/Generation Scaling in Steady State transmission planning studies (PGRR042) | - Referred to PLWG by ROS - Tabled - ERCOT to prepare revised PGRR |  | Jeff Billo (ERCOT)
3 | 2016-02-10 | 2016-01-01 | Analysis Methodology | N | Generation Deliverability | - Referred to PLWG by ROS. - Market participant requested links to past material. (Provided). - Ready to make recommendation to ROS? If not, what action items are needed to complete assignment? |  | Jeff Billo (ERCOT)
4 | 2016-02-10 | 2016-01-01 | Analysis Methodology | N | Treatment of DC-Ties in Whitepaper - Ensuring proper assumption about DC-Tie used in ERCOT RTP cases | - Seeking ROS Direction - ROS approved revisions. |  | Jeff Billo (ERCOT)
5 | 2016-02-10 | 2016-01-01 | Data Requirements | N | ERCOT ALDR request management - Ensuring stakeholder review of large annual data requests. |  |  | Ken Donohoo (ONCOR)
6 | 2016-02-10 | 2016-01-01 | Model Data | N | DG reporting and modeling |  |  | Ken Donohoo (ONCOR)
7 | 2016-02-10 | 2016-01-01 | Analysis Methodology | N | Generation Interconnection studies consistency of analysis between TSPs |  |  | Ken Donohoo (ONCOR)
8 | 2016-02-10 | 2016-01-01 | Analysis Methodology | N | N-1-1 definition, application and understanding |  |  | Ken Donohoo (ONCOR)
9 | 2016-02-10 | 2016-01-01 | Model Data | N | Inclusion of Generators meeting Section 6.9 Requirements | Impacts to study results |  | David Mercado (Centerpoint)
10 | 2016-03-02 | 2016-03-01 | Model Data | Y | PGRR-046 Addition of Geomagnetically Induced Current (GIC) Model Building Requirements | PGRR-046 Submitted by ERCOT.