## Timeline 2015
Date | Residential Annual Validation Task List | Status
2015-03-30 | ERCOT to provide list of ESI IDs to TDSPs | Complete
2015-04-10 | TDSPs to provide finalized list of ESI IDs to ERCOT | Complete
2015-04-15 | Market Notice announcing lists are available to CR of record | Complete
2015-04-15 | TDSPs to begin submitting 814_20 transactions | Complete
2015-09-30 | TDSPs to complete submissions of all 814_20 transactions | Complete
2015-10-02 | ERCOT completes review of expected database changes | Complete
Date | Business Annual Validation Task List | Status
2015-03-30 | ERCOT Provides Qtr Validation Lists to TDSPs (BUS Only) | Complete
2015-03-30 | ERCOT to provide list of ESI IDs to TDSPs | Complete
2015-04-10 | TDSPs to provide finalized list of ESI IDs to ERCOT | Complete
2015-04-15 | Market Notice announcing lists are available to CR of record | Complete
| Complete Quarterly Validations (to be renamed as "Other" Annual Validation - ie Zip Code reconciliation efforts) | Complete
2015-04-15 | TDSPs to begin submitting 814_20 transactions | Complete
2015-09-30 | TDSPs to complete submissions of all 814_20 transactions | Complete
2015-10-02 | ERCOT to review database for expected changes | Complete
2015-10-05 | All TDSPs have submitted at least 99% of changes | Complete
2015-11-02 | Initial Weather Responsiveness Report Produced | Complete
2016-01-02 | Weather Responsiveness Overdue Report Produced | Complete
Monthly | Continue Overdue Reporting Until All Complete | In Progress
Update: 02/24/2016