## Timeline 2015
Date | Residential Annual Validation Task List | Status
2015-03-30 | ERCOT to provide list of ESI IDs to TDSPs | Complete
2015-04-10 | TDSPs to provide finalized list of ESI IDs to ERCOT | Complete
2015-04-15 | Market Notice announcing lists are available to CR of record | Complete
2015-04-15 | TDSPs to begin submitting 814_20 transactions | Complete
2015-09-30 | TDSPs to complete submissions of all 814_20 transactions | Complete
2015-10-02 | ERCOT completes review of expected database changes | Complete
Date | Business Annual Validation Task List | Status
2015-03-30 | ERCOT Provides Qtr Validation Lists to TDSPs (BUS Only) | Complete
2015-03-30 | ERCOT to provide list of ESI IDs to TDSPs | Complete
2015-04-10 | TDSPs to provide finalized list of ESI IDs to ERCOT | Complete
2015-04-15 | Market Notice announcing lists are available to CR of record | Complete
| Complete Quarterly Validations Zip Code reconciliation efforts to be included in AV pursuant to LPG 11.3, Additional Validations (Zip Code reconciliation efforts under 11.3.5,Validation of Service Address Zone Improvement Plan Code) | Complete
2015-04-15 | TDSPs to begin submitting 814_20 transactions | Complete
2015-09-30 | TDSPs to complete submissions of all 814_20 transactions | Complete
2015-10-02 | ERCOT to review database for expected changes | Complete
2015-10-05 | All TDSPs have submitted at least 99% of changes | Complete
2015-11-02 | Initial Weather Responsiveness Report Produced | Complete
2016-01-02 | Weather Responsiveness Overdue Report Produced | Complete
Monthly | Continue Overdue Reporting Until All Complete | In Progress
Update: 02/24/2016