## Sheet1
TX SET Meeting Notes / Action Items
March 23rd - 24th 2016
Agenda Item: | Decision / Resolution | Action Items :
February 2016 Meeting Notes | Minor changes were made to the Meeting Notes. | The Texas SET Chair will have the updated notes posted to the February Texas SET meeting page key documents.
Mass Transition/Default-POLR Rule | • RMS assignment to discuss Mass Transition— Possible POLR Rule change from two days out to one day out.
AMWG Update
Other discussion
Market Test Flight 0214 Update | ERCOT to provide flight update No update received
TX SET Procedures | On Hold-Discuss reline changes sent to the TXSET listserv for review | Leave current issue process in tact and continue to review document to identify where additional process improvements can be made
RMS Updates
Request to Review RMG Section 7.10 Procedures for Extended Unplanned System Outages. --Determine if clarifying language is needed to guide market participants when giving notices and additional instructions to the market. | Texas SET reviewed the language in the Extended Outage sections 7.10, 7.10.1, and 7.10.2 and made changes where needed. | The Texas SET Chair will send the redlined document to the meeting attendees for review and to facilitate continued discussion at the April meeting. Texas SET will begin with section 7.10.3.
Flight 0216 Update
IBANK03 or IBANK04 --Final Review ERCOT updated Documents | Texas SET reviewed the updated documents and made an additional change to the "Change from an Establilsihed Service Provider to a different Established Service Provided" scenario. The change was to remove the IBANK04 script and add the ENR01 script to this scenario. It was determined that the bank does not need to be involved in this scenario. | The Texas SET Chair will send the updated script pack to the ERCOT Flight Administrator..
Texas SET Swim Lanes Review
ERCOT updated documents-810_02 addtion to swimlanes with 867_03 flow | ERCOT reviewed the updated swimlanes. ERCOT will review the corresponding MOU swimlanes to determine any updates needed that involve 810s. | The Texas SET Chair will send the updated swimlanes to the Texas SET email distribution list for comments to be returned at the April Meeting. ERCOT will get with Nueces to determine what if any changes are needed.
RMG Safety NET Timelines
Notes: PUCT to Review Final Draft Prior to Texas SET Submitting Changes to RMS | The final review of these changes were delayed until Texas SET completes the review of section 7.10 Procedures for Extended Unplanned System Outages.
ONCOR Discussion Items
Possible Modification to Letter of Authorization (LOA) -- ONCOR | ONCOR requested that Texas SET table the discussion until the April Meeting.
Proposed Change to the Prepay Language in RMG | Texas SET reviewed the changes proposed by ONCOR and determined that the other TDSPs would keep their language the same as already written. | ONCOR to submit and RMGRR for their changes.
Validation Processes When a Character is Included in the Customer Name on a Switch or MVI Transaction. | Texas SET determined that further investigation is needed prior to determining any changes that may be necessary. The group reviewed ANSI ASCII basic, extended and not allowed character sets listed at the following url. http://edi.aaltsys.info/01_standards.html ERCOT stated that they use the ERCOT Initiated MarkeTrak subtype to sync system orders when they receive a 997 reject from a TDSP. | TDSPs will determine what special characters that they are rejecting and return with a list at the April meeting.
CNP Meter Removal Due to Fire or Demolition Discussion | Texas SET agreed to Centerpoint's proposal to use the "NONE" in the meter field for subsequent transactions after a meter is removed due to a fire on demolition. | Centerpoint will update the market when this change will be implemented.
TXU--Section 7.11.3.2 Monthly Submission of Customer Billing Contact Information Discussion
CBCI File Process-- | Texas SET reviewed the language and made changes to close the loop on REP responsibilities in the CBCI file process. | The Texas SET Chair will put the redlined changes into the RMGRR form and send to ERCOT for submission.
Issues
2016-I141--Cancellation / Date Change Window Draft NPRR to change | Texas SET drafted the NPRR to make the language changes for this issue. | The Texas SET Chair will put the changes into an NPRR and RMGRR form and send to ERCOT for submission. The Texas SET Chair will also update the issue and send to ERCOT to repost.
(Close 2016-I142) Determined that it was not a DEV issue and request from TDTMS to review Section 15.4.1.4 New ESI ID creation of the Protocols to see if there is some language that can be added to the transaction timing of the 814_20. | Texas SET drafted the NPRR to make the language changes for this issue. | The Texas SET Chair will put the changes into an NPRR form and send to ERCOT for submission. The Texas SET Chair will also update the issue and send to ERCOT to repost.
Retail Market Test Environment--Joint TDTMS Discussions
TDTMS Agenda items | ERCOT reviewed the Requirments document and made changes where needed. Texas SET and TDTMS determined that there will not be a need to conduct a joint meeting at April's meeting and that any future input will be upon request from TDTMS.
RMS assignments on hold:
New Entrant Documentation—Procedures and Documentation Location | No Action taken.
Add Master Customer List (MCL) guide back to the Texas SET Guides | No Action taken.
Discussion Items on Hold
Texas SET Release Discussion | No action taken.
REP Certification Matrix—Long-term solution | No action taken.
Next Meeting--ERCOT MET Center | April 20th RM 102
April 21st RM 102
Attendees
Diana Rehfeldt TNMP | Lindsay Butterfield ERCOT | Kathryn Thurman ERCOT
Paul Yockey ERCOT | Jim Lee AEP | Kaci Jacobs TXU
John Schatz TXU | Ron Kindler ONCOR | Kyle Patrick NRG
Becky Taylor CNP | Carolyn Reed CNP | Chris Rowley ONCOR
Sam Pak ONCOR | Catherine Meiners ERCOT | Vikrum Gupta ERCOT
Monica Jones NRG
Webex
Jasmine Thom CES | Connie Hermes NEC Retail | Dan Bisutti ESG
Deb Belin Aurea | Kathy Scott CNP | Rebecca Reed Zerwas NRG
Deborah Croce EC Infosystems | Barbara Goubeaud EC Infosystems | Stephen Wilson SU
Debbie McKeever ONCOR | Isabel Durham CNP | Suzy Clifton ERCOT