## Slide 1
Impact Analysis
Cost Estimation Metrics
05/12/2016

## Slide 2: Impact Analysis Cost Estimation Metrics
ERCOT continues to review Revision Request IA cost estimates compared with actual spend on their related implementation projects.
Data Used for Analysis
  38 Revision Request projects completed from 2013-2015
Summary-level results are now available
Still in Progress
  Individual project analysis
  Efficiency/improvement opportunity identification

## Slide 3: Revision Request Projects – IA Range to Actual Spend Variance
Less than $100k
26 Projects
$100k or greater
12 Projects
Exceeds IA Range
9 Projects
Below IA Range
23 Projects
Within IA Range
6 Projects
If actual spend falls within the IA range the variance is 0
Chart: Revision Requests IA Results: 2013 - 2015
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38
Actual Spend Variance | -12935.22 | -16666.06 | -37449.05 | -44756.07 | -35450.43 | -16526.31 | -15668.75 | -50606 | -4247.46 | -1256 | -26949 | -12126.22 | 0 | -9429.49 | -14270 | 5906.75 | -43508.42 | 0 | -22356.25 | -11098.57 | 20350 | -69907 | 767 | -47596.58 | 14114 | -770.5 | -102411.54 | 39699 | 0 | -25164.3 | -35982.81 | 169955 | 0 | 0 | 233094.58 | 114279 | 130549.98 | 0
Baseline Estimate % Variance
NOGRR093 (M)
NPRR481 (M)
NPRR207 (M)
NPRR500 (M)
NPRR457 (M)
NPRR479 (M)
NPRR543 (M)
NPRR385 (M)
NPRR456 (E)
NPRR407 (M)
NPRR397, NPRR464 (M)
SCR773 (M)
NOGRR105 (M)
SCR775 (M)
SCR768 (E)
NPRR514 (M)
SCR770 (M)
NPRR476 (M)
SCR772 (M)
NPRR393 (M)
NPRR586 (M)
NPRR377 (E)
NPRR313 (M)
NPRR260 (M)
NPRR469 (M)
SCR769 (M)
NPRR425 (E)
NPRR463 (M)
2015 CMM release (1) (V)
NPRR520 (E)
SCR779 (E)
NPRR322 (M)
NPRR416, NPRR575 (M)
NPRR461 (E)
SCR756 (M)
NPRR347, NPRR400 (E)
2015 Mkt Sys Enhancements (2) (V)
2014 Mkt Sys Enhancements (3) (V)
(1) NPRR559, NPRR597, NPRR601, NPRR639, SCR778
(2) NPRR626, NPR645, NPRR665, OBD
(3) NPRR568, NPRR240, NPRR532, NPRR555, NPRR564, NPRR598
(E) ERCOT Sponsored
(M) Market Sponsored
(V) Various

## Slide 4: Impact Analysis Cost Estimation Metrics
Observations:
Reasons for Variances Between IA and Actual Project Spend | Examples
Approved project scope changes | SCR756, NPRR347/400, 2015 Market System Enhancements
Incorrect assessment of project complexity / ERCOT labor less than estimate | NPRR377, NPRR425, SCR770, NPRR260
Missed system impact in IA process | NPRR322, NPRR463
Expedited IA process due to delivery urgency | 2015 Market System Enhancements, NPRR322
Change in project resource mix (using contractors instead of FTEs) | NPRR322
Hardware/software components delivered with on-hand inventory (or not needed) | NPRR385

## Slide 5: Revision Request Variance Analysis – 38 Projects
Actual Spend Range | Sum of IA Midpoint | Sum of Actuals | Variance
Less than $100k | $1,760,000 | $1,174,805 | -$585,195
Greater than $100k | $4,842,500 | $5,403,469 | $560,969
Totals | $6,602,500 | $6,578,274 | -$24,226
Actual Spend Range | Project Count | Total Variance | Average / Project | Absolute Average | Min / Max
Less than $100k | 26 | -$452,436 | -$17,401 | $20,566 | -$69,907 / +$20,350
Greater than $100k | 12 | $524,019 | $43,668 | $70,928 | -$102,412 / +$233,095
Negative variance = under-spend
Positive variance = over-spend
0.4% variance
This report measures the variance between actuals and the nearest point of the IA estimate range
This report measures the variance between actuals and the IA midpoints

## Slide 6: Impact Analysis Cost Estimation Metrics
Summary Observations:
Overall, Impact Analysis cost estimates align reasonably well with actual project spending
An overhaul of the process is not needed; however, we do see opportunities for improvement
  Step 1: Improve efficiency on small IAs to allow for more focus on large IAs
  Next steps: TBD