|  |  |  | System Planning |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Monthly Status Report April 2016 |  |  |
|  |  |  | Report Highlights |  |  |
|  | - ERCOT is currently reviewing proposed transmission improvements with a total cost of $1.5 Billion. - Transmission Projects endorsed in 2016 total $58.5 Million. - All projects (in engineering, routing, licensing and construction) total approximately $6.81 Billion. - Transmission Projects energized in 2016 total about $149.0 Million. |  |  |  |  |

Regional Planning Group Project Reviews

- AEPSC has submitted the LRGV Area Transmission Improvements project. This is a Tier 1 project that is estimated to cost $621.5 million. This project is currently under ERCOT independent review.

- Oncor has submitted the Big Brown – Navarro 345 kV double-circuit upgrade project. This is a Tier 3 project that is estimated to cost $10.2 million. The project has completed the RPG review and based on the ERCOT independent review, ERCOT is not recommending the Oncor Big Brown – Navarro 345 kV DCKT upgrade project at this time.

- AEPSC has submitted the Hidalgo-Starr Transmission project. This is a Tier 1 project that is estimated to cost $151.1 million. This project is currently under ERCOT independent review.

- Lone Star has submitted the North Central 345 kV Transmission project. This is a Tier 1 project that is estimated to cost $83.1 million. ERCOT has completed the independent review and based on the review, ERCOT is not recommending the North Central 345 kV Transmission project upgrade project at this time..

- CPS Energy and Sharyland Utilities have jointly submitted the LRGV Import project. This is a Tier 1 project that is estimated to cost $643.7 million. This project is currently under ERCOT independent review.

- AEPSC and Oncor have jointly submitted the Barrilla Junction Area Improvements project. This is a Tier 1 project that is estimated to cost $111.9 million. This project is currently under ERCOT independent review.

- Brazos Electric Cooperative (BEC) has submitted the Salt Creek Area project. This is a Tier 2 project that is estimated to cost $17 million. This project is currently under ERCOT independent review.

- AEPSC has submitted the Maverick County Transmission project. This is a Tier 2 project that is estimated to cost $44.3 million. This project is currently under ERCOT independent review.

- Brazos Electric Cooperative (BEC) and AEPSC have jointly submitted the Katz to Tardis project. This is a Tier 2 project that is estimated to cost $30 million. This RPG project is submitted as a replacement to the BEC Aspermont–Knox Area Improvement project that was submitted for RPG review on November 5, 2015. This project is currently under ERCOT independent review.

- Oncor has submitted the Andrews County South–North Andrews–Holt 138 kV project. This is a Tier 3 project that is estimated to cost $33.5 million. This project has completed the review and ERCOT will prepare the RPG letter.

- Oncor has submitted the Riverton–Sand Lake 138kV line project. This is a Tier 2 project that is estimated to cost $26 million. This project is currently under ERCOT independent review.

- Sharyland has submitted the Vealmoor second 345/138 kV auto project. This is a Tier 3 project that is estimated to cost $7 million. This project has completed the review and ERCOT will prepare the RPG letter.

- Oncor has submitted the Southwest DFW 345 kV Upgrades project. This is a Tier 3 project that is estimated to cost $40 million. This project is in study mode.

- TNMP has submitted the Line 69H Rebuild and Conversion project. This is a Tier 1 project that is estimated to cost $50.6 million. This project is currently under ERCOT independent review.Oncor has submitted the Norwood–Amelia/East Levee 138 kV Double-Circuit Line Upgrade project. This is a Tier 3 project that is estimated to cost $15 million. This project is submitted for RPG comments

- AEPSC and Oncor have jointly submitted the Far West Texas project. This is a Tier 1 project that is estimated to cost $423 million. This project is submitted for RPG comments

# Planning Model Activities

The short term calendar of major planning model events is as follows.

- Jul 1, 2016	Post 16SSWG cases

- Jul 20, 2016 	Post 16SSWG Contingency Files and Planning Data Dictionary

- Aug 15, 2016	Begin 16SSWG Update 1

- Oct 15, 2016	Post 16SSWG Update 1

The following table shows interconnection projects that met Planning Guide section 6.9 (1)(b) – 6.9(1)(d) and were not modeled in SSWG cases due to lack of RARF data in accordance with Planning Guide section 6.9(1)(a) and 6.9 (3).  “Insufficient Planning Data” refers to data needed only for the Steady State model and is not the complete set of data marked Required for Planning in the Resource Registration Glossary.

# Other Notable Activities

- ERCOT is currently working on reliability analysis for the 2016 Regional Transmission Plan (RTP). The results and cases for the 2016 RTP N-1 reliability analysis along with the list of preliminary projects were posted on MIS Secure website on April 11th 2016. ERCOT also continues to work on the 2016 Long Term System Assessment (LTSA). ERCOT developed and presented load forecasts on three of the eight scenarios and is currently working on generation expansion analysis.

- The System Protection Working Group completed the 2016 CY cases on April 1, 2016.  Work on the 2016 FY cases has begun.

- At the request of the Public Utility Commission, ERCOT is currently studying how to integrate the Lubbock Power and Light System into the ERCOT grid.  An update was presented at the April Regional Planning Group meeting.