## Slide 1
2016 RTP Update
June, 2016
RPG Meeting

## Slide 2: Agenda
Status update
Preliminary reliability projects of 2016 RTP
Next steps

## Slide 3: 2016 RTP status update
Initial start cases posted on MIS Secure on March 8 2016
Single-event (N-1) secure cases with reliability projects posted on MIS Secure on April 11 2016
Currently in progress
  TSP review of reliability projects
  P3 (G1+N1) and P6.2 (X1+N1) reliability projects and updated reliability case posting
  Sensitivity analysis case preparation
  Short circuit study initial case preparation
  Economic start case preparation

## Slide 4: RTP upgrades summary by voltage level (preliminary findings)
 | 69 kV | 138 kV | 345 kV | Grand Total
Line addition | 1 | 1 | - | 2
Line upgrade | 1 | 6 | - | 7
Reactor/Capacitor addition | - | 3 | - | 3
Transformer addition | 1 | 1 | - | 2
Terminal upgrade |  | 1 | - | 1
Grand Total | 4 | 10 | - | 14
 | 69 kV | 138 kV | 345 kV | Grand Total
Line addition | 2 | 6 | 1 | 9
Line upgrade | 3 | 19 | - | 22
Reactor/Capacitor addition | - | 6 | 2 | 8
Transformer addition | - | 3 | 5 | 8
Transformer upgrade | - | - | 1 | 1
Other** | 3 | 4 | 1 | 8
Grand Total | 8 | 38 | 10 | 56
Equipment upgrades and additions identified in 2016 RTP
New* upgrades and additions identified in 2016 RTP
*Not found in MOD or previous RTPs
**Other: Terminal equipment upgrades and substation additions

## Slide 5: List of new 138 kV upgrades identified in 2016 RTP
RTP Project ID | Project Name | County | Year needed
North Central | Terrell North – Terrell Switch upgrade | Kaufman | 2018*
North Central | Kaufman Northwest – Rose Hill upgrade | Kaufman | 2019
North Central | Grape vine ball street – Grape vine junction upgrade | Tarrant | 2021*
Far West | New ‘Wicket to Permian Basin’ line | Reeves/Ward | 2018*
South Central | Wells Branch to Howard tap upgrade | Travis | 2022
South | South McAllen – Bensten terminal upgrade | Hidalgo | 2018*
Coast | New switched shunt at Jones Creek | Brazoria | 2018*
Coast | New switched shunt at Velasco | Brazoria | 2021*
Coast | Bunker area line upgrades | Harris | 2018*
*This table indicates the study year when the reliability needs were identified, it is possible that the need exists in the prior year. TSPs are encouraged to validate the need in the prior years as part of their project study.

## Slide 6: Next steps
Case conditioning
Initial start cases, and contingency list ready
Set 1 (P1, P7),
Set 2 (P2, P4, P5) contingency analysis for the base cases
Set 3 (P3: G-1+N-1, part of P6: X-1+N-1) contingency analysis for the base cases
Economic case preparation and analysis
2016 RTP Report
Blue box: complete
Yellow box: in progress
Short circuit study
Long-lead time equipment study
Sensitivity analysis
Other Reliability Studies
Multiple element outage and cascading analyses

## Slide 7: Question
?