## Sheet1
TX SET Meeting Notes / Action Items
May 18th and 19th 2016
Agenda Item: | Decision / Resolution | Action Items :
April 2016 Meeting Notes | No changes were made to the notes. | The Texas SET Chair will have the notes posted to the April 2016 meeting page.
Mass Transition/Default-POLR Rule | • RMS assignment to discuss Mass Transition— Possible POLR Rule change from two days out to one day out.
AMWG Update
Other discussion
Market Test Flight 0214 Update | ERCOT to provide flight update No update received
TX SET Procedures | On Hold-Discuss reline changes sent to the TXSET listserv for review | Leave current issue process in tact and continue to review document to identify where additional process improvements can be made
RMS Updates
• Draft NPRR, Modifications to Date Change and Cancellation Evaluation Window—RMS voted to approve the submittal of the NPRR for a number. • Draft RMGRR, Update Retail Market Guide to align with NPRRXX—RMS Voted to approve the submittal of the RMGRR for a number. | The Texas SET Chair provided an update from the May RMS meeting.
• 771NPRR-01 Clarifications to New ESI ID Creation Process 050416—RMS voted to approve the submittal of the NPRR for a number. | The Texas SET Chair provided an update from the May RMS meeting.
• RMGRR137, Timeline and Completion Process for Correcting Customer Billing Contact Information Files o Urgent Status—RMS voted to approve. o Language Review—RMS voted to approve both the language and the Impact Analysis since there is no ERCOT impact. | The Texas SET Chair provided an update from the May RMS meeting.
Flight Update
ERCOT presented an update on the June 2016 Flight.
RMG Safety NET Timelines
Notes: PUCT to Review Final Draft Prior to Texas SET Submitting Changes to RMS | Texas SET continued to discuss proposed changes and the need to have the Safety Net spreadsheets for the daily process. | TDSPs will research and provide feedback at the next TX SET meeting reporting the number of Safety Net ESI IDs that they received where the corresponding EDI transactions have already been received and / or processed. CRs will research to determine if there are reasons why they believe that they have not received the response transactions that would cause the ESI ID to show up on the Safety Net spreadsheets.
RMG Section 7.10 Procedures for Extended Unplanned System Outages. -- Finalize Language from Attendee Feedback | Texas SET finalized the language changes and drafted an RMGRR. | The Texas SET Chair will submit the RMGRR for a number and a vote at the August RMS meeting.
Discussion Items
Possible Modification to Letter of Authorization (LOA) -- ONCOR | ONCOR removed this as an agenda discussion item prior to the meeting.
Validation Processes When a Character is Included in the Customer Name on a Switch or MVI Transaction. Review Nodal Protocol Section19.5.1 Alphanumeric Field(s)--Continue Discussions Based on Attendee Feedback | Texas SET continued to discuss options for handling these Special Language characters and determined an official Issue will need to be created to track the discussion. It was determined that an NPRR change will be needed regardless of the results of the discussions. | ERCOT will created the issue. Market Participants will determine if they can find another solution to deal with the Special Language Characters exceptions that they are experiencing.
NRG 814_28 Question and Answer discussion | Texas SET determined that the Tenant Based Permit is still a valid code that is used for some areas of Texas. | NRG will send examples of the use to the TDSPs to determine if they are valid or if they have been used in error. Feedback will be provided at the June Texas SET meeting.
Sharyland Deferred Cost Recovery Charge (DCRC)—TXU Requested Discussion of Possible New SAC04 Code | Texas SET discussed when the SAC04 code would be updated and how much time the TDSPs are required to give the market before the new charges go into effect. It was determined that the effective date of the change will depend on the results of the rate case before the PUCT. | ERCOT will work with Sharyland to develop the change control required to add a new SAC04 code to the Texas SET Implementation Guide.
Issues
2016-I141--Cancellation / Date Change Window RMS Voted to Approve the Submission of Both the NPRR and RMGRR. One More Review of Business Case Language and Gain Consensus for Language Prior to Submission. | Texas SET reviewed and made changes to the Business Case as needed. It was determined that RMGRR needs to be submitted on an urgent basis so it can move through the governance process with the NPRR. | The Texas SET Chair will submit both the NPRR and RMGRR for a number.
Retail Market Guide Section 7.11.2, Acquisition and Transfer of Customers from one Retail Electric Provider to Another--Remove 3 day waiting period on Self Selected Switches Discussion | Texas SET reviewed and finalized the language in the RMGRR. | The Texas SET Chair will submit the RMGRR for a number and a vote at the August RMS meeting.
RMS assignments:
New Entrant Documentation—Procedures and Documentation Location | Texas SET began drafting an outline of items needed for New Entrants. | The Texas SET Chair will send the draft to the TXSET email distribution list for review and feedback to be given at the June meeting.
Add Mass Customer List (MCL) guide back to the Texas SET Guides | Texas SET drafted a new Mass Customer List guide. | The Texas SET Chair will send the draft to the TXSET email distribution list for review and feedback to be given at the June meeting.
Discussion Items on Hold
Texas SET Release Discussion | No Action
REP Certification Matrix—Long-term solution | No Action
Next Meeting--ERCOT MET Center | June 22nd RM 168
June 23rd RM 102--Cancelled at the May meeting. Texas SET will re-visit the need for meeting day two the month prior to that meeting to assist attendees in their travel plans.
Attendees
Diana Rehfeldt TNMP | Kathryn Thurman ERCOT | Paul Yockey ERCOT
Kaci Jacobs TXU | Kyle Patrick NRG | Jim Lee AEP
Carolyn Reed CNP | Kathy Scott CNP | Sam Pak ONCOR
Becky Taylor CNP
Webex
BarbarGoubeaud EC InfoSystems | Jasmine Thom CES | Mary Sithihou Stream Energy
Mike Woolsey ONCOR | Stephen Wilson SU | Teresa Rodriquez Stream Energy
Deborah Croce InfoSystems | Michael Glass SU