|  |  |  | System Planning |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Monthly Status Report May 2016 |  |  |
|  |  |  | Report Highlights |  |  |
|  | - ERCOT is currently reviewing proposed transmission improvements with a total cost of $1.5 Billion. - Transmission Projects endorsed in 2016 total $58.5 Million. - All projects (in engineering, routing, licensing and construction) total approximately $6.81 Billion. - Transmission Projects energized in 2016 total about $149.0 Million. |  |  |  |  |

Regional Planning Group Project Reviews

- AEPSC has submitted the LRGV Area Transmission Improvements project. This is a Tier 1 project that is estimated to cost $621.5 million. ERCOT will present the results of the independent review to the Board of Directors in June 2016 for its endorsement.

- AEPSC has submitted the Hidalgo-Starr Transmission project. This is a Tier 1 project that is estimated to cost $151.1 million. ERCOT will present the results of the independent review to the Board of Directors in June 2016 for its endorsement.

- CPS Energy and Sharyland Utilities have jointly submitted the LRGV Import project. This is a Tier 1 project that is estimated to cost $643.7 million. ERCOT will present the results of the independent review to the Board of Directors in June 2016 for its endorsement.

- AEPSC and Oncor have jointly submitted the Barrilla Junction Area Improvements project. This is a Tier 1 project that is estimated to cost $111.9 million. This project is currently under ERCOT independent review.

- Brazos Electric Cooperative (BEC) has submitted the Salt Creek Area project. This is a Tier 2 project that is estimated to cost $17 million. This project is currently under ERCOT independent review.

- AEPSC has submitted the Maverick County Transmission project. This is a Tier 2 project that is estimated to cost $44.3 million. This project is currently under ERCOT independent review.

- Brazos Electric Cooperative (BEC) and AEPSC have jointly submitted the Katz to Tardis project. This is a Tier 2 project that is estimated to cost $30 million. This RPG project is submitted as a replacement to the BEC Aspermont–Knox Area Improvement project that was submitted for RPG review on November 5, 2015. This project is currently under ERCOT independent review.

- Oncor has submitted the Riverton–Sand Lake 138kV line project. This is a Tier 2 project that is estimated to cost $26 million. This project is currently under ERCOT independent review.

- Oncor has submitted the Southwest DFW 345 kV Upgrades project. This is a Tier 3 project that is estimated to cost $40 million. This project is in study mode.

- TNMP has submitted the Line 69H Rebuild and Conversion project. This is a Tier 1 project that is estimated to cost $50.6 million. This project is currently under ERCOT independent review.

- Oncor has submitted the Norwood–Amelia/East Levee 138 kV Double-Circuit Line Upgrade project. This is a Tier 3 project that is estimated to cost $15 million. This project has completed the Regional Planning Group review process, and ERCOT will prepare an RPG endorsement letter.

- AEPSC and Oncor have jointly submitted the Far West Texas project. This is a Tier 1 project that is estimated to cost $ 423 million. This project is currently in study mode.

- Brazos Electric Cooperative (BEC) has submitted the Northern Johnson County Area Improvement project. This is a Tier 2 project that is estimated to cost $ 8.1 million. This project is in its RPG comment period.

# Planning Model Activities

The short term calendar of major planning model events is as follows.

- Jul 1, 2016	Post 16SSWG cases

- Jul 20, 2016 	Post 16SSWG Contingency Files and Planning Data Dictionary

- Aug 15, 2016	Begin 16SSWG Update 1

- Oct 15, 2016	Post 16SSWG Update 1

The following table shows interconnection projects that met Planning Guide section 6.9 (1)(b) – 6.9(1)(d) and were not modeled in SSWG cases due to lack of RARF data in accordance with Planning Guide section 6.9(1)(a) and 6.9 (3).  “Insufficient Planning Data” refers to data needed only for the Steady State model and is not the complete set of data marked Required for Planning in the Resource Registration Glossary.

# Other Notable Activities

- ERCOT is currently working on reliability analysis for the 2016 Regional Transmission Plan (RTP). The results and cases for the 2016 RTP N-1 reliability analysis along with the list of preliminary projects were posted on MIS Secure website on April 11th 2016. ERCOT also continues to work on the 2016 Long Term System Assessment (LTSA). ERCOT has completed generation expansion analysis on seven of the eight scenarios.

- The System Protection Working Group is working on the 2016 FY cases with a projected completion date of 07/01/2016.

- At the request of the Public Utility Commission, ERCOT is currently studying how to integrate the Lubbock Power and Light System into the ERCOT grid.  An update was presented at the March Regional Planning Group meeting.