## Slide 1
Flight Testing Update
Paul Yockey
Flight Administrator
Texas Set Working Group
07/20/2016

## Slide 2
Agenda
Flight 0616 Schedule
Flight 0616 Summary
Flight 0616 Adhoc Summary
Flight 1016 Schedule
Questions

## Slide 3: Flight 0616 Schedule
Flight 0616 signup began 05/11/16
Flight 0616 signup deadline was 05/18/16 (Adhoc, 06/24/16 for Current MPs Only, subject to Flight Administrator and TDSPs’ Approval)
Connectivity testing began 05/24/16
Day 1 transactions began 06/13/16
Flight 0616 concluded on 06/24/16 (Contingency/Adhoc Period until 08/12/16)
No transactions were sent or received the week of July 4 (7/4 – 7/8)
Simulated (SIM) Dates were not used in Flight 0616
Texas Set Working Group
07/20/16

## Slide 4: Flight 0616 Summary
Flight 0616 is 100% complete
2 New CRs tested
0 Existing CRs tested
814 tasks were completed including connectivity
Texas Set Working Group
07/20/16

## Slide 5: Flight 0616 Adhoc Summary
Adhoc testing is 100% complete
2 CR tested for Adhoc Bank Change
3 CRs tested for 1 Additional Territory
260 tasks were completed including connectivity
Texas Set Working Group
07/20/16

## Slide 6: Flight 1016 Schedule
Flight 1016 signup begins 09/07/16
Flight 1016 signup deadline is 09/14/16 (Adhoc, 10/21/16 for Current MPs Only, subject to Flight Administrator and TDSPs’ Approval)
Connectivity testing begins 09/20/16
Day 1 transactions begin 10/10/16
Flight 1016 is scheduled to conclude on 10/21/16 (Contingency/Adhoc Period until 11/18/16)
Simulated (SIM) Dates will not be used in Flight 1016
Texas Set Working Group
07/20/16

## Slide 7: Questions
Questions?
Texas Set Working Group
07/20/16