## Sheet1
TX SET Meeting Notes / Action Items
June 22nd 2016
Agenda Item: | Decision / Resolution | Action Items :
Change Control Call--10:15 AM
• 2016 -804 Sharyland request for a new SAC04 code with a description of “Deferred Cost Recovery Charge” and identified as “MSC056”. | Texas SET reached consensus to recommend RMS approve the change control at their August 2nd meeting. | Texas SET will review redline changes to the 810_02 Texas SET Implementation Guide SAC04 codes spreadsheets at the Texas SET meeting following the RMS vote on the Change Control.
May 2016 Meeting Notes | Minor updates were made to the notes. | The Texas SET Chair will have the notes posted to the Texas SET meeting page key documents.
Mass Transition/Default-POLR Rule | • RMS assignment to discuss Mass Transition— Possible POLR Rule change from two days out to one day out.
AMWG Update
Other discussion
Market Test Flight 0214 Update | ERCOT to provide flight update No update received
TX SET Procedures | On Hold-Discuss reline changes sent to the TXSET listserv for review | Leave current issue process in tact and continue to review document to identify where additional process improvements can be made
RMS Updates
• 778NPRR, Modifications to Date Change and Cancellation Evaluation Window— • 139RMGRR, Update Retail Market Guide to align with NPRR778— | The Texas SET Chair stated that both revisions were approved at RMS and that PRS subsequently approved the NPRR. ERCOT announced that the Impact Analysis (IA) was completed with a $50K to $75K price. | Texas SET will review the IA at the July Texas SET meeting and make a recommendation to RMS to endorse the IA for PRS at the August 2nd meeting.
• 771NPRR-01 Clarifications to New ESI ID Creation Process 050416— | The Texas SET Chair stated that both revisions were approved at RMS.
• 140RMGRR, Efficiencies for Acquisition Transfer Process— | The Texas SET Chair stated that both revisions were approved at RMS.
• 141RMGRR, Clarifying Procedures for Market Participants During an Extended Unplanned System Outage— | The Texas SET Chair stated that both revisions were approved at RMS.
Flight Update | ERCOT presented the statistics for the 0616 Test Flight.
| The ERCOT Flight Administator stated that Texas SET will need to review the SOR01 and 02 scripts to make possible changes to which test day the 814_20s are sent. | This will be added to the agenda for July.
RMG Safety NET Timelines
Notes: PUCT to Review Final Draft Prior to Texas SET Submitting Changes to RMS | Texas SET members discussed the TDSP feedback based on internal analysis comparing timing of EDI transactions as they relate to the Safety NET spreadsheets. --The results indicate that between 90 to 100% of the Move In EDI Transactions have been received and a response sent. --TDSPs agreed that sunsetting the daily Safety NET process is a viable option. --The CRs agreed sunsetting might be a possible option. --Another suggested option was to have the CRs resend the EDI transactions. --The CRs stated that some of the CR systems will not allow their agents to resend another enrollment for the same customer. | The CRs will review transaction timing internally over the next couple of months in order to provide feedback and recommendations to Texas SET. Texas SET will revisit any changes needed in the Retail Market Guide (RMG) once the feedback is received.
Discussion Items
NRG 814_28 Question and Answer discussion--TDSP feedback from examples received | NRG was not able to provide examples to the TDSPs for this issue. | Texas SET will revisit the issue when examples are available for review.
Issues
2016-I141, Allow for cancel and date change requests to be processed at ERCOT and TDUs within the 1day window time frame without being rejected. NPRR778, Modifications to Date Change and Cancellation Evaluation Window 139RMGRR, Update Retail Market Guide to align with NPRR778 | • ERCOT noted and Texas SET made changes to related language in Section 11, Solution to Stacking of the Retail Market Guide (RMG). • ERCOT provided an update for the NPRR778 Impact Analysis and stated that the estimated cost is $50K to $75K with estimated project duration of 3 to 6 months. | The Texas SET Chair will submit Texas SET comments to update language changes in Section 11.2.1.2, ERCOT Operating Rule 2 for Rejection Cancel Date Change under RMGRR139.
2016-I143, Validation Processes When a Character is Included in the Customer Name on a Switch or MVI Transaction. Review Nodal Protocol Section19.5.1 Alphanumeric Field(s)--Continue Discussions Based on Attendee Feedback | ERCOT stated that NP Section 15.5.1 Alphanumeric Field(s) displays a level of detail that is normally contained only in the Texas SET Implementation Guides. The same language is contained under the Transaction SET notes of the Introduction page in each Texas SET Implementation Guide . ERCOT requested and received consensus from Texas SET to remove NP Section 15.5.1 Alphanumeric Field (s) from the Protocols. ERCOT will create an NPRR to make this change. | • ERCOT to create an NPRR to remove language from Nodal Protocols 19.5.1. • ERCOT to provide options which may include potential ERCOT system changes or changes to the Texas SET Guides at the July or August Texas SET meeting.
Retail Market Guide Section 9 Appendix D3: TDSP’s Discretionary Service Timelines Matrix -- Correction to remove the word "Draft" from the header box on the Excel Spreadsheet. | TXU stated that Appendix D3: TDSP’s Discretionary Service Timelines Matrix Excel Spreadsheet was posted with the word "Draft" in the header. Texas SET agreed that Texas SET needs to contact ERCOT for direction to have this corrected. | Per ERCOT Market Rules the Texas SET Chair will submit an RMGRR to correct the Appendix.
ERCOT Market Continuity Workshop--Possible RMS Leadership Assignment to Texas SET | The RMS Chair stated that there were Retail Market related issues identified during the ERCOT sponsored (WMS) Continuity Workshop on June 8th. (See slide 10 on the attached presentation).The RMS Chair stated that RMS may be assigning Texas SET with the task to review and provided process solutions for specific retail related areas.
RMS assignments:
New Entrant Documentation—Procedures and Documentation Location | Texas SET continued to develop the New Entrant document by identifying areas in which New TDSPs, CRs and MOU/EC s need to develop their knowledge base. ERCOT suggested that Texas SET review and update the Opt-In Checklist document for the TDSPs. ERCOT noted that the TDSP tab in the Texas SET Market Test Script pack needs to be reviewed and scripts developed. | The Texas SET Chair will send the updated New Entrant document to the Texas SET email distribution list and notify members that the TDSP script pack will be reviewed at a future Texas SET meeting.
Add Mass Customer List (MCL) guide back to the Texas SET Guides | No updates made.
Parking Lot
Texas SET Release Discussion | On Hold
REP Certification Matrix—Long-term solution | On Hold
Next Meeting--ERCOT MET Center | July 20th ERCOT MET Center RM 168 10 AM
July 21st Meeting date cancelled
Attendees
Diana Rehfeldt TNMP | Paul Yockey ERCOT | Kathryn Thurman ERCOT
Michael Glass Sharyland Utilities | Kaci Jacobs TXU | Bill Reily ONCOR
Kyle Patrick NRG | Jim Lee AEP | Becky Taylor CNP
Monsherra Odanga ONCOR | Sam PAK ONCOR | Carolyn Reed CNP
Kathy Scott CNP
Webex
Jasmine Thom CES | Barbara Goubeaud EC InfoSystems | Catherine Meiners ERCOT
Dave Michelsen ERCOT | Dan Bisutti ESG | Deborah Croce EC InfoSystems
Lindsay Butterfield ERCOT | Teresa Rodriquez Stream Energy | Doug Sumerville Zoom Energy
Kelly Tidwell Direct Energy | Taylor Woodruff ONCRO