## Slide 1: SMT Update To AMWG
August 23, 2016

## Slide 2: SMT Standard Monthly Maintenance Schedule

## Slide 3: SMT Monthly Maintenance Schedule
Monthly maintenance to be conducted the third weekend of every month
As needed additional maintenance to be conducted the first weekend of every month.
Maintenance weekends will commence activities starting on Saturdays beginning at 12:01 A.M.

## Slide 4: Update on SMT Upcoming Events Maintenance, Releases and Disaster Recovery Exercise

## Slide 5: SMT Planned Events 2016
August 6, 2016 – Planned maintenance outage on first weekend – COMPLETED SUCCESSFULLY
September 17, 2016 – Planned maintenance outage, minor release, and DR pre-test activities on third weekend
October 8 through October 15, 2016 – Annual disaster recovery exercise
  12 Hour outage Saturday October 8, 8:00 AM to 8:00 PM to flip to DR site
  12 Hour outage Saturday October 15, 8:00 AM to 8:00 PM to flip back to Production site
November 19, 2016 – Planned maintenance outage on third weekend
December 17, 2016 – Planned maintenance outage and minor release on third weekend
Market Notices will be sent out for all events at 30 days, 10 days, 3 days, 1 day and upon successful completion
*** Additional maintenance days may be added due to current unknown issuance of critical software patches or situations requiring security updates

## Slide 6: SMT September 17, 2016 Minor Release to Correct Deficiencies and Usability Defects

## Slide 7: September 17, 2016 SMT Minor Release to Correct Deficiencies and Usability Defects
Planned Release for September 17 2016 SMT to include the following:
Provide month to month variances for each item on the SMT Third Party statistics report
  Currently the SMT Third Party statistics report does not provide month to month variances
  SMT will add in parenthesis for each statistic the change from the previous month
Correct the tab key to navigate a user from the User ID field to the Password field on the SMT login page
  Currently clicking the tab key navigates a user from the User ID field to the Forgot User ID link
  SMT will correct the tab key to navigate a user from the User ID field to the Password field

## Slide 8: September 17, 2016 SMT Minor Release to Correct Deficiencies and Usability Defects
Planned Release for September 17 2016 SMT to include the following:
Improve the SMT website portal On Demand Read description for users
  Currently when a user clicks the On Demand Read button on SMT the message displayed is “Please wait. Your on demand request is being processed. Please wait a few moments then click here to refresh your screen”
  TDSPs process differently the data provided by an On Demand Read. Some TDSPs go straight to the meter and get a new read. Some TDSPs go to a data store where more current data is collected several times a day and stored.
  SMT will identify the users TDSP territory and after the user clicks the On Demand Read button will provide more descriptive information of the data that will be returned.

## Slide 9: September 17, 2016 SMT Minor Release to Correct Deficiencies and Usability Defects
The Release is planned for implementation on September 17, 2016 and will require an outage of the portal website, HAN and ODR from Saturday September 17, 2016 12:01 A.M. CST until Saturday September 17, 2016 11:59 A.M. CST
LSE file delivery and the FTPS folders will not be affected.
Market Notices will be sent out - 30 day (8//17/16), 10 day (9/7/16), 3 day (9/14/16), 1 day (9/16/6), and Final Complete (9/18/16)

## Slide 10: SMT Drop Down for Rejecting Third Party Agreements

## Slide 12: SMT One Time Help Desk Tickets Inquiry

## Slide 13: Level 1 Help Desk – Third Party Tickets September 1, 2015 – June 30th, 2016

## Slide 14: SMT Third Party Review Current Functionality to Support Green Button Connect PowerPoint Navigation Tool

## Slide 15: Status Update of AMWG Change Requests As of February 15, 2016

## Slide 16: Status of AMWG Change Requests
Delivered | Approved Awaiting Project Packaging | Approved Awaiting Project Packaging | AMWG Reporting Options Under Review | RMS Approved Awaiting Categorization | JDOA Estimated Awaiting AMWG Review | Tabled RMS | AMWG Delayed | RMS Remanded back to AMWG | Pushed Back as Defect
2013 002 | 2015 021 | 2013 015 | 2013 001 |  |  | 2014 018 | 2015 029 |  | 2015 022
2013 005 | 2015 042 | 2015 019 | 2013 003 |  |  |  | 2015 030 |  | 
2013 006 | 2015 033 | 2015 020 | 2013 004 |  |  |  | 2015 031 |  | 
2013 007 |  | 2015 023 | 2013 008 |  |  |  | 2015 032 |  | 
2013 009 |  | 2015 025 | 2013 010 |  |  |  | 2015 034 |  | 
2013 012 |  | 2015 026 | 2013 011 |  |  |  | 2015 038 |  | 
2013 013 |  | 2015 027 |  |  |  |  | 2015 040 |  | 
2013 016 |  | 2015 028 |  |  |  |  | 2015 041 |  | 
2013 017 |  | 2015 035 |  |  |  |  |  |  | 
2015 024 |  | 2015 036 |  |  |  |  |  |  | 
2013 014 |  | 2015 037 |  |  |  |  |  |  | 
 |  | 2015 039 |  |  |  |  |  |  | 
Total 10 | See column 3 | Total 15 | Total 6 | Total 1 | Total 0 | Total 1 | Total 8 | Total 0 | Total 1

## Slide 17
AMWG Change Request | AMWG CR Document | Status | Categorization and Estimated Delivery Date | Estimated Cost
AMWG CR 2013 001 – Report for AMWG Data Monitoring – Data Completeness Measurements |  | Estimate Complete & RMS Approved 3/3/15 | Reporting Options Under Review | Small (20-40)
AMWG CR 2013 002 – Reports for AMWG Data Monitoring – Data Timeliness Measurements |  | Implemented | Q2 2014 Delivered | Included in Maintenance Contract
AMWG CR 2013 003 – Reports for AMWG Data Monitoring – Measurement of Percentage of Actual Meter Reads |  | Estimate Complete & RMS Approved 3/3/15 | Reporting Options Under Review | Small (20-40)
AMWG CR 2013 004 – Reports for AMWG Data Monitoring – Measurement of Estimates |  | Estimate Complete & RMS Approved 3/3/15 | Reporting Options Under Review | Medium (40-60)
AMWG CR 2013 005 – Reports for AMWG Data Monitoring – Number of SMT Help Desk Tickets Monthly by Ticket Type |  | Implemented | Q2 2014 Delivered | Included in Maintenance Contract
AMWG CR 2013 006 – Reports for AMWG Data Monitoring – Availability of SMT API |  | Implemented | Q2 2014 Delivered | Included in Maintenance Contract
AMWG CR 2013 007 – Reports for AMWG Data Monitoring – Availability of SMT FTPS |  | Implemented | Q2 2014 Delivered | Included in Maintenance Contract
AMWG CR 2013 008 – Reports for AMWG Data Monitoring – Average Time to Deliver HAN Messages |  | Estimate Complete & RMS Approved 3/3/15 | Reporting Options Under Review | Small (20-40)
AMWG CR 2013 009 – Reports for AMWG Data Monitoring – Number of Accounts by Type |  | Implemented | Q2 2014 Delivered | Included in Maintenance Contract
AMWG CR 2013 010 – Reports for AMWG Data Monitoring – Number of Reports Requested by GUI (Portal) and Number of FTPS Accesses |  | Estimate Complete & RMS Approved 5/6/15 | Reporting Options Under Review | Medium (40-60)
AMWG Change Requests

## Slide 18
AMWG Change Request | AMWG CR Document | Status | Categorization and Estimated Delivery Date | Estimated Cost
AMWG CR 2013 011 – Average Time from HAN Provision Request to Meter Ready Status |  | Estimate Complete & RMS Approved 3/3/15 | Reporting Options Under Review | Small (20-40)
AMWG CR 2013 012 – Bypass redundant screen for Users with only one meter when accessing HAN device information |  | Implemented | Q4 2014 Delivered | Included in Third-Party
AMWG CR 2013 013 – Timeout on SMT takes user to “incorrect login” screen |  | Implemented | Q4 2014 Delivered | Included in Third-Party
AMWG CR 2013 014 – Allow SMT user to toggle between 15-Minute Reads and Daily Reads without having to reset the date range |  | Implemented | February 2016 Delivered | Included in Usability
AMWG CR 2013 015 – Expand Daily Usage Graph to show 35 days of daily usage on the SMT GUI |  | Estimate Complete & RMS Approved 3/3/15 | 2 Important Awaiting Packaging | Medium (40-60)
AMWG CR 2013 016 – Capability for RORs to grant access to vendors on their behalf to the ROR’s customers via API (energy usage, HAN messaging , and HAN provisioning) and FTPS files |  | Implemented | Q3 2014 Delivered | Included in Maintenance Contract
AMWG CR 2013 017 – REP API for Energy Usage on SMT (Backfill of Historical Usage Data for Existing Customers- “Interim” Older infrastructure prior to May 2015 unable to meet required CR 017 volume ) | See Below CR 2013 017 FINAL | Implemented with performance less than requested in CR | Q4 2013 Delivered | Included in SMT Maintenance Contract
AMWG CR 2013 017 – REP API for Energy Usage on SMT (Subscription for New Customer Historical Usage – “Interim” Older infrastructure prior to May 2015 unable to meet required CR 017 volume ) | See Below CR 2013 017 FINAL | Implemented with performance less than requested in CR | Q2 2014 Delivered | Included in Maintenance Contract
AMWG CR 2013 017 – REP API for Energy Usage on SMT – FINAL - On May 2015 the new SMT infrastructure was implemented which enabled SMT to support the required CR 017 volumes) |  | New SMT infrastructure meets performance requirements in the CR | Q2 2015 Delivered | Delivered 2015
AMWG CR 2014 018 – Add Generation Data to the SMT Portal View |  | JDOA Estimate Completed | RMS Tabled 6/2/15 RMS Tabled 8/4/15 | Medium (40-60) Graph and Table Small (20-40) Table Only
AMWG Change Requests (Cont.)

## Slide 19
AMWG Change Request | AMWG CR Document | Status | Categorization and Estimated Delivery Date | Estimated Cost
AMWG CR 2015 019 – Relocate Various SMT User Guides from the Authenticated Site to the Unauthenticated Site |  | JDOA Estimate Completed | 2 Important Awaiting Packaging | Small (20-40)
AMWG CR 2015 020 – Add Customer Type in the Customer Information Section in the View / Edit Agreement Page |  | JDOA Estimate Completed | 3 Nice to Have Awaiting Packaging | Medium (40-60)
AMWG CR 2015 021 – Improve REP of Record Search Criteria During the Customer Registration Process |  | Estimate Complete & RMS Approved 5/6/15 | 1 Critical Awaiting Packaging | Medium,(40-60)
AMWG CR 2015 022 – Keep Selected ROR Visible During Customer Registration |  | JDOA Estimate Completed | Push Back as Defect | Small (20-40)
AMWG CR 2015 023 – Allow Entry of Multiple ESIIDs During Customer Registration Process |  | JDOA Estimate Completed | 3 Nice to Have Awaiting Packaging | High (60-120)
AMWG CR 2015 024 – Third Party Access Renew Energy Data Agreement After One Year |  | JDOA Estimate Completed | Q4 2015 Delivered | 0 Dollar
AMWG CR 2015 025 – Third Party User Experience Add Identifying Data Fields in the Report Request Status Page |  | JDOA Estimate Completed | 2 Important Awaiting Packaging | High (60-120)
AMWG CR 2015 026 – SMT Functionality Display Portal Message when Report Can Not be Displayed in the SMT Portal Page |  | JDOA Estimate Completed | 2 Important Awaiting Packaging | Minor (0-20)
AMWG CR 2015 027 – SMT Functionality Allow Specific Date Entry on the Export Report Screen |  | JDOA Estimate Completed | 3 Nice to Have Awaiting Packaging | Small (20-40)
AMWG CR 2015 028 – SMT Functionality Allow ESIIDs to be Copied and Pasted into the ESIID Box on the Usage Page |  | JDOA Estimate Completed | 3 Nice to Have Awaiting Packaging | Minor (0-20)
AMWG CR 2015 029 – This Party Allow Third Parties to Utilize an API for On Demand Data Requests |  | Estimate Complete & RMS Approved | AMWG Delayed | High (60-120)
AMWG Change Requests (Cont.)

## Slide 20
AMWG Change Request | AMWG CR Document | Status | Categorization and Estimated Delivery Date | Estimated Cost
AMWG CR 2015 030 – Support multiple RORs during CSV file meter upload |  | JDOA Estimate Completed | AMWG Delayed | High (60-120)
AMWG CR 2015 031 – Allow only current ROR for account registration validation and meter add validation |  | JDOA Estimate Completed | AMWG Delayed | High (60-120)
AMWG CR 2015 032 – Support SFTP protocol for SMT integration |  | Investigation Complete | AMWG Delayed | High (60-120)
AMWG CR 2015 033 – Provide user id and password rules up front on UI registration page |  | JDOA Estimate Completed | 2 Important Awaiting Packaging | Minor (0-20)
AMWG CR 2015 034 – Display the day of the week in addition to the date on usage reports |  | JDOA Estimate Completed | AMWG Delayed | Medium (40-60)
AMWG CR 2015 035 - Provide a customer-selected option to receive a monthly usage report via email |  | Estimate Complete & RMS Approved | 2 Important Awaiting Packaging | Medium (40-60)
AMWG CR 2015 036 – Rename Overview tab to Home |  | Estimate Complete & RMS Approved | 2 Important Awaiting Packaging | Minor (0-20)
AMWG CR 2015 037 – Remove SMT Demo from Private Site for REPs, TDSPs, and Third Parties |  | Estimate Complete & RMS Approved | 2 Important Awaiting Packaging | Minor (0-20)
AMWG CR 2015 038 – Provide a “Hold” capability on Third Party accounts to reactivate usage until the Third Party has integrated with FTPS and API |  | JDOA Estimate Completed | AMWG Delayed | High (60-120)
AMWG CR 2015 039 – Provide more detail for Third Party Agreement Invitation Error Messages |  | Estimate Complete & RMS Approved | 2 Important Awaiting Packaging | Medium (40-60)
AMWG CR 2015 040 – Improve SMT Administration Functionality for TDSPs, RORs, Third Parties, and Businesses |  | JDOA Estimate Completed | AMWG Delayed | 5 Functions Small, Small, Zero, Medium, High
AMWG Change Requests (Cont.)

## Slide 21
AMWG Change Request | AMWG CR Document | Status | Categorization and Estimated Delivery Date | Estimated Cost
AMWG CR 2015 041 – Allow Enrollment for New Customer 12 Month History for Third Parties |  | RMS Remanded back to AMWG for Further Discussion | AMWG Delayed | Medium (40-60)
AMWG CR 2015 042 – Automate Machine to Machine Consumption of Third Party Agreement Information |  | RMS Approved 8/4/15 | 2 Important Awaiting Packaging | Med / High (80)
AMWG Change Requests (Cont.)

## Slide 22: Rough Order Of Magnitude (ROM) Estimate of Effort Classification
These are rough order of magnitudes and do not include project ramp-up and testing effort (SIT & UAT) and only assumes unit testing.
Actual estimates could vary significantly depending on requirements.
Ramp-up and testing would be 20 to 40% of the overall effort
Overall project cost will vary based on efficiency gains from packaging like functionality
Change Type | ROM
MINOR | 0 – 20 K
SMALL | 20 – 40 K
MEDUIM | 40 – 60 K
HIGH | 60 – 120 K
VERY HIGH | Over 120 K

## Slide 23: Q&A Monthly SMT Reports to AMWG Data Through July 2016