## Sheet1
TX SET Meeting Notes / Action Items
July 20th 2016
Agenda Item: | Decision / Resolution | Action Items :
June 2016 Meeting Notes | No changes were made to the notes. | The Chair to have the notes posted to the June 2016 meeting page key documents.
Mass Transition/Default-POLR Rule | • RMS assignment to discuss Mass Transition— Possible POLR Rule change from two days out to one day out.
AMWG Update
Other discussion
Market Test Flight 0214 Update | ERCOT to provide flight update No update received
TX SET Procedures | On Hold-Discuss reline changes sent to the TXSET listserv for review | Leave current issue process in tact and continue to review document to identify where additional process improvements can be made
RMS Updates--No July Meeting
Flight Update | ERCOT presented the test flight statistics.
Review SOR01 and SOR02 scripts to determine which test day the 814_20s will be sent | Texas SET members reveiwed and made changes to the scripts to as needed. | ERCOT will update the scripts and send to the Chair for distribution to the Texas SET membership.
Discussion Items
Retail Market Guide Section 9 Appendix D3: TDSP’s Discretionary Service Timelines Matrix -- Correction to remove the word "Draft" from the header box on the Excel Spreadsheet. Review Revision Request and make recommendation to RMS. | ERCOT Market Rules determined that the change was an administrative change and would not need the RMGRR.
RMGRR140, Efficiencies for Acquisition Transfer Process, Impact Analysis | Texas SET members reached consensus to request RMS approve this RMGRR. The RMGRR had a low cost impact that will be absorbed by the O & M budgets. | The Chair will request that RMS approve the Impact Analysis.
RMGRR141, Clarifying Procedures for Market Particpants During an Extended Unplanned System Outage, Impact Analysis | Texas SET members reached consensus to request RMS approve this RMGRR. The RMGRR had no impacts to ERCOT. | The Chair will request that RMS approve the Impact Analysis.
Issues
2016-I141, Allow for cancel and date change requests to be processed at ERCOT and TDUs within the 1day window time frame without being rejected. NPRR778, Modifications to Date Change and Cancellation Evaluation Window--Review Impact Analysis and make recommendation to RMS | • Texas SET reviewed the Impact Analysis with T. Anderson from ERCOT to determine a rank and priority to recommend to RMS. Consensus was reached to request that RMS endorse the NPRR and approve RMGRR139. | The Chair will request that RMS endorse the Impact Analysis for NPRR778 with a rank of 1700 and priority of 2016. The Chair will request that RMS approve RMGRR139.
2016-I143, Validation Processes When a Character is Included in the Customer Name on a Switch or MVI Transaction--ERCOT update on NPRR language to remove Nodal Protocol Section19.5.1 Alphanumeric Field(s) and options for potential Texas SET Implementation Guide changes | ERCOT presented options for potential changes needed for the Texas SET Implementation Guides. ERCOT sent the presentation to the Texas SET email distribution list. | Texas SET membership will review the proposed options and return feedback at the August 17th Texas SET meeting.
RMS assignments:
Potential Assignment from ERCOT Market Continuity Workshop | The RMS Chair stated that an assignment is likely to come from the August 2nd RMS meeting to review the Retail Transaction processing issues related to a system outage as discussed in the ERCOT Market Continuity Workshop.
New Entrant Documentation—Procedures and Documentation Location | Texas SET membership reviewed ERCOT questions and changes made to the Opt In Checklist. | The document will be distributed to the Texas SET membership and further discussion will take place at the August 17th and 18th meeting.
RMGRR132, NOIE Disconnect and Reconnect Process and NPRR772, Clarification of Process for Transmission Outages Related to a Service Disconnection Request for a Generation Resource Comparisons | The RMS Chair stated that an assignment is likely for Texas SET to review the tabled RMGRR132 to compare the language to that of NPRR772 to determine if changes are needed to align the RMGRR with the NPRR.
Add Mass Customer List (MCL) guide back to the Texas SET Guides | No Action taken.
Parking Lot
RMG Safety NET Timelines
Notes: PUCT to Review Final Draft Prior to Texas SET Submitting Changes to RMS | No discussion held.
2016 -804 Sharyland request for a new SAC04 code with a description of “Deferred Cost Recovery Charge” and identified as “MSC056”. | The RMS Chair, ERCOT, and Texas SET membership determined how to complete the black-line changes by October 1, 2016. RMS will vote on the Change Control at the August 2nd meeting. Texas SET will review and possibly reach consensus on the Redlines to the Texas SET Implementation Guide at the August 17th meeting. RMS will have an email vote since the September meeting will be cancelled. (email to go out on September 12th with results due back by close-of-business September 16th). Texas SET to review the response from RMS at the September meeting. If all is approved, the change will become effective on October 3, 2016.
Texas SET Release Discussion | On Hold
REP Certification Matrix—Long-term solution | On Hold
Next Meeting--ERCOT MET Center | August 17th ERCOT MET Center RM 102 10 AM
August 18th ERCOT MET Center RM 102 9:30 AM
Attendees
Diana Rehfeldt TNMP | Kathryn Thurman ERCOT | Paul Yockey ERCOT
Sarah Heselmeyer ERCOT | Kyle Patrick NRG | Kaci Jacobs TXU
Jim Lee AEP | Lindsay Butterfield ERCOT | Carolyn Reed CNP
Kathy Scott CNP | Sam Pak ONCOR
Webex
Teresa Rodriquez Stream Energy | Mike Woolsey ONCOR | Dave Michelsen ERCOT
Monsherra Ondanga, ONCOR | Kelly Brink ERCOT