## New AV Schedule_20160629
| Date | Residential Annual Validation Task List | Status
| 3/30/20XX | ERCOT to provide list of ESI IDs to TDSPs
| 4/10/20XX | TDSPs to provide finalized list of ESI IDs to ERCOT
| 4/15/20XX | Market Notice announcing lists are available to CR of record
| 4/15/20XX | TDSPs to begin submitting 814_20 transactions
| 9/30/20XX | TDSPs to complete submissions of 814_20 transactions
| 10/2/20XX | ERCOT completes review of expected database changes
| Date | Business Annual Validation Task List | Status
| 3/30/20XX | ERCOT Provides Qtr Validation Lists to TDSPs (BUS Only)
| 3/30/20XX | ERCOT to provide list of ESI IDs to TDSPs
| 4/10/20XX | TDSPs to provide finalized list of ESI IDs to ERCOT
| 4/15/20XX | Market Notice announcing lists are available to CR of record
| 4/15/20XX | TDSPs to begin submitting 814_20 transactions
| 9/30/20XX | TDSPs to complete submissions of 814_20 transactions
| 10/2/20XX | ERCOT to review database for expected changes
| 10/5/20XX | TDSPs have submitted at least 99% of changes
| 11/2/20XX | Initial Weather Responsiveness Report Produced
| 1/2/20XX | Weather Responsiveness Overdue Report Produced
| Monthly | Continue Overdue Reporting Until All Complete
Update: 06/29/2016
Zip Code reconciliation efforts to be included in AV pursuant to LPG 11.3, Additional Validations (Zip Code reconciliation efforts under
11.3.5,Validation of Service Address Zone Improvement Plan Code)