## Sheet1
TX SET Meeting Notes / Action Items
August 17th and 18th 2016
Agenda Item: | Decision / Resolution | Action Items :
July 2016 Meeting Notes | Administrative changes were made to the July notes. | The Texas SET Chair will have the final version posted to the July meeting page.
Mass Transition/Default-POLR Rule | • RMS assignment to discuss Mass Transition— Possible POLR Rule change from two days out to one day out.
AMWG Update
Other discussion
Market Test Flight 0214 Update | ERCOT to provide flight update No update received
TX SET Procedures | On Hold-Discuss reline changes sent to the TXSET listserv for review | Leave current issue process in tact and continue to review document to identify where additional process improvements can be made
RMS Updates
NPRR771, Clarifications to New ESI ID Creation Process--TAC approved | If the ERCOT Board approves this NPRR will become effective 9/1/2016. Update only
o NPRR778, Modifications to Date Change and Cancellation Evaluation Window—RMS voted to endorse with a rank of 1700 and priority of 2016. o RMGRR139, Alignment with NPRR778, Modifications to Date Change and Cancellation Evaluation Window—RMS voted to approve with TX SET comments. | Update only
o RMGRR140, Efficiencies for Acquisition Transfer Process—RMS voted to approve. o RMGRR141, Clarifying Procedures for Market Participants During an Extended Unplanned System Outage—RMS voted to approve. o Texas SET Change Control 804: Add a new SAC04 code of “MSC056” for Deferred Cost Recovery Charge—RMS voted to approve. | Update only
Flight Update | ERCOT Staff presented the flight statistics for the 0616 and 1016 test flights.
Review 2017 Flight Schedule | ERCOT Staff presented the proposed 2017 Flight Schedule and requested a consensus for the dates. ERCOT requested that TX SET review the proposal to remove the Blackout Period and provide feedback on this change. Texas SET attendees will review the schedule and provide consensus at an additional Texas SET WebEx only meeting to be held on August 26 at 9 AM. | The TX SET Chair will set up a WebEx only meeting for August 26 at 9 AM
August 26th WebEx Meeting Discussion | Texas SET reached consensus on the Flight Schedule dates and the removal of the blackout period language from the schedule. The ERCOT Flight Administrator clarified that the removal of the blackout period language did not extend the Adhoc period dates. Those will remain as listed in the Schedule. | The Texas SET Chair will update the document and send it to ERCOT to have posted for a vote at the RMS September 13, 2016 meeting.
Review SOR01 and SOR02 scripts to determine which test day the 814_20s will be sent | ERCOT Staff reviewed the changes to the script pack and received consensus from the Texas SET membership. | The ERCOT Flight Administrator will posted the updated script pack to the Testing website.
Discussion Items
MDWG and ERCOT Discussion—Re-architect and Update ERCOT’s External Web Services (EWS) | ERCOT Staff and the Market Data Working Group (MDWG) Chair presented information related to changes being proposed to ERCOT's External Web Services. | The Texas SET Chair will have the presentation posted to the August 17th meeting page and send the same to the Texas SET distribution email list.
814_04 / 05 Transactions--Scheduled Dates-TXU | TXU requested that the TDSPs review and investigate the reasons why a Scheduled meter read in the 814_05 would not be the same as the Completed Date in the 867_04. The TDSPs requested that specific examples be sent to them to research. | TXU to send examples to the TDSPs.
Texas SET Change Control 804: Add a new SAC04 code of “MSC056” for Deferred Cost Recovery Charge—Review Implementation Guide Redlines and reach consensus. | Texas SET reviewed the redlines to the Texas SET 810 Implementation Guide and reached consensus to request RMS to approve the redlines. | ERCOT will present the Implementation Guide redlines to RMS and request a vote to approve.
Issues
2016-I143, Validation Processes When a Character is Included in the Customer Name on a Switch or MVI Transaction--Review ERCOT Options 1 Continue With Existing Manual Workaround 2 Update ERCOT’s Systems to Reject Any Transaction Containing Special Language Characters 3 Update ERCOT’s Systems to Translate Special Language Characters into Normal Characters 4 Implement Option 3 in the Short Term, Followed by Option 2 During the Next TX SET Release | Texas SET membership reviewed the options presented by ERCOT and made recommendations for going forward. 1. It was noted that one Competitive Retailer's inappropriate use of the Special Language Characters could cause another Competitive Retailer's transactions to be delayed at the TDSP if they are received in the same file from ERCOT. 2. NRG stated that they made changes to their system to correct the issue. 3. TXU stated that they are in the process of making similar changes as NRG. 4. Texas SET membership determine that a combination of Option 1 and Option 2 will be better in the short and long term. 5. Texas SET determined that the Texas SET leadership should reach out to the market to get feedback from the other Competitive Retailers before moving forward. | The Texas SET Chair will send an email to the Texas SET email distribution list to request greater feedback at the September 21st meeting regarding the recommendation that Option 1 (short term) & 2 (long term) be recommended.
RMS assignments:
New Entrant Documentation—Procedures and Documentation Location | No discussion held this month.
RMGRR132, NOIE Disconnect and Reconnect Process and NPRR772, Clarification of Process for Transmission Outages Related to a Service Disconnection Request for a Generation Resource--review language in both | Texas SET, ONCOR and Golden Spread Electric Cooperative reviewed the NPRR and drafted comments to be submitted to have RMS review at their September 13th meeting. It was subsequently determined that the Texas SET comments were the same as the ROS August 4, 2016 comments and that the Chair will ask RMS to endorse the ROS 8/4/2016 comments. | The Texas SET Chair to recommend that RMS endorse ROS August 4, 2016 Commnets
ERCOT Market Continuity Workshop- Retail o Manual workarounds, how would those need to be adjusted? o Other Considerations | Texas SET hosted a discussion session during the 2nd day of their meeting for RMS, TX SET, TDTMS and AMWG memebership. The notes from this session will be posted in two separate documents. | The Texas Set Chair will have the notes posted to the August 18th meeting page key documents.
Add Mass Customer List (MCL) guide back to the Texas SET Guides | No discussion held this month.
Parking Lot
RMG Safety NET Timelines
Notes: PUCT to Review Final Draft Prior to Texas SET Submitting Changes to RMS | NRG noted that they are still reviewing the Safety NET process internally.
Texas SET Release Discussion | On Hold
REP Certification Matrix—Long-term solution | On Hold
Next Meeting--ERCOT MET Center | September 21st ERCOT MET Center RM 168 10 AM
September 22nd ERCOT MET Center RM 102 9:30 AM
Attendees -- Day 1
Diana Rehfeldt TNMP | Taylor Woodruff ONCOR | Becky Taylor CNP
Paul Yockey ERCOT | Sarah Heselmeyer ERCOT | Kathryn Thurman ERCOT
Kaci Jacobs TXU | Jeff Chen CNP | Jim Lee AEP
Tom Burke GSEC | Carolyn Reed CNP | Kyle Patrick NRG
Kathy Scott CNP | Sam Pak ONCOR | Monsherra Odanga, ONCOR
Webex -- Day 1
Barbara Goubeaud ECInfoSystems | Brian Brandov ERCOT | Eric Blakey Just Energy
jasmine Thom (CES) | Jenny Evanson Sharyland | Julie Thomas Luminant
Linday Butterfield ERCOT | Rebecca Zerwas NRG | Sheryl (APG&E)
WebEx -- August 26, 2016 Call
Diana Rehfeldt TNMP | Jasmine Thom CES | Carolyn Reed CNP
Becky Taylor CNP | Paul Yockey ERCOT | Jim Lee AEP
Monsherra Odanga ONCOR | Kathryn Thurman ERCOT | Dan Bisutti ESG
Kathy Scott CNP | Michael Glass Sharyland | Kyle Patrick NRG
Sam Pak ONCOR | Mike Woolsey ONCOR | Deborah Croce EC InfoSystems