## Slide 1
NERC Readiness Spotlight
Yvette Landin
NERC Standards and Compliance

## Slide 2: NERC Readiness Risk Spotlight
None
None
All Readiness Activities on Track

## Slide 3: Legend
The bulleted items in the slides represent various readiness activities or key pieces of information around readiness.
Action: Something needs to happen and is typically in red font to bring attention to the item.
Complete: Represents a completed Action or resolved issue.
Information: Represents information associated with the Standard, requirement, such as an Owner, enforcement date, etc.

## Slide 4: October 1, 2016 Enforcement

## Slide 5: MOD-031-2: Demand and Energy Data
Effective Date & Applicability
  10/1/16 R3
  PC, TP, BA, RP, LSE, DP
Significant Changes
  None were significant, only minor
Initiatives
  To Clarify internal documents used per change in R3
Estimated Cost
  None
Risks
  Changes require modification in ERCOT’s processes.
    Upcoming Readiness Milestones
  Final Review: 5/31/16

## Slide 6: January 1, 2017 Enforcement

## Slide 7: IRO-010-2: Reliability Coordinator Data Specification and Collection (Related to TOP-003-3)
Enforcement Date (phased) & Applicability
  1/1/17: R1 & R2 (RC)
  4/1/17: R3 (RC, BA, GO, GOP, LSE, TOP, TO, DP)
Significant Changes
  The definition of Operational Planning Analysis and Real-time Assessment is changing to include phase angle limitations.
  The RC shall maintain a documented specification for the data necessary to perform above assessments
  The RC shall distribute its data specification
Initiatives
  Need to collect phase angle limitation information [related to OPA/RTA terms]. Initiate RFI survey 2Q’16 (Solis)
  Need a place in NMMS. Determine impacts after survey complete. 2Q’16 (John, Joe and Jay) – In Progress
  NPRR790, Addition of Phase Angle Limits to the Network Operations Model - In progress
  Draft data specification/mapping document (Thompson, Solis, Frosch/Landin) [R1, R2] (6/23/16)
  Initiate CFR updates for R3 in 2Q ‘16 (Stout) – In Progress
  Initiate procedure/control updates in 4Q’16 (Thompson, Hartmann, Colleen/Yvette)
  Operator training on schedule for cycle 6 (Spinner) – On schedule
Estimated Cost
  See NPRR790
Risks
    None
  Upcoming Readiness Milestones
  Share Mapping Document with OWG 8/18; ROS 9/8; NRWG 9/13

## Slide 8: TOP-003-3 Operational Reliability Data (Related to IRO-010-2)
Enforcement Date & Applicability
  1/1/17: R1-R4 (TOP & BA)
  4/1/17: R5 (TOP, BA, GO, GOP, LSE, TO, DP)
Significant Changes
  This Standard is same as IRO-010-2 expect applicability is for the TOP and BA
  The TOP/BA shall maintain a documented specification for the data necessary to perform above assessments
  The TOP/BA shall distribute its data specification
Initiatives
  See details in IRO-010-2 Slide
Estimated Cost
  See details in IRO-010-2 Slide
Risks
  None
  Upcoming Readiness Milestones
  See details in IRO-010-2 Slide

## Slide 9: April 1, 2017 Enforcement

## Slide 10: EOP-010-1 Geomagnetic Disturbance Operations
Enforcement Date & Applicability
  4/1/17 (R2)
  BA, RC, TOP
Significant Changes
  R2. Each Reliability Coordinator shall disseminate forecasted and current space weather information to functional entities identified as recipients in the Reliability Coordinator's GMD Operating Plan.
Initiatives
  Review desk procedures (Landin/Frosch)
Estimated Cost
  None
Risks
    None
  Upcoming Readiness Milestones

## Slide 11: EOP-011-1 Operations Planning
Enforcement Date & Applicability
  4/1/17
  BA, RC, TOP
Significant Changes
  New Definition: A condition when a Load-Serving Entity or Balancing Authority has exhausted all other resource options and can no longer meet its expected Load obligations.
  R1, TOP, required to have a RC reviewed Operating Plan
  R3, RC required to review the TOP plan within 30 days
Initiatives
  NOGRR - Template for TOPs to use, much like the Black Start template (Frosch/Landin, Sharma/Solis) – In progress
    Draft sent to TOPs for review.
  New process/procedure for reviewing Op Plans (Sharma, Thompson)
  CFR updates R1, R4, R5 (Stout) – in progress
Estimated Cost
  O&M
Risks
    None
  Upcoming Readiness Milestones
  Follow-up meeting 3/22/16

## Slide 12: Remedial Action Scheme Definition
Enforcement Date
  4/1/17
Significant Changes
  New definition for SPS/RAS
  25 standards use RAS
Initiatives
  Review all SPSs to determine if still a RAS, coordinate with RAS owners (Sharma)
  NPRR792, NOGRR164 and PGRR051 (Sharma, Thompson) – In flight
    MIS changes needed (SPS & RAP report name updates)
    Documentation (Reports, CMP and Operator procedures)
    System changes (distinguish between AMP&RAS and TCM/RTCA display changes)
  Joint Workshop with Texas RE (scheduled 5/9/16)
  Controls (Colleen)
  Monitor revisions to working group manuals (Landin)
Estimated Cost
  TBD
Risks
    None
  Upcoming Readiness Milestones
  Sandip reached out to RAS owners, feedback due 3/7, follow-up meeting 3/28/16
  PRS, OWG, PLWG meetings

## Slide 13: IRO- 001-4 Reliability Coordination - Responsibilities
Enforcement Date & Applicability
  4/1/17
  RC, TOP, BA, GOP, DP
Significant Changes
  Retires the requirement to have a Regional Reliability Plan
Initiatives
  Reliability Plan is required to be approved by the ORS/OC every 3 years, ERCOT’s plan is up for its 3 year review in February 2017. Initiate updates to the Reliability Plan and add to ORS and OC agenda beginning in December. Approvals will take place at February ORS and March OC. (Hartmann, Landin)
  Initiate revision to desk procedures in December (Frosch, Hartmann)
  Initiate CFR updates for R2 and R3 in 2Q’16 (Stout)
  Initiate Alert review after procedures have been approved. (Chad/Yvette)
Estimated Cost
  None
Risks
  None
  Upcoming Readiness Milestones
  Kick-off meeting 2/15/16

## Slide 14: IRO-002-4 Reliability Coordination – Monitoring and Analysis
Enforcement Date & Applicability
  4/1/17
  RC
Significant Changes
  Aside from new definitions that are captured in IRO-010, minor language tweaks to standard language
Initiatives
  Initiate procedure updates in 4Q’16 (Colleen/Hartmann)
  Initiate Control updates after procedure updates are complete (Chad/Yvette)
Estimated Cost
  O&M
Risks
  O&M
  Upcoming Readiness Milestones
  Kick-off meeting 2/15/16

## Slide 15: IRO-008-2 RC Operational Analyses & Real-time Assessments (Related to TOP-002-4)
Enforcement Date & Applicability
  4/1/17
  RC
Significant Changes
  R2, Coordinated Operating Plan for next-day operations to address SOL/IROLs
  R3, Notify impacted entities as to their role in Operating Plan
  R5, Notify impacted TOPs when Real-time assessment results show exceedances. Could the “NSA Active Constraints” posted on the MIS every 5 minutes be used to meet this requirement?
  R6, Notify impacted TOPs when exceedances have been mitigated. Use same MIS posting as above?
Initiatives
  Coordinate Operating Plan (Thompson)
  Controls (Colleen/Yvette)
Estimated Cost
  O&M
Risks
  None
  Upcoming Readiness Milestones
  Kick-off meeting 2/15/16

## Slide 16: TOP-002-4 – Operations Planning (Related to IRO-008-2)
Enforcement Date & Applicability
  4/1/17
  BA, TOP
Significant Changes
  R2 Each TO shall have an Operating Plan for next‐day operations to address potential System Operating Limit (SOL) exceedances identified as a result of its Operational Planning Analysis
  R3 Each TO shall notify entities identified in the Operating Plan(s) cited in Requirement R2 as to their role in those plan
  R4 Each BA shall have an Operating Plan(s) for the next‐day that addresses expected generation resource commitment and dispatch, Interchange scheduling, demand patterns, capacity and energy reserve requirements, including deliverability capability
  R5 Each BA shall notify entities identified in the Operating Plan(s) cited in Requirement R4 as to their role in those plan
  R6 Each TO shall provide its Operating Plan(s) for next‐day operations identified in Requirement R2 to its RC
Initiatives
  Initiate updates to procedures and evidence in 4Q’16
  Initiate CFR updates in 3Q’16 R1, R2, R3, R6 (Stout) – in progress
  Controls (Colleen/Yvette)
Estimated Cost
  O&M
Risks
  None
  Upcoming Readiness Milestones
  Kick-off meeting 2/15/16

## Slide 17: IRO-014-3 Coordination Among Reliability Coordinators
Enforcement Date & Applicability
  4/1/17
  RC
Significant Changes
  Not applicable for ERCOT but want to ensure the RC to RC agreements could complete with this
Initiatives
  RC to RC Agreements
Estimated Cost
  O&M
Risks
    None
  Upcoming Readiness Milestones
  Kick-off in Feb

## Slide 18: IRO-017-1 Outage Coordination
Enforcement Date & Applicability
  4/1/17
  RC, TOP, BA, PC, TP
Significant Changes
  Ensure all standard requirements for the coordination of outages are accounted for in protocols
  R3 - PC and TP shall provide planning assessments to RC
  R4 - PC and TP shall jointly develop solution with RC
Initiatives
  Draft outline document to show compliance with R1 in 2Q’16 (Reed)
  New processes for R3 and R4 (Sandeep)
  Revision of existing procedures (Colleen)
  CFR updates for R2 in 2Q’16 (Stout) – in progress
  Controls (Chad/Yvette)
Estimated Cost
  O&M
Risks
    None
  Upcoming Readiness Milestones
  Kick-off in Feb

## Slide 19: TOP-001-3 Transmission Operations
Enforcement Date & Applicability
  4/1/17
  BA, TOP, GOP, DP
Significant Changes
  No significant changes, operator training needed since they will receive calls for R9
  R9, Each BA and TO shall notify its RC and known impacted interconnected entities of all planned outages, and unplanned outages of 30 minutes or more, for telemetering and control equipment, monitoring and assessment capabilities, and associated communication channels between the affected entities.
Initiatives
  Initiate revision of existing procedures in 4Q’16 (Colleen)
  Add to training cycle
  Initiate CFR changes in 3Q’16 (R1, R5-R10, R12-16, R18-R19) – in progress
  Controls (Chad/Yvette)
Assignees
  Compliance Partner: Barcak
  Business Owner: Hartmann
Estimated Cost
  O&M
Risks
    None
  Upcoming Readiness Milestones
  Kick-off in Feb

## Slide 20: PRC-010-1 Under Voltage Load Shedding
Enforcement Date & Applicability
  4/1/17
  PC, TP
Significant Changes
  New definition: An automatic load shedding program, consisting of distributed relays and controls, used to mitigate undervoltage conditions impacting the Bulk Electric System (BES), leading to voltage instability, voltage collapse, or Cascading. Centrally controlled undervoltage-based load shedding is not included.
  PC or TP responsibilities, will want to make sure this falls on the TP and not ERCOT.
  Consolidated PRC-010, PRC-020, PRC-021, PRC-022, and select EOP-003 requirements into one Standard
Initiatives
  Possible NOGRR, 6.2.6.3.6 to make clear who’s responsibility – DWG to discuss at 8/11 meeting to determine whether responsibilities should be clarified.
Estimated Cost
  O&M
Risks
  None
  Upcoming Readiness Milestones
  Kick-off 3/8

## Slide 21: PRC-010-2 Under Voltage Load Shedding
Enforcement Date & Applicability
  4/2/17
  PC, TP
Significant Changes
  Incorporated PRC-022 R1.5, involving UVLS equipment Misoperations. These were originally to be omitted from PRC010, but a later meeting of SDTs, it was determined to incorporate this aspect as well.
Initiatives
  Not at this time.
Estimated Cost
  O&M
Risks
  None
  Upcoming Readiness Milestones
  Kick-off meeting on 3/8

## Slide 22: July 1, 2017 Enforcement

## Slide 23: MOD-033-1 Steady-State and Dynamic System Model Validation
Enforcement Date & Applicability
  7/1/17
  PC, RC, TOP
Significant Changes
  The Steady State data validation appears to be an existing process, but as a process run every 5 minutes vs every 2 years, we need to ensure what we’re doing satisfies the intent of the Standard.
  The dynamic model data validation process needs to be developed.
Initiatives
  Develop documentation process for Steady State data validation.
  Establish and document dynamic data validation process. This will likely require development of methods and revision of existing procedures
  Initiate CFR updates for R2 (Stout) – in progress
Estimated Cost
  TBD
Risks
    None
  Upcoming Readiness Milestones
    Kick off meeting held on 3/8

## Slide 24: January 1, 2018 Enforcement

## Slide 25: PRC-026-1 Relay Performance During Stable Power Swings
Enforcement Date & Applicability
  R1 – 1/1/18
  R2-R4 – 1/1/20
  PC, GO, TO
Significant Changes
  This is the third phase of a three-phased standard development project that focused on developing this new Reliability Standard to address protective relay operations due to stable power swings.
  R1. Each Planning Coordinator shall, at least once each calendar year, provide notification of each generator, transformer, and transmission line BES Element in its area that meets one or more of the following criteria…
  Initiatives
  [insert]
Estimated Cost
  TBD
Risks
    TBD
  Upcoming Readiness Milestones
  Internal Review
  Kickoff – May

## Slide 26: BAL-002-2 Disturbance Control Standard
Enforcement Date & Applicability
  ?
  BA
Significant Changes
  ERCOT’s Reportable Balancing Contingency Event is 800 MW, frequency/ACE must be returned to its Pre-Reporting ACE value within 15 minutes.
  Initiatives
  [insert]
Assignees
  Compliance Partner: Bezzam
  Business Owner: Sharma, Mango
Estimated Cost
  TBD
Risks
    TBD
  Upcoming Readiness Milestones
  Internal Review
  Kickoff –

## Slide 27: Template
Effective Date
  [insert]
Significant Changes
  [insert]
Initiatives
  [insert]
Assignees
  Compliance Partner:
  Business Owner:
Estimated Cost
  TBD
Risks
    [Insert]
  Upcoming Readiness Milestones
  Kick-off ..