## Sheet1
Goal Description | Deliverables | Schedule | Champion | Contributors | Status
Modify rules where conflicts exist for DR participation in multiple programs and multiple parties | Protocol Revisions and/or Changes to the TR & SOW | End of Year | King | Carter, Raish, Totten | In progress (still part of LRISv2)
Next Steps with Smart Meter Texas | Recommend improvements to SMT for third party access and send to WMS for consideration | End of Year | King | Carter, PDW, Goza, Helton | Final draft of report coming; review next DSWG (PUCT Rulemaking first part of next year)
Continue to assess the way DR, retail rate structures and Energy Efficiency is counted in the CDR. | DSWG should review any proposals | Ongoing | Reed | Jay Z. | In progress
Review potential improvements to the indicative pricing tool to improve accuracy | Recommend changes as needed | Next Release - End of 2nd Quarter | M Smith | Trefny, Patterson | New version released
Complete the effort to allow 3rd party DR providers to participate in SCED | Recommendation for next steps | End of Year | Totten | Carter, King, Lowrey, PDW, Wiegand, ERCOT staff | In progress (still part of LRISv2)
WMS Assignment to address DR deployment impacts on SCED | Use NPRR 626 as a preliminary deliverable with some historical review once implemented | Ongoing | Carter | PDW, ERCOT Staff | In progress; UFR deployments in reliability Adder being addressed
Improve annual report on demand response | Change due date and/or data collection frequency; improve/update category definitions; NPRR | End of 3Qtr for NPRR | ERCOT Staff | Jay Z, Thurnher, Wiegand, Barnes/Sams, Morris | SaaS code updated/run by mid-Dec for 2015; 2016 will be completed by in first quarter of 2017. NPRR expected next year regarding data collection process.
Modify DSWG working group procedures | Revised procedure | 2016-06-01 | Carter | PDW, ERCOT Staff | Need WMS endorsement
Evaluate participation in SCED by 10 min ERS generation resources | Recommendation for next steps; draft NPRR | Draft NPRR by 6/1 | Thurnher | Trefny, Garcia | NPRR777
Complete effort associated with TDSP Outages and effect on ERS performance | NPRR738 | NPRR in flight | Carter | Garcia, Goza, PDW | Approved by Board in August