|  |  |  |  | System Planning |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Monthly Status Report September 2016 |  |  |
|  |  | Report Highlights |  |  |  |  |
|  | - ERCOT is currently reviewing proposed transmission improvements with a total cost of $747 Million. - Transmission Projects endorsed in 2016 total $271 Million. - All projects (in engineering, routing, licensing and construction) total approximately $6.61 Billion as of June 1, 2016. - Transmission Projects energized in 2016 total about $1.26 Billion as of June 1, 2016. |  |  |  |  |  |

Regional Planning Group Project Reviews

- AEPSC and Oncor have jointly submitted the Barrilla Junction Area Improvements project. This is a Tier 1 project that is estimated to cost $111.9 million. ERCOT has completed the independent review and will present this project to the Board of Directors in October 2016 for their endorsement.

- Brazos Electric Cooperative (BEC) has submitted the Salt Creek Area project. This is a Tier 2 project that is estimated to cost $17 million. This project is currently under ERCOT independent review.

- AEPSC has submitted the Maverick County Transmission project. This is a Tier 2 project that is estimated to cost $44.3 million. This project is currently under ERCOT independent review.

- Oncor has submitted the Riverton–Sand Lake 138kV line project. This is a Tier 2 project that is estimated to cost $26 million. This project is currently under ERCOT independent review.

- TNMP has submitted the Line 69H Rebuild and Conversion project. This is a Tier 1 project that is estimated to cost $50.6 million. ERCOT has completed the independent review and will present this project to the Board of Directors in October 2016 for their endorsement.

- AEPSC and Oncor have jointly submitted the Far West Texas project. This is a Tier 1 project that is estimated to cost $423 million. This project is currently in study mode.

- Brazos Electric Cooperative (BEC) has submitted the Northern Johnson County Area Improvement project. This is a Tier 2 project that is estimated to cost $8.1 million. This project is currently under ERCOT independent review.

- LCRA TSC has submitted the Cooks Point substation project. This is a Tier 1 project that is estimated to cost $52 million. This project is currently under ERCOT independent review.

- Oncor has submitted the Littman - Fullerton 138 kV Line project. This project is initially classified as a Tier 3 project and estimated to cost $15 million. This project is submitted for RPG comments.

# Planning Model Activities

The short term calendar of major planning model events is as follows.

- Oct 15, 2016	Post 16SSWG Update 1

The following table shows interconnection projects that met Planning Guide section 6.9(1)(b) – 6.9(1)(d) and were not modeled in SSWG cases due to lack of RARF data in accordance with Planning Guide section 6.9(1)(a) and 6.9(3).  “Insufficient Planning Data” refers to data needed only for the Steady State model and is not the complete set of data marked Required for Planning in the Resource Registration Glossary.

# Other Notable Activities

- ERCOT is currently working on reliability analysis for the 2016 Regional Transmission Plan (RTP). The results and cases for the 2016 RTP preliminary reliability analysis (NERC P0, P1, P2-1, P3, P6-2 and P7) along with the list of preliminary projects were posted on MIS Secure website on June 17th 2016.

- ERCOT continues to work on the 2016 Long Term System Assessment (LTSA). ERCOT has completed generation expansion analysis on the eight scenarios and is now working on the transmission expansion analysis for the ‘Current Trends’ scenario.