## Slide 1: SMT Update To AMWG
November 15, 2016

## Slide 2: SMT Disaster Recovery Exercise October 8 through October 15, 2016

## Slide 3: SMT Disaster Recovery Exercise October 8 through October 15, 2016
SMT successfully completed a 2016 disaster recover exercise
October 8, 2016 - SMT switched from the Production environment to the Disaster Recovery environment
SMT moved from the Production environment to the Disaster Recovery environment on Saturday October 8, 2016 from 00:01 A.M. CST until Saturday October 8, 2016 6:30 A.M. CST which required an outage of all SMT services. This process was scheduled for 10 hours but was completed ahead of schedule within 6.5 hours.
ROR and Third Party FTPS Folders for LSE interval data became available for download utilizing the SMT Disaster Recovery environment earlier on Saturday October 8, 2016 at 01:01 A.M. CST within 1 hour.
October 8 until October 15 – SMT conducted operations on the SMT Disaster Recovery environment
All SMT services were available utilizing SMT Disaster Recovery environment from Saturday October 8, 2016 6:30 A.M. CST until Saturday October 15, 2016 00:00 A.M. CST.

## Slide 4: SMT Disaster Recovery Exercise October 8 through October 15, 2016
Key lessons learned during the disaster recovery exercise
Identified an out of space condition on the Disaster Recovery environment that was experienced on Tuesday October 13, 2016 between 9:00 P.M CST until 11:00 P.M CST. This issue may have caused intermittent login issues for users trying to access the SMT website portal. There was no impact to the FTPS, HAN, APIs or Reporting. There were no help desk tickets reported concerning this issue. This issue was attributed to a human miscalculation of the amount of space required by the Disaster Recovery environment file system due to growth of the database since the previous Disaster Recovery test. This issue was corrected and documented for future use of the Disaster Recovery environment.
October 15, 2016 – SMT switched from the Disaster Recovery environment back to the Production environment
SMT moved from its Disaster Recovery environment back to its Production Recovery environment on Saturday October 15, 2016 from 00:01 A.M. CST until Saturday October 15, 2016 8:55 A.M. CST which required an outage of all SMT services. This process was scheduled for 10 hours but was completed ahead of schedule within 8 hours and 55 minutes.
ROR and Third Party FTPS Folders for LSE interval data became available for download utilizing the SMT Production environment earlier on Saturday October 15, 2015 01:01 A.M. CST within 1 hour.

## Slide 5: Update on SMT Upcoming Events Maintenance and Minor Defect Correction Releases

## Slide 6: SMT Planned Events Q4 2016 and Q1 2017
October 8 through October 15, 2016 – Annual disaster recovery exercise - COMPLETED
November 19, 2016 – Planned maintenance outage on third weekend of the month
December 17, 2016 – Planned maintenance outage and minor release on third weekend of the month
January 21, 2017 – Planned maintenance outage on third weekend of the month
February 18, 2017 - Planned maintenance outage and minor release on third weekend of the month
March 18, 2017 – Planned maintenance outage on third weekend of the month
Market Notices will be sent out for all events at 30 days, 10 days, 3 days, 1 day and upon successful completion
*** Additional maintenance days may be added due to current unknown issuance of critical software patches or situations requiring security updates

## Slide 7: December 17, 2016 Minor Release to Correct Deficiencies and Usability Defects

## Slide 8: December 17, 2016 SMT Minor Release to Correct Deficiencies and Usability Defects
SMT planned release for December 17 2016 will include the following:
Improve the usability experience for SMT website portal users with multiple meters
  Currently one meter is shown on the My Meters page and a user with multiple meters must know to click the bread crumb link at the top of the page titled My Meters to select a different meter. This current usability design causes help desk tickets.
  An improvement will be implemented to provide a new clearly visible View My Other Meters button on the screen near the meter number. This button will only be visible for users with multiple meters.
Correct the message for “Add Meter” functionality when a user enters an invalid Meter Number
  Currently when a user adds a meter to their account and enters a valid ESIID and a valid REP, but an invalid Meter Number the message incorrectly displays “ESIID Does Not Exist”
  For this scenario the message will be corrected to display “Meter Number is incorrect. Please enter a valid Meter Number”

## Slide 9: December 17, 2016 SMT Minor Release to Correct Deficiencies and Usability Defects
SMT planned release for December 17 2016 will included the following:
Correct the defect that causes a Third Party agreement invitation to fail if the Third Party contact name contains a hyphen
  Currently on the Initiate Agreement screen, if the Third Party enters a Third Party Contact name with a hyphen under the Third Party Contact information section the invitation fails
  The SMT Third Party agreement invitation functionality will be modified to allow Third Party Contact names with hyphens

## Slide 10: December 17, 2016 SMT Minor Release to Correct Deficiencies and Usability Defects
The release is planned for implementation on December 17, 2016 and will required an outage of the portal website, HAN and ODR services from Saturday December 17, 2016 00:01 A.M. CST until Saturday December 17, 2016 6:00 A.M. CST.
LSE file delivery and the FTPS folders are not expected to be affected.
Market Notices will be sent out for the following::30 day (11//17/16), 10 day (12/7/16), 3 day (12/14/16), 1 day (12/16/6), and Final Complete (12/18/16)

## Slide 11: SMT ESIID Entry Length Shortened to 9 Digits

## Slide 12: SMT ESIID Length Shortened to 9 Digits
The SMT ESIID length was shortened to 9 digits in May of 2013
It was implemented in Release 4.4
It was implemented to improve usability and to address issues identified through help desk tickets concerning user ESIID entry

## Slide 13: SMT Customer Share Feedback

## Slide 14: SMT Customer Share Feedback
SMT provided a historical report containing all of the SMT customer share feedback for November 2014 through September 2016
SMT provided October 2016 weekly SMT customer share feedback reports
Going forward, SMT will continue to share the monthly customer share feedback report information with AMWG
Discuss historical and October SMT customer share feedback and next steps

## Slide 15: SMT Help Desk SLAs

## Slide 16: Status Update of AMWG Change Requests

## Slide 17: Status of AMWG Change Requests
Delivered | Approved Awaiting Project Packaging | Approved Awaiting Project Packaging | AMWG Reporting Options Under Review | RMS Approved Awaiting Categorization | JDOA Estimated Awaiting AMWG Review | Tabled RMS | AMWG Delayed | RMS Remanded back to AMWG | Pushed Back as Defect
2013 002 | 2015 021 | 2013 015 | 2013 001 |  |  | 2014 018 | 2015 029 |  | 2015 022
2013 005 | 2015 042 | 2015 019 | 2013 003 |  |  |  | 2015 030 |  | 
2013 006 | 2015 033 | 2015 020 | 2013 004 |  |  |  | 2015 031 |  | 
2013 007 |  | 2015 023 | 2013 008 |  |  |  | 2015 032 |  | 
2013 009 |  | 2015 025 | 2013 010 |  |  |  | 2015 034 |  | 
2013 012 |  | 2015 026 | 2013 011 |  |  |  | 2015 038 |  | 
2013 013 |  | 2015 027 |  |  |  |  | 2015 040 |  | 
2013 016 |  | 2015 028 |  |  |  |  | 2015 041 |  | 
2013 017 |  | 2015 035 |  |  |  |  |  |  | 
2015 024 |  | 2015 036 |  |  |  |  |  |  | 
2013 014 |  | 2015 037 |  |  |  |  |  |  | 
 |  | 2015 039 |  |  |  |  |  |  | 
Total 10 | See column 3 | Total 15 | Total 6 | Total 1 | Total 0 | Total 1 | Total 8 | Total 0 | Total 1

## Slide 18
AMWG Change Request | AMWG CR Document | Status | Categorization and Estimated Delivery Date | Estimated Cost
AMWG CR 2013 001 – Report for AMWG Data Monitoring – Data Completeness Measurements |  | Estimate Complete & RMS Approved 3/3/15 | Reporting Options Under Review | Small (20-40)
AMWG CR 2013 002 – Reports for AMWG Data Monitoring – Data Timeliness Measurements |  | Implemented | Q2 2014 Delivered | Included in Maintenance Contract
AMWG CR 2013 003 – Reports for AMWG Data Monitoring – Measurement of Percentage of Actual Meter Reads |  | Estimate Complete & RMS Approved 3/3/15 | Reporting Options Under Review | Small (20-40)
AMWG CR 2013 004 – Reports for AMWG Data Monitoring – Measurement of Estimates |  | Estimate Complete & RMS Approved 3/3/15 | Reporting Options Under Review | Medium (40-60)
AMWG CR 2013 005 – Reports for AMWG Data Monitoring – Number of SMT Help Desk Tickets Monthly by Ticket Type |  | Implemented | Q2 2014 Delivered | Included in Maintenance Contract
AMWG CR 2013 006 – Reports for AMWG Data Monitoring – Availability of SMT API |  | Implemented | Q2 2014 Delivered | Included in Maintenance Contract
AMWG CR 2013 007 – Reports for AMWG Data Monitoring – Availability of SMT FTPS |  | Implemented | Q2 2014 Delivered | Included in Maintenance Contract
AMWG CR 2013 008 – Reports for AMWG Data Monitoring – Average Time to Deliver HAN Messages |  | Estimate Complete & RMS Approved 3/3/15 | Reporting Options Under Review | Small (20-40)
AMWG CR 2013 009 – Reports for AMWG Data Monitoring – Number of Accounts by Type |  | Implemented | Q2 2014 Delivered | Included in Maintenance Contract
AMWG CR 2013 010 – Reports for AMWG Data Monitoring – Number of Reports Requested by GUI (Portal) and Number of FTPS Accesses |  | Estimate Complete & RMS Approved 5/6/15 | Reporting Options Under Review | Medium (40-60)
AMWG Change Requests

## Slide 19
AMWG Change Request | AMWG CR Document | Status | Categorization and Estimated Delivery Date | Estimated Cost
AMWG CR 2013 011 – Average Time from HAN Provision Request to Meter Ready Status |  | Estimate Complete & RMS Approved 3/3/15 | Reporting Options Under Review | Small (20-40)
AMWG CR 2013 012 – Bypass redundant screen for Users with only one meter when accessing HAN device information |  | Implemented | Q4 2014 Delivered | Included in Third-Party
AMWG CR 2013 013 – Timeout on SMT takes user to “incorrect login” screen |  | Implemented | Q4 2014 Delivered | Included in Third-Party
AMWG CR 2013 014 – Allow SMT user to toggle between 15-Minute Reads and Daily Reads without having to reset the date range |  | Implemented | February 2016 Delivered | Included in Usability
AMWG CR 2013 015 – Expand Daily Usage Graph to show 35 days of daily usage on the SMT GUI |  | Estimate Complete & RMS Approved 3/3/15 | 2 Important Awaiting Packaging | Medium (40-60)
AMWG CR 2013 016 – Capability for RORs to grant access to vendors on their behalf to the ROR’s customers via API (energy usage, HAN messaging , and HAN provisioning) and FTPS files |  | Implemented | Q3 2014 Delivered | Included in Maintenance Contract
AMWG CR 2013 017 – REP API for Energy Usage on SMT (Backfill of Historical Usage Data for Existing Customers- “Interim” Older infrastructure prior to May 2015 unable to meet required CR 017 volume ) | See Below CR 2013 017 FINAL | Implemented with performance less than requested in CR | Q4 2013 Delivered | Included in SMT Maintenance Contract
AMWG CR 2013 017 – REP API for Energy Usage on SMT (Subscription for New Customer Historical Usage – “Interim” Older infrastructure prior to May 2015 unable to meet required CR 017 volume ) | See Below CR 2013 017 FINAL | Implemented with performance less than requested in CR | Q2 2014 Delivered | Included in Maintenance Contract
AMWG CR 2013 017 – REP API for Energy Usage on SMT – FINAL - On May 2015 the new SMT infrastructure was implemented which enabled SMT to support the required CR 017 volumes) |  | New SMT infrastructure meets performance requirements in the CR | Q2 2015 Delivered | Delivered 2015
AMWG CR 2014 018 – Add Generation Data to the SMT Portal View |  | JDOA Estimate Completed | RMS Tabled 6/2/15 RMS Tabled 8/4/15 | Medium (40-60) Graph and Table Small (20-40) Table Only
AMWG Change Requests (Cont.)

## Slide 20
AMWG Change Request | AMWG CR Document | Status | Categorization and Estimated Delivery Date | Estimated Cost
AMWG CR 2015 019 – Relocate Various SMT User Guides from the Authenticated Site to the Unauthenticated Site |  | JDOA Estimate Completed | 2 Important Awaiting Packaging | Small (20-40)
AMWG CR 2015 020 – Add Customer Type in the Customer Information Section in the View / Edit Agreement Page |  | JDOA Estimate Completed | 3 Nice to Have Awaiting Packaging | Medium (40-60)
AMWG CR 2015 021 – Improve REP of Record Search Criteria During the Customer Registration Process |  | Estimate Complete & RMS Approved 5/6/15 | 1 Critical Awaiting Packaging | Medium,(40-60)
AMWG CR 2015 022 – Keep Selected ROR Visible During Customer Registration |  | JDOA Estimate Completed | Push Back as Defect | Small (20-40)
AMWG CR 2015 023 – Allow Entry of Multiple ESIIDs During Customer Registration Process |  | JDOA Estimate Completed | 3 Nice to Have Awaiting Packaging | High (60-120)
AMWG CR 2015 024 – Third Party Access Renew Energy Data Agreement After One Year |  | JDOA Estimate Completed | Q4 2015 Delivered | 0 Dollar
AMWG CR 2015 025 – Third Party User Experience Add Identifying Data Fields in the Report Request Status Page |  | JDOA Estimate Completed | 2 Important Awaiting Packaging | High (60-120)
AMWG CR 2015 026 – SMT Functionality Display Portal Message when Report Can Not be Displayed in the SMT Portal Page |  | JDOA Estimate Completed | 2 Important Awaiting Packaging | Minor (0-20)
AMWG CR 2015 027 – SMT Functionality Allow Specific Date Entry on the Export Report Screen |  | JDOA Estimate Completed | 3 Nice to Have Awaiting Packaging | Small (20-40)
AMWG CR 2015 028 – SMT Functionality Allow ESIIDs to be Copied and Pasted into the ESIID Box on the Usage Page |  | JDOA Estimate Completed | 3 Nice to Have Awaiting Packaging | Minor (0-20)
AMWG CR 2015 029 – This Party Allow Third Parties to Utilize an API for On Demand Data Requests |  | Estimate Complete & RMS Approved | AMWG Delayed | High (60-120)
AMWG Change Requests (Cont.)

## Slide 21
AMWG Change Request | AMWG CR Document | Status | Categorization and Estimated Delivery Date | Estimated Cost
AMWG CR 2015 030 – Support multiple RORs during CSV file meter upload |  | JDOA Estimate Completed | AMWG Delayed | High (60-120)
AMWG CR 2015 031 – Allow only current ROR for account registration validation and meter add validation |  | JDOA Estimate Completed | AMWG Delayed | High (60-120)
AMWG CR 2015 032 – Support SFTP protocol for SMT integration |  | Investigation Complete | AMWG Delayed | High (60-120)
AMWG CR 2015 033 – Provide user id and password rules up front on UI registration page |  | JDOA Estimate Completed | 2 Important Awaiting Packaging | Minor (0-20)
AMWG CR 2015 034 – Display the day of the week in addition to the date on usage reports |  | JDOA Estimate Completed | AMWG Delayed | Medium (40-60)
AMWG CR 2015 035 - Provide a customer-selected option to receive a monthly usage report via email |  | Estimate Complete & RMS Approved | 2 Important Awaiting Packaging | Medium (40-60)
AMWG CR 2015 036 – Rename Overview tab to Home |  | Estimate Complete & RMS Approved | 2 Important Awaiting Packaging | Minor (0-20)
AMWG CR 2015 037 – Remove SMT Demo from Private Site for REPs, TDSPs, and Third Parties |  | Estimate Complete & RMS Approved | 2 Important Awaiting Packaging | Minor (0-20)
AMWG CR 2015 038 – Provide a “Hold” capability on Third Party accounts to reactivate usage until the Third Party has integrated with FTPS and API |  | JDOA Estimate Completed | AMWG Delayed | High (60-120)
AMWG CR 2015 039 – Provide more detail for Third Party Agreement Invitation Error Messages |  | Estimate Complete & RMS Approved | 2 Important Awaiting Packaging | Medium (40-60)
AMWG CR 2015 040 – Improve SMT Administration Functionality for TDSPs, RORs, Third Parties, and Businesses |  | JDOA Estimate Completed | AMWG Delayed | 5 Functions Small, Small, Zero, Medium, High
AMWG Change Requests (Cont.)

## Slide 22
AMWG Change Request | AMWG CR Document | Status | Categorization and Estimated Delivery Date | Estimated Cost
AMWG CR 2015 041 – Allow Enrollment for New Customer 12 Month History for Third Parties |  | RMS Remanded back to AMWG for Further Discussion | AMWG Delayed | Medium (40-60)
AMWG CR 2015 042 – Automate Machine to Machine Consumption of Third Party Agreement Information |  | RMS Approved 8/4/15 | 2 Important Awaiting Packaging | Med / High (80)
AMWG Change Requests (Cont.)

## Slide 23: Rough Order Of Magnitude (ROM) Estimate of Effort Classification
These are rough order of magnitudes and do not include project ramp-up and testing effort (SIT & UAT) and only assumes unit testing.
Actual estimates could vary significantly depending on requirements.
Ramp-up and testing would be 20 to 40% of the overall effort
Overall project cost will vary based on efficiency gains from packaging like functionality
Change Type | ROM
MINOR | 0 – 20 K
SMALL | 20 – 40 K
MEDUIM | 40 – 60 K
HIGH | 60 – 120 K
VERY HIGH | Over 120 K

## Slide 24: Analysis of AMWG Change Requests
14 – Customer Usability Improvement
  2013 015
  2013 018
  2015 019
  2015 021
  2015 022
  2015 023
  2015 026
  2015 027
  2015 028
  2015 030
  2015 033
  2015 034
  2015 035
  2015 036

## Slide 25: Analysis of AMWG Change Requests
7 – Third Party Enhancement
  2015 020
  2015 025
  2015 029
  2015 038
  2015 039
  2015 041
  2015 042
1 – Security Control
  2015 031

## Slide 26: Analysis of AMWG Change Requests
6 – SMT New Reporting
  2013 001
  2013 003
  2013 004
  2013 008
  2013 010
  2013 011
3 – REP Usability Improvement
  2015 032
  2015 037
  2015 040

## Slide 27: SMT Third Party Processes Third Party Registration, Agreement Creation, Customer Agreement Acceptance, Other Third Party Processes

## Slide 28: SMT Third Party Processes
AMWG Key Documents Navigation Tool
R4.3 3rd Party – Navigation Deck (Part 1 of 2) – v3.1 – 20140611
R4.3 3rd Party – Navigation Deck (Part 2 of 2) – v3.1 – 20140611
SMT User Guides
Smart Meter Texas C?
Customer User Guide - Section 9 Managing Third Party Agreements
Smart Meter Texas Third Party Service Provider User Guide – Entire Document

## Slide 29: SMT Third Party Processes
SMT FAQs Public
What is a Third –Party Service Provider?
Who else can access my usage data, meter, and premise information?
Who else can access my In-Home Devices?
What is a Third-Party Agreement?
SMT FAQs Private (Third Parties and REPs)
All FAQs

## Slide 30: Analysis of Existing SMT Statistics Reports Not Already Shared with AMWG

## Slide 31: Analysis of Existing SMT Statistics Reports not Already Shared with AMWG
Identified one report “The Monthly Login Report” that is not currently shared on a monthly basis with AMWG
This report has been shared when requested to the Market, but no one to date has desired to continue on a monthly basis
The Monthly Login Report provides the number of SMT website successful logins by day over a month period
The Monthly Login Report for October has been provided for AMWG review

## Slide 32: Future Third Party Reporting Enhancements to Analysis and Statistics

## Slide 33: Future Third Party Reporting Enhancements to Analysis and Statistics
SMT Third Party Monthly Reporting Statistic Categories to be Added
  Invitations Accepted by Customers in the Month of the Reporting Period
  Invitations Not Accepted by Customers in the Month of the Reporting Period
  Invitations Pending in the Month of the Reporting Period
  Agreements Closed by Customers / Third Parties in the Month of the Reporting Period
  Agreements Completed in the Month of the Reporting period
SMT Third Party Help Desk Ticket Categories to be Added
  Registration Assistance
  Agreements Support
  FTP Integration
  API Integration
  Customer Data Access
  On Behalf of Vendor Request
  Front End Usability
  General Information

## Slide 34: Q&A Monthly SMT Reports to AMWG Data Through October 2016