## Slide 1
Project Update and Summary of
Project Priority List (PPL) Activity
December 1, 2016

## Slide 2
Project Portfolio Update p. 3-7
  Recent/Upcoming Project Highlights
  2016 Release Targets
  2017 Release Targets
  Aging Projects Review
  Priority/Rank Options for Revision Requests with Impacts
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index
Project Update Agenda

## Slide 3: Recent / Upcoming Project Highlights
2016 December Release – Week of 12/6/2016 In Flight
  NPRR713 – Reactive Power Testing Requirements
  NPRR754 – Revise Load Distribution Factors Report Posting Frequency
  NOGRR147 – Reactive Power Testing Requirements
  SCR787 – Maintain NDCRC Data For Generator Transfer Between Resource Entities
  SCR788 – Addition of Integral ACE Feedback to GTBD Calculation
2016 December Retail Release – Weekend of 12/10/2016 In Flight
  RMGRR127 – Efficiencies for Acquisition Transfer
  RMGRR140 – Efficiencies for Acquisition Transfer Process
  SCR786 – Retail Market Test Environment
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2016 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
NPRR686(b) – Solar portion
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
(a), (b), etc. indicates multiple phases
February 2/2 – 2/4 | April 4/12 – 4/14 | June 6/21 – 6/23 | August 8/30 – 9/1 | September 9/26 – 9/30 | December 12/6 – 12/8
NPRR588 NPRR615 NPRR686(b) | NPRR419 NPRR728 COPMGRR040 | NPRR515 NPRR617 NPRR700 NPRR719 NPRR742 VMCRR008 EMS Upgrade | NPRR662 NPRR712(a) RMGRR126 RMGRR137 | NPRR219 SCR783 NOGRR050 NOGRR143(a) NPRR712(b) NOGRR143(b) NPRR495 NPRR736 NPRR770 | NPRR713 NPRR754 NOGRR147 SCR787 SCR788 RMGRR127 RMGRR140 SCR786
3 | 3 | 6 | 4 | 9 | 8
Project Status Codes: NS = Not Started, I = Initiation, P = Planning, E = Execution, H = On Hold
-
E
E
E
E
E
E
E
EMS Upgrade “Chill”
6/16
12/10 – 12/11 (Retail)
7/23 – 7/24
(Retail)
11/1 – 11/3
5/1

## Slide 5: 2017 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
(a), (b), etc. indicates multiple phases
February 2/14 – 2/17 | May 5/2 – 5/4 | June 6/27 – 6/29 | September 9/12 – 9/14 | October 10/31 – 11/2 | December 12/5 – 12/7
NPRR272 NPRR649 NPRR764 RRGRR003 RRGRR006 RRGRR007 RRGRR009 | SCR790 NPRR746 NPRR785 NPRR786 RMGRR134 | NPRR573 NPRR714 NPRR744 NPRR758 NPRR782 NPRR789 | NPRR775 SCR777 |  | SCR789
7 | 5 | 6 | 2 | 0 | 1
Project Status Codes: NS = Not Started, I = Initiation, P = Planning, E = Execution, H = On Hold
2017 TBD Items (and point at which they became “TBD”)
2014 | 2015 | 2016
NOGRR084, NPRR664 | None | SCR781 H
In-Flight Items Planned for Future Delivery
CMM bundle (Planning): NPRR519, NPRR620, NPRR683, NPRR702, NPRR741, NPRR743, NPRR755, NPRR760
12/9 – 12/10 (Retail)
10/2 – 10/3
(Off-Cycle)
2/18 – 2/19
(Retail)
5/6 – 5/7
(Retail)
7/8 – 7/9
(Retail)
11/11 – 11/12 (Retail)
E
E
E
E
E
E
E
P
I
I
I
I
H
P
P
P
NS
NS
NS
E
NS
9/16 – 9/17
(Retail)
2/13 – NMMS Upgrade

## Slide 6: Aging Projects Review
Definition of “Aging Item”
  PPL Source Doc = Revision Request
  PPL Project Status = “Not Started”
  PPL Priority < Current Year
Item | Description | Board Approval Date | Submitter | Target PPL Start Date | Comments | ERCOT Opinion
NPRR664 | Index Fuel Price | 12/9/2014 | RCWG | TBD | TAC asked that ERCOT not proceed until further notice | Do not start – path forward is TBD

## Slide 7: Priority / Rank Options for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
 | None this month |  |  | 
Options for…