## Sheet1
TX SET Meeting Notes / Action Items
October 20th 2016
Agenda Item: | Decision / Resolution | Action Items :
September 2016 Meeting Notes | No additional comments or edits to meeting notes.
Mass Transition/Default-POLR Rule | • RMS assignment to discuss Mass Transition— Possible POLR Rule change from two days out to one day out.
AMWG Update
Other discussion
Market Test Flight 0214 Update | ERCOT to provide flight update No update received
TX SET Procedures | On Hold-Discuss reline changes sent to the TXSET listserv for review | Leave current issue process in tact and continue to review document to identify where additional process improvements can be made
RMS Updates
No October Meeting
Flight Update
IBANK01 & IBANK02 -- Refund discussion--Max No-Refund Limits? | Edit language in scripts to read "TDSPs are not required to refund amounts under $10. If the TDSP refunds the dollar amount to CR it shall use the same process that is used in production within 30 days of end of test. NOTE: Nueces does not execute this script" | ERCOT to add language to the script.
Discussion Items
Update Contact Information--CR Internal Discussion Update | CRs discussed internally and it was determined that the email address is considered confidential information and could not be passed along to the TDSPs. | No further action required.
Texas SET Transactions - Version 4.0 | It was discovered that the flow for the 814_25 transactions on the transaction description card was incorrect and needed to be revised. | ERCOT to update the transaction description card.
Issues
2016-I143, Validation Processes When a Character is Included in the Customer Name on a Switch or MVI Transaction--Review ERCOT Options 1 Continue With Existing Manual Workaround--Short Term 2 Update ERCOT’s Systems to Reject Any Transaction Containing Special Language Characters--Long Term 3 Update ERCOT’s Systems to Translate Special Language Characters into Normal Characters 4 Implement Option 3 in the Short Term, Followed by Option 2 During the Next TX SET Release | Discussion continued between Market Participants and ERCOT regarding the concerns of removing this language prior to a market change to address the issue. ERCOT committed to modify the NPRR and to bring the modified NPRR back to the market for consideration. | ERCOT to modifiy the current NPRR and resubmit for discussion.
RMS assignments:
NPRR796, Extended Character Set Clean Up—Revisit Last Month's discussion and make recommendation to RMS and consider possible Change Control / SCR for Issue I143 above. | See I143 Discussion | See action items for I143
New Entrant Documentation—Procedures and Documentation Location ERCOT Feedback on Opt In Checklist Continue New Entrant Document update | ERCOT presented an updated version of the Opt In Checklist for TEXAS SET's review. | ERCOT to send to the Texas SET email distribution list.
Add Mass Customer List (MCL) guide back to the Texas SET Guides--Create Change Control to add this back | Did not review, will review at next meeting. | On agenda for November
ERCOT Market Continuity Workshop- Retail o Continue Discussions | Jim Lee has notes
RMG Safety NET Timelines Notes: PUCT to Review Final Draft Prior to Texas SET Submitting Changes to RMS Discuss any updates offered from CRs | Short updates were provided by the CRs in attendance that they were still reviewing their processes.
Parking Lot
Texas SET Release Discussion | On Hold
REP Certification Matrix—Long-term solution | On Hold
Next Meeting--ERCOT MET Center | November 30th RM 168
Attendees -- Day 1
Kyle Patrick NRG | Kathryn Thurman ERCOT | Moncia Jones NRG
Lindsay Butterfield ERCOT | Sarah Heselmeyer ERCOT | Rebecca Reed Zerwas NRG
Kaci Jacobs TXU | Paul Yockey ERCOT
Kathy Scott CNP | Jim Lee AEP
Carolyn Reed CNP | Sam Pak ONCOR
Stephen Wilson SU | Monsherra Odanga ONCOR
Webex -- Day 1
Becky Taylor CNP
Deborah Croce EC InfoSystems
Barbara Goubeaud EC Inforsystems
Teresa Rodriguez Stream Energy
Mary Sithihao Stream Energy