## Slide 1
Project Update – RMS
January 10, 2017

## Slide 2
Project Portfolio Update p. 3-5
  2016 Release Results
  2017 Release Targets
  2016 Retail Project Results
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index
Project Update Agenda

## Slide 3: 2016 Release Results – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
NPRR686(b) – Solar portion
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
(a), (b), etc. indicates multiple phases
February 2/2 – 2/4 | April 4/12 – 4/14 | June 6/21 – 6/23 | August 8/30 – 9/1 | September 9/26 – 9/30 | December 12/6 – 12/8
NPRR588 NPRR615 NPRR686(b) | NPRR419 NPRR728 COPMGRR040 | NPRR515 NPRR617 NPRR700 NPRR719 NPRR742 NPRR745 VMCRR008 EMS Upgrade | NPRR662 NPRR712(a) RMGRR126 RMGRR137 | NPRR219 SCR783 NOGRR050 NOGRR143(a) NPRR712(b) NOGRR143(b) NPRR495 NPRR736 NPRR770 | NPRR713 NPRR754 NOGRR147 SCR787 SCR788 RMGRR127 RMGRR140 SCR786
3 | 3 | 7 | 4 | 9 | 8
Project Status Codes: NS = Not Started, I = Initiation, P = Planning, E = Execution, H = On Hold
EMS Upgrade “Chill”
6/16
12/10 – 12/11 (Retail)
7/23 – 7/24
(Retail)
11/1 – 11/3
5/1

## Slide 4: 2017 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
(a), (b), etc. indicates multiple phases
March 3/7 – 3/9 | May 5/9 – 5/11 | July 7/11 – 7/13 | September 9/12 – 9/14 | October 10/31 – 11/2 | December 12/5 – 12/7
NPRR272 NPRR649 NPRR764 NPRR785 RRGRR003 RRGRR006 RRGRR007 RRGRR009 | SCR790 NPRR746 NPRR786 RMGRR134 | NPRR573 NPRR714 NPRR744 NPRR758 NPRR782 NPRR789 | NPRR775 SCR777 | NPRR778 | SCR789
8 | 4 | 6 | 2 | 1 | 1
Project Status Codes: NS = Not Started, I = Initiation, P = Planning, E = Execution, H = On Hold
2017 TBD Items (and point at which they became “TBD”)
2014 | 2015 | 2016 | 2017
NOGRR084, NPRR664 | None | SCR781 H | None
In-Flight Items Planned for Future Delivery
CMM bundle (Planning): NPRR519, NPRR620, NPRR683, NPRR702, NPRR741, NPRR743, NPRR755, NPRR760
12/9 – 12/10 (Retail)
10/2 – 10/3
(Off-Cycle)
3/18 – 3/19
(Retail)
5/20 – 5/21
(Retail)
7/15 – 7/16
(Retail)
11/11 – 11/12 (Retail)
E
E
E
E
E
E
E
E
P
I
I
E
H
P
P
P
NS
NS
NS
E
NS
NS
9/16 – 9/17
(Retail)
2/13 – NMMS Upgrade

## Slide 5: 2016 Retail Project Results
Revision Request | Impact Analysis | Results
SCR786 Retail Market Test Environment | $100k-$150k * 4-6 months | $95k ** 8 months
RMGRR126 Additional ERCOT Validations for CBCI File | $35k-$55k 4-6 months | Delivered in July 2016 with Mass Transition Acquisition Enhancements project
RMGRR137 Timeline and Completion Process for Correcting CBCI Files | No project required | Delivered in July 2016 with Mass Transition Acquisition Enhancements project
RMGRR127 Efficiencies for Acquisition Transfer | <$10k O&M | Delivered in December 2016 with Mass Transition Acquisition Enhancements project
RMGRR140 Efficiencies for Acquisition Transfer Process | <$5k O&M | Delivered in December 2016 with Mass Transition Acquisition Enhancements project
** Project is not yet closed so actual spending includes remaining forecast
* Original IA estimated at $1.5M-$2.5M for 1.5-3.0 years
Market and ERCOT worked out an alternative to achieve the majority of desired benefits at a reduced cost

## Slide 6: Questions?
Any Questions?