|  |  |  |  | System Planning |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Monthly Status Report November 2016 |  |  |
|  |  | Report Highlights |  |  |  |  |
|  | - ERCOT is currently reviewing proposed transmission improvements with a total cost of $855.7 Million. - Transmission Projects endorsed in 2016 total $489.1 Million. - All projects (in engineering, routing, licensing and construction) total approximately $6.23 Billion as of October 1, 2016. - Transmission Projects energized in 2016 total about $1.72 Billion as of October 1, 2016. |  |  |  |  |  |

Regional Planning Group Project Reviews

- AEPSC has submitted the Maverick County Transmission project. This is a Tier 2 project that is estimated to cost $44.3 million. This project is currently under ERCOT independent review.

- Oncor has submitted the Riverton–Sand Lake 138kV line project. This is a Tier 2 project that is estimated to cost $26 million. ERCOT has completed the independent review and issued the report.

- AEPSC and Oncor have jointly submitted the Far West Texas project. This is a Tier 1 project that is estimated to cost $423 million. This project is currently under ERCOT independent review.

- Brazos Electric Cooperative (BEC) has submitted the Northern Johnson County Area Improvement project. This is a Tier 2 project that is estimated to cost $8.1 million. This project is currently under ERCOT independent review.

- LCRA TSC has submitted the Cooks Point substation project. This is a Tier 1 project that is estimated to cost $52 million. This project is currently under ERCOT independent review.

- Oncor has submitted the NW Carrollton-Norwood 138 kV Double-Circuit Line Upgrade project.  This is a Tier 3 project that is estimated to cost $23.5 million. This project has completed the RPG review and ERCOT will prepare the RPG acceptance letter.

- Sharyland Utilities has submitted the South Plains Transmission project. This is a Tier 1 project that is estimated to cost $251 million. This project is under study mode.

- LCRA TSC has submitted the Mountain Home substation and transmission line addition project. This is a Tier 1 project that is estimated to cost $77.3 million. This project has been submitted for RPG comments.

# Planning Model Activities

The short term calendar of major planning model events is as follows:

- Nov 21, 2016	Complete Transmission Loss Factors

The following table shows interconnection projects that met Planning Guide section 6.9(1)(b) – 6.9(1)(d) and were not modeled in SSWG cases due to lack of RARF data in accordance with Planning Guide section 6.9(1)(a) and 6.9(3).  “Insufficient Planning Data” refers to data needed only for the Steady State model and is not the complete set of data marked Required for Planning in the Resource Registration Glossary.

# Other Notable Activities

- ERCOT is currently finalizing the 2016 Regional Transmission Plan (RTP) study. ERCOT has completed its reliability and economic analysis for the 2016 RTP.

- ERCOT has started developing the scope for the 2017 RTP. A scope and process document was shared with the Regional Planning Group (RPG) for feedback and review on October 21, 2016.

- ERCOT is finalizing the 2016 Long Term System Assessment (LTSA). ERCOT has completed reliability analysis for the three scenarios, namely the Current Trends Scenario, Environmental Mandate, and the High Energy Efficiency and Distributed Generation Scenario.  ERCOT is currently working on  completing its LTSA economic analysis. A list of preminary projects and cases was posted for stakeholder review on the MIS Secure website on October 18, 2016.

- On July 19, 2016, Public Utility Commission of Texas (PUCT) Chairman Nelson filed a memo in docket 45633 addressing the proposed move of the Lubbock Power and Light (LP&L) system from the Southwest Power Pool (SPP) grid into the Electric Reliability Council of Texas (ERCOT) grid.  The memo included a recommendation for analyses to be performed by SPP and ERCOT. ERCOT and SPP have worked together to develop a SPP-ERCOT Coordinated Lubbock ERCOT Integration Study Scope. The study scope was presented to the stakeholders in November RPG meeting.

- ERCOT presented the Rayburn Load Integration Study scope to stakeholders in September RPG meeting. ERCOT is currently working on the Rayburn Load Integration Study.

- ERCOT finalized NERC PRC-006-2 UFLS assessment and the report had been reviewed by the ERCOT Dynamics Working Group.