## Slide 1: Planning Geomagnetic Disturbance Task Force (PGDTF) Update to the ROS
January 12, 2017
Michael Juricek
PGDTF Chairman
<number>
1/12/2017 ROS Meeting

## Slide 2: National and State GMD Activity
The NERC Planning Committee Approved the GMDTF’s Proposal to Address the FERC’s Directives.
The NECR GMD Mitigation Standard Drafting Team Meets on January 17 through 19, 2017. WebEx is Available.
FERC Deadline for Response to Directives is May 29, 2018.
85 (R) SB 83 – Relating to Protection of Energy Critical Infrastructure From Electromagnetic, Geomagnetic, Terrorist, and Cyber- Attack Threats.
85 (R) HB 407 – Relating to Protection of the Electric Power Transmission and Distribution System.
Michael Juricek – 1/12/2017 ROS Meeting
<number>

## Slide 3: Activities for the PGDTF in 2017
Document GMD Planning Responsibilities in the Planning Guide for June 2017 BOD Meeting (R1).
Create GIC System Model for Geomagnetic Disturbance (GMD) Vulnerability Assessment (R2).
Revise GIC System Model Procedure Manual.
Met on January 11, 2017.
Michael Juricek – 1/12/2017 ROS Meeting
<number>

## Slide 4: Schedule for Creating GIC System Model
12/31/2016 – TSP Data for 345 kV System Based on 2021 Summer Peak Case Released on 10/15/2016 Due to ERCOT
3/31/2017 – TSP Data for 138 kV and 69 kV Systems and RE Data Based on 2021 Summer Peak Case Released on 10/15/2016 and Update to 345 kV System Data Due to ERCOT
6/1/2017 – ERCOT Provides First Pass of GIC System Model for Review to TSPs and REs
7/1/2017 – TSPs and REs Provide Changes to GIC System Model to ERCOT
Subsequent Model Review Passes as Needed
1/1/2018 – Complete 2021 Summer Peak and 2021 Minimum GIC System Models Using July 2017 SSWG 2021 Summer Peak and 2021 Minimum Base Cases
Michael Juricek – 1/12/2017 ROS Meeting
<number>

## Slide 5: Questions and Answers
<number>
Michael Juricek – 1/12/2017 ROS Meeting