## Slide 1
Flight Testing Update
Paul Yockey
Flight Administrator
Texas Set Working Group
01/24/2017

## Slide 2
Agenda
Flight 0217 Schedule
Flight 0217 Summary
Flight 0217 Adhoc Schedule
Questions

## Slide 3: Flight 0217 Schedule
Initial Flight 0217 Market Notice was sent 12/14/2016
Flight 0217 signup began 01/11/2017
Flight 0217 signup deadline was 01/18/17
Connectivity testing begins 01/24/17
Day 1 transactions begin 02/13/17
Flight 0217 is scheduled to conclude on 02/24/17 (Contingency/Adhoc Period until 04/07/17)
Texas Set Working Group
01/24/17

## Slide 4: Flight 0217 Summary
3 New CRs are testing
2 New DUNS + 4 CRs are testing
2 Existing CRs are testing for Service Provider Change
1 CR is testing for Bank Change
1621 tasks are scheduled including connectivity
Texas Set Working Group
01/24/17

## Slide 5: Flight 0217 Adhoc Schedule
Adhoc signup deadline is 02/24/17
Adhoc connectivity testing begins 02/27/17
Adhoc testing begins no later than 03/10/17
All scripts to be completed by 03/31/17
Texas Set Working Group
01/24/17

## Slide 6: Questions
Questions?
Texas Set Working Group
01/24/17