## PROJECTS
Generator Interconnection Status Report | January 2017
Date: 2/1/2017 8:39:42 AM

## New Units
New Resources Approved for Synchronization
INR | Project | MW | County | Part2 Synch Apprv
16INR0037b | Old Settler Wind | 150 | Floyd | 2017-01-12
16INR0037 | Cotton Plains Wind | 50 | Floyd | 2017-01-12
16INR0073 | East Pecos Solar | 120 | Pecos | 2017-01-25
17INR0009 | Wolf Hollow 2 | 1118 | Hood | 2017-01-05
New Resources Approved for Commercial Operation
INR | Project | MW | County | Resource Commissioning Date*
16INR0062a | Electra Wind | 230 | Wilbarger | 2017-01-31
14INR0060 | Horse Creek Wind | 230 | Haskell | 2017-01-23
*Defined in Section 2 of the ERCOT Nodal Protocols: The date on which ERCOT declares that a Resource has completed all qualification testing administered by ERCOT as part of the Resource Interconnection process so that a Resource is approved for participation in ERCOT market operations.

## Summary of GIR
Summary of Generation Interconnection Requests |  | Fuel Type | Screening Study (MW)* | Full Study (MW) | IA Executed, FIS Approved (MW) | IA Executed, FIS Pending (MW) | Grand Total (MW)**
Currently tracking 254 generation interconnection or change requests |  | Gas-AllOther | 0 | 2860 | 3768 | 1378 | 8006
GENERATION INTERCONNECTION REQUESTS CURRENTLY UNDER REVIEW |  | Gas-CombinedCycle | 0 | 2573 | 5568 | 2329 | 10470
January 2017 | Total | Total Gas | 0 | 5433 | 9336 | 3707 | 18476
Security Screening Study (SSS) Underway | 51 | Nuclear | 0 | 0 | 0 | 0 | 0
SSS Completed | 36 | Coal | 0 | 0 | 240 | 0 | 240
Full Interconnect Study (FIS) Underway | 105 | Wind | 3682 | 11982 | 4256 | 6350 | 26270
FIS Completed | 4 | Solar | 6171 | 6308 | 1063 | 956 | 14498
Interconnection Agreement Executed -> FIS Pending | 40 | Biomass | 0 | 0 | 0 | 0 | 0
Interconnection Agreement Executed | 54 | Storage | 0 | 270 | 324 | 30 | 624
Total Interconnection Requests | 254 | Petroleum Coke | 0 | 0 | 0 | 0 | 0
Cancelled Studies (since last month) | 2 | Total | 9853 | 23993 | 15219 | 11043 | 60108
Total Capacity Under Study, MW | 60108 | * Confidential project interconnection requests per Protocol Section 1.3.1.1(l) If the capacity for a single project is reported in the column, the value is redacted.
Total Wind Capacity, MW | 26270 | ** Redacted project capacity from column E is excluded from the Grand Totals.
Interconnection Agreement Executed, MW | 26262
Cancelled Capacity, MW (since last month) | 190
Screening Study column: Total MW capacity for which a Screening Study is underway or completed, but a Full Interconnect Study (FIS) has not been requested yet.
Full Study column: Total MW capacity for which an FIS has been requested. This includes projects in the following four subcategories:
• FIS and Screening Study both pending
• FIS pending and Screening Study completed
• FIS pending and an Interconnection Agreement (IA) has been executed (Note: this is the MW amount reported in the IA Executed / FIS Pending
column described below, and ties to the amounts reported in the “IA Table” tab)
· FIS completed and approved by ERCOT
IA Executed, FIS Approved column: Total MW capacity for which an IA has been executed and an FIS has been requested and approved.
IA Executed, FIS Pending column: Total MW capacity for which an FIS has been requested and is still pending, but an IA has been executed.

## IA Table
Generation Interconnection Agreements as of January 2017
Planning Guide Section 6.9 Requirements
(Other than model data submission)
GINR Reference Number | Project Name | County | Projected Date | Fuel | MW For Grid | Changes From Last Report | Meets Section 6.9 Requirements (1)(b) through (1)(d) | Sufficient Financial Security Received by TSP | Air Permit | Water Rights | FIS completion
14INR0062 | Salt Fork 1 Wind | Gray | 2017-01-01 | WIND | 174 | Projected Date | Yes | Yes | N/A | N/A | Complete
15INR0085 | Tyler Bluff Wind | Cooke | 2017-01-01 | WIND | 126 | Projected Date | Yes | Yes | N/A | N/A | Complete
12INR0059b | Barilla Solar 1B | Pecos | 2017-02-01 | SOLAR | 7 | Projected Date | Yes | Yes | N/A | N/A | Complete
13INR0010b | Mariah Del Norte | Parmer | 2017-02-01 | WIND | 230 | Projected Date | Yes | Yes | N/A | N/A | Complete
14INR0013 | San Roman Wind 1 | Cameron | 2017-02-01 | WIND | 94 | Projected Date | Yes | Yes | N/A | N/A | Complete
15INR0070_1 | West Texas Solar | Pecos | 2017-02-01 | SOLAR | 110 |  | Yes | Yes | N/A | N/A | Complete
16INR0037 | Cotton Plains Wind | Floyd | 2017-02-01 | WIND | 50 | Projected Date | Yes | Yes | N/A | N/A | Complete
16INR0037b | Old Settler Wind | Floyd | 2017-02-01 | WIND | 150 | Projected Date | Yes | Yes | N/A | N/A | Complete
14INR0038 | PHR Peakers | Galveston | 2017-03-01 | GAS | 390 |  | Yes | Yes | Yes | N/A | Complete
15INR0061 | SolaireHolman 1 | Brewster | 2017-03-01 | SOLAR | 50 |  | Yes | Yes | N/A | N/A | Complete
16INR0023 | BNB Lamesa Solar (Phase I) | Dawson | 2017-03-01 | SOLAR | 102 | Projected Date | Yes | Yes | N/A | N/A | Complete
16INR0054 | NASA-JSC CHP | Harris | 2017-03-01 | GAS | 12 | PG Section 6.9 | Yes | Yes | N/A | N/A | Complete
16INR0073 | East Pecos Solar | Pecos | 2017-03-01 | SOLAR | 120 |  | Yes | Yes | N/A | N/A | Complete
15INR0070_1b | Pearl Solar | Pecos | 2017-04-01 | SOLAR | 50 |  | Yes | Yes | N/A | N/A | Complete
16INR0122 | Blue Summit Battery | Wilbarger | 2017-04-01 | STORAGE | 30 | NEW | No | No | N/A | N/A | Incomplete
15INR0074 | Falvez Astra W | Deaf Smith | 2017-05-01 | WIND | 163 |  | Yes | Yes | N/A | N/A | Complete
16INR0055 | Chapman Ranch Wind I | Nueces | 2017-05-01 | WIND | 250 |  | Yes | Yes | N/A | N/A | Complete
17INR0009 | Wolf Hollow 2 | Hood | 2017-05-01 | GAS | 1118 |  | Yes | Yes | Yes | Yes | Complete
13INR0049 | Friendswood G | Harris | 2017-06-01 | GAS | 129 | Projected Date | Yes | Yes | Yes | Yes | Complete
14INR0031 | Baytown Chiller | Chambers | 2017-06-01 | GAS | 270 |  | Yes | Yes | Yes | N/A | Complete
17INR0007 | Colorado Bend II | Wharton | 2017-06-01 | GAS | 1148 |  | Yes | Yes | Yes | Yes | Complete
17INR0022 | NET Power LaPorte | Harris | 2017-06-01 | GAS | 11 |  | No | Yes | Yes | No | Complete
11INR0054 | Midway Wind | San Patricio | 2017-08-01 | WIND | 161 |  | Yes | Yes | N/A | N/A | Complete
11INR0062 | Patriot Wind | Nueces | 2017-08-01 | WIND | 180 |  | Yes | Yes | N/A | N/A | Incomplete
11INR0082a | Val Verde Wind | Val Verde | 2017-08-01 | WIND | 149 |  | Yes | Yes | N/A | N/A | Complete
16INR0065b | SP-TX-12-Phase B | Upton | 2017-08-01 | SOLAR | 120 |  | Yes | Yes | N/A | N/A | Complete
16INR0082 | Salt Fork 2 Wind | Carson | 2017-08-01 | WIND | 200 |  | No | No | N/A | N/A | Incomplete
15INR0064 | BearKat Wind A | Glasscock | 2017-09-01 | WIND | 197 | SFS, PG Section 6.9 | Yes | Yes | N/A | N/A | Incomplete
17INR0027 | Dermott Wind 1 | Scurry | 2017-09-01 | WIND | 250 |  | Yes | Yes | N/A | N/A | Incomplete
12INR0002a | Silver Canyon Wind A | Briscoe | 2017-10-01 | WIND | 200 |  | No | No | N/A | N/A | Incomplete
13INR0056 | Fluvanna Renewable 1 | Scurry | 2017-10-01 | WIND | 155 |  | Yes | Yes | N/A | N/A | Incomplete
14INR0060b | Willow Springs Wind | Haskell | 2017-10-01 | WIND | 230 |  | Yes | Yes | N/A | N/A | Incomplete
16INR0009 | Port Comfort | Calhoun | 2017-10-01 | GAS | 100 | Project Name | Yes | Yes | Yes | Yes | Complete
16INR0049 | Nazareth Solar | Castro | 2017-10-01 | SOLAR | 201 |  | No | No | N/A | N/A | Complete
16INR0062b | Lockett Wind Farm | Wilbarger | 2017-10-01 | WIND | 184 |  | Yes | Yes | N/A | N/A | Complete
16INR0087 | RTS Wind | McCulloch | 2017-10-01 | WIND | 160 | Projected Date | Yes | Yes | N/A | N/A | Complete
14INR0057 | Buckthorn Wind 1 | Erath | 2017-11-01 | WIND | 96 |  | Yes | Yes | N/A | N/A | Complete
15INR0082 | Flat Top Wind I | Comanche | 2017-11-01 | WIND | 200 |  | Yes | Yes | N/A | N/A | Incomplete
12INR0059c | Barilla Solar 2 | Pecos | 2017-12-01 | SOLAR | 21 |  | No | No | N/A | N/A | Complete
12INR0060 | Infinity Live Oak Wind | Schleicher | 2017-12-01 | WIND | 201 |  | No | No | N/A | N/A | Complete
13INR0005c | Grandview W 3 | Carson | 2017-12-01 | WIND | 188 |  | Yes | Yes | N/A | N/A | Incomplete
13INR0038 | Swisher Wind | Swisher | 2017-12-01 | WIND | 300 |  | Yes | Yes | N/A | N/A | Complete
14INR0023b | Longhorn South | Briscoe | 2017-12-01 | WIND | 160 | Projected Date | Yes | Yes | N/A | N/A | Complete
14INR0030c | Panhandle Wind 3 | Carson | 2017-12-01 | WIND | 248 |  | No | No | N/A | N/A | Incomplete
14INR0041a | Bruenning's Breeze | Willacy | 2017-12-01 | WIND | 228 | Project Name, Projected Date | Yes | Yes | N/A | N/A | Incomplete
14INR0045a | Torrecillas Wind A | Webb | 2017-12-01 | WIND | 200 |  | Yes | Yes | N/A | N/A | Incomplete
14INR0045b | Torrecillas Wind B | Webb | 2017-12-01 | WIND | 200 |  | Yes | Yes | N/A | N/A | Incomplete
15INR0045 | Riggins Solar | Pecos | 2017-12-01 | SOLAR | 150 |  | Yes | Yes | N/A | N/A | Incomplete
15INR0049 | Javelina 2 Wind | Zapata | 2017-12-01 | WIND | 200 | Projected Date | Yes | Yes | N/A | N/A | Complete
16INR0019 | Capricorn Ridge Solar | Coke | 2017-12-01 | SOLAR | 100 |  | No | No | N/A | N/A | Incomplete
16INR0091 | Santa Rita Wind | Reagan | 2017-12-01 | WIND | 300 |  | Yes | Yes | N/A | N/A | Complete
16INR0121 | Salt Fork Wind Expansion | Carson | 2017-12-01 | WIND | 54 |  | No | No | N/A | N/A | Incomplete
16INR0003 | Freeport LNG | Brazoria | 2018-02-01 | GAS | 11 |  | Yes | Yes | Yes | N/A | Complete
12INR0018 | Pampa Wind | Gray | 2018-03-01 | WIND | 500 |  | No | No | N/A | N/A | Incomplete
14INR0033 | Goodnight Wind | Armstrong | 2018-03-01 | WIND | 500 |  | No | No | N/A | N/A | Incomplete
16INR0023b | Lamesa Solar B (Phase II) | Dawson | 2018-03-01 | SOLAR | 98 |  | No | No | N/A | N/A | Incomplete
18INR0001 | Rockwood G | Colorado | 2018-04-01 | GAS | 1122 |  | No | No | Yes | No | Complete
13INR0010a | Mariah Del Este | Parmer | 2018-06-01 | WIND | 139 |  | Yes | Yes | N/A | N/A | Incomplete
13INR0010c | Mariah Del Sur | Parmer | 2018-06-01 | WIND | 230 |  | Yes | Yes | N/A | N/A | Incomplete
13INR0026 | Canadian Breaks Wind | Oldham | 2018-06-01 | WIND | 201 | Projected Date | No | No | N/A | N/A | Incomplete
16INR0044 | Halyard Wharton | Wharton | 2018-06-01 | GAS | 419 |  | No | No | Yes | Yes | Complete
16INR0045 | Halyard Henderson | Henderson | 2018-06-01 | GAS | 450 |  | No | No | Yes | Yes | Incomplete
16INR0074 | Chocolate Bayou | Brazoria | 2018-06-01 | WIND | 150 |  | No | No | N/A | N/A | Complete
17INR0003 | SPC Jackson G | Jackson | 2018-06-01 | GAS | 916 |  | No | No | No | No | Complete
17INR0016 | Navasota South Peaker | Wilson | 2018-06-01 | GAS | 582 |  | No | No | Yes | No | Complete
17INR0017 | Clear Springs G | Guadalupe | 2018-06-01 | GAS | 558 |  | No | No | Yes | No | Complete
15INR0064b | BearKat Wind B | Glasscock | 2018-09-01 | WIND | 129 | NEW | Yes | Yes | N/A | N/A | Incomplete
17INR0027b | Coyote Wind | Scurry | 2018-09-01 | WIND | 250 |  | Yes | Yes | N/A | N/A | Incomplete
13INR0010def | Scandia Wind DEF | Parmer | 2018-10-01 | WIND | 600 |  | No | No | N/A | N/A | Incomplete
15INR0050 | Unity Wind | Deaf Smith | 2018-10-01 | WIND | 203 |  | No | No | N/A | N/A | Incomplete
15INR0079 | Pullman Road | Randall | 2018-10-01 | WIND | 300 |  | No | No | N/A | N/A | Complete
17INR0020a | RE Maplewood 2a Solar | Pecos | 2018-10-01 | SOLAR | 100 |  | Yes | Yes | N/A | N/A | Incomplete
18INR0004 | Shawnee G | Hill | 2018-10-01 | GAS | 928 |  | No | No | Yes | No | Incomplete
10INR0009 | Caprock Wind | Castro | 2018-12-01 | WIND | 300 | Projected Date | No | No | N/A | N/A | Incomplete
12INR0029 | Comanche Run Wind | Swisher | 2018-12-01 | WIND | 500 |  | No | No | N/A | N/A | Complete
13INR0045 | Changing Winds | Castro | 2018-12-01 | WIND | 288 | Projected Date | No | No | N/A | N/A | Incomplete
16INR0005 | Brownsville G | Cameron | 2018-12-01 | GAS | 871 |  | No | No | Yes | No | Complete
16INR0114 | Upton Solar | Upton | 2018-12-01 | SOLAR | 102 |  | Yes | Yes | N/A | N/A | Complete
15INR0059 | Pecos Solar I | Pecos | 2019-01-01 | SOLAR | 108 |  | No | No | N/A | N/A | Incomplete
16INR0037c | Pumpkin Farm Wind | Floyd | 2019-01-01 | WIND | 280 |  | Yes | Yes | N/A | N/A | Incomplete
16INR0065 | Castle Gap Solar | Upton | 2019-01-01 | SOLAR | 150 | Projected Date, MW For Grid | Yes | Yes | N/A | N/A | Complete
15INR0023 | Indeck Wharton | Wharton | 2019-02-01 | GAS | 654 |  | No | No | Yes | Yes | Complete
16INR0008 | Tenaska Roans Prairie | Grimes | 2019-04-01 | GAS | 663 |  | No | No | Yes | No | Complete
16INR0010 | FGE Texas 1 | Mitchell | 2019-04-01 | GAS | 745 |  | No | No | Yes | Yes | Incomplete
17INR0020b | RE Maplewood 2b Solar | Pecos | 2019-05-01 | SOLAR | 200 |  | Yes | Yes | N/A | N/A | Incomplete
14INR0027 | Guadalupe II | Guadalupe | 2019-06-01 | GAS | 362 |  | No | Yes | Yes | No | Complete
17INR0010 | FGE Texas II | Mitchell | 2019-09-01 | GAS | 799 |  | No | No | Yes | No | Incomplete
13INR0023 | Texas Clean C | Ector | 2019-12-01 | COAL | 240 |  | No | No | Yes | Yes | Complete
16INR0065a | Castle Gap Solar 2 | Upton | 2020-01-01 | SOLAR | 30 | Projected Date, MW For Grid | Yes | Yes | N/A | N/A | Complete
17INR0020c | RE Maplewood 2c Solar | Pecos | 2020-01-01 | SOLAR | 100 |  | Yes | Yes | N/A | N/A | Incomplete
16INR0006 | Pinecrest G | Angelina | 2020-04-01 | GAS | 785 | Projected Date | No | No | Yes | Yes | Incomplete
13INR0020b | Rattlesnake W 2 | Glasscock | 2020-05-01 | WIND | 158 | Projected Date | No | No | N/A | N/A | Complete
17INR0020d | RE Maplewood 2d Solar | Pecos | 2020-07-01 | SOLAR | 100 |  | Yes | Yes | N/A | N/A | Incomplete
15INR0013 | Bethel CAES | Anderson | 2020-11-01 | STORAGE | 324 |  | No | No | Yes | Yes | Complete

## Full Study Table
All Projects, in the Full Interconnect Study (FIS) phase, without a Signed Interconnection Agreement
GINR Reference Number | County | Fuel | Capacity to Grid (MW) | Projected Date (as specified by the resource developer)
17INR0042 | Harris | Gas | 100 | 2017-04-01
17INR0053 | Taylor | Wind | 44 | 2017-04-05
17INR0052 | Taylor | Wind | 44 | 2017-04-05
16INR0122 | Wilbarger | Storage | 30 | 2017-04-05
17INR0035 | Willacy | Wind | 227 | 2017-05-31
16INR0014 | Castro | Wind | 200 | 2017-07-01
14INR0074 | Williamson | Gas | 92 | 2017-07-01
16INR0082 | Carson | Wind | 200 | 2017-08-01
17INR0046 | Upton | Solar | 450 | 2017-08-15
11INR0062 | Nueces | Wind | 180 | 2017-08-15
17INR0027 | Scurry | Wind | 250 | 2017-09-01
15INR0064 | Glasscock | Wind | 197 | 2017-09-15
16INR0093 | Reeves | Solar | 48 | 2017-10-01
16INR0089 | Andrews | Solar | 60 | 2017-10-01
14INR0060b | Haskell | Wind | 230 | 2017-10-01
13INR0056 | Scurry | Wind | 155 | 2017-10-17
12INR0002b | Briscoe | Wind | 200 | 2017-10-31
12INR0002a | Briscoe | Wind | 200 | 2017-10-31
14INR0048_1 | Wilbarger | Wind | 114 | 2017-11-30
15INR0063 | Castro | Wind | 200 | 2017-11-30
15INR0082 | Comanche | Wind | 200 | 2017-11-30
17INR0033 | Briscoe | Wind | 200 | 2017-12-01
16INR0117 | Briscoe | Wind | 200 | 2017-12-01
16INR0076 | Brazoria | Gas | 135 | 2017-12-01
16INR0061 | Hardeman | Wind | 200 | 2017-12-01
16INR0033 | Castro | Wind | 150 | 2017-12-01
16INR0014b | Castro | Wind | 200 | 2017-12-01
16INR0012 | Kenedy | Wind | 200 | 2017-12-01
15INR0051 | Castro | Wind | 200 | 2017-12-01
14INR0044 | Reeves | Solar | 100 | 2017-12-01
13INR0006 | Gray | Wind | 750 | 2017-12-01
08INR0019c | Gray | Wind | 250 | 2017-12-01
08INR0019b | Gray | Wind | 250 | 2017-12-01
08INR0019a | Gray | Wind | 250 | 2017-12-01
16INR0121 | Carson | Wind | 54 | 2017-12-01
16INR0019 | Coke | Solar | 100 | 2017-12-01
14INR0041a | Willacy | Wind | 228 | 2017-12-01
16INR0115 | Pecos | Solar | 182 | 2017-12-15
15INR0062 | Hale | Wind | 200 | 2017-12-15
13INR0005c | Carson | Wind | 188 | 2017-12-15
15INR0045 | Pecos | Solar | 150 | 2017-12-22
15INR0054 | Reeves | Gas | 123 | 2017-12-29
15INR0053 | Winkler | Gas | 123 | 2017-12-29
14INR0014 | Val Verde | Solar | 100 | 2017-12-30
14INR0030c | Carson | Wind | 248 | 2017-12-30
17INR0043 | Brooks | Wind | 400 | 2017-12-31
17INR0038 | Zapata | Wind | 400 | 2017-12-31
17INR0036 | Gray | Wind | 200 | 2017-12-31
17INR0032 | Duval | Wind | 53 | 2017-12-31
17INR0031 | Cameron | Wind | 150 | 2017-12-31
17INR0005 | Starr | Wind | 200 | 2017-12-31
16INR0112 | La Salle | Wind | 200 | 2017-12-31
16INR0111 | Starr | Wind | 200 | 2017-12-31
16INR0105 | Jim Hogg | Wind | 300 | 2017-12-31
16INR0100 | Brewster | Solar | 150 | 2017-12-31
16INR0099 | Brewster | Solar | 50 | 2017-12-31
16INR0098 | Brewster | Solar | 50 | 2017-12-31
16INR0097 | Upton | Solar | 200 | 2017-12-31
16INR0092 | Brewster | Solar | 50 | 2017-12-31
16INR0086 | Concho | Wind | 150 | 2017-12-31
16INR0081 | Starr | Wind | 200 | 2017-12-31
16INR0029 | Hill | Wind | 200 | 2017-12-31
16INR0027 | Grayson | Wind | 100 | 2017-12-31
15INR0044 | Webb | Solar | 200 | 2017-12-31
14INR0056 | Mills | Wind | 101 | 2017-12-31
14INR0045b | Webb | Wind | 200 | 2017-12-31
14INR0045a | Webb | Wind | 200 | 2017-12-31
18INR0048 | Anderson | Gas | 100 | 2018-01-01
18INR0010 | Karnes | Gas | 396 | 2018-01-01
16INR0102 | Pecos | Solar | 130 | 2018-01-01
16INR0101 | Pecos | Solar | 57 | 2018-01-01
14INR0033 | Armstrong | Wind | 500 | 2018-03-28
16INR0023b | Dawson | Solar | 98 | 2018-03-31
12INR0018 | Gray | Wind | 500 | 2018-03-31
17INR0045 | Victoria | Gas | 100 | 2018-04-01
15INR0063b | Castro | Wind | 101 | 2018-04-18
15INR0057 | Wharton | Gas | 142 | 2018-05-01
15INR0055 | Austin | Gas | 142 | 2018-05-01
18INR0025 | Lynn | Wind | 506 | 2018-05-01
15INR0062b | Hale | Wind | 122 | 2018-05-15
18INR0033 | Irion | Wind | 301 | 2018-06-01
18INR0013 | Denton | Gas | 224 | 2018-06-01
17INR0048 | Harris | Gas | 149 | 2018-06-01
12INR0055 | Baylor | Wind | 80 | 2018-06-01
16INR0045 | Henderson | Gas | 450 | 2018-06-01
13INR0010c | Parmer | Wind | 230 | 2018-06-01
13INR0010a | Parmer | Wind | 139 | 2018-06-01
13INR0026 | Oldham | Wind | 201 | 2018-06-29
17INR0024 | Nolan | Gas | 350 | 2018-06-30
16INR0036 | Nolan | Gas | 280 | 2018-06-30
18INR0059 | Willacy | Wind | 201 | 2018-07-01
18INR0018 | Matagorda | Wind | 150 | 2018-07-01
14INR0011 | Swisher | Storage | 270 | 2018-07-01
18INR0045 | Childress | Solar | 241 | 2018-09-01
18INR0029 | Armstrong | Wind | 278 | 2018-09-01
17INR0027b | Scurry | Wind | 250 | 2018-09-01
15INR0064b | Glasscock | Wind | 129 | 2018-09-01
18INR0042 | Callahan | Wind | 100 | 2018-10-01
18INR0027 | Upton | Solar | 150 | 2018-10-01
13INR0056b | Scurry | Wind | 152 | 2018-10-01
18INR0004 | Hill | Gas | 928 | 2018-10-01
17INR0020a | Pecos | Solar | 100 | 2018-10-01
15INR0050 | Deaf Smith | Wind | 203 | 2018-10-01
13INR0010def | Parmer | Wind | 600 | 2018-10-01
18INR0022 | Winkler | Solar | 150 | 2018-10-31
17INR0025 | Zapata | Wind | 202 | 2018-10-31
18INR0039 | Crane | Solar | 300 | 2018-12-01
15INR0072 | Pecos | Solar | 140 | 2018-12-01
15INR0034 | San Patricio | Wind | 201 | 2018-12-01
18INR0051 | Clay | Wind | 200 | 2018-12-31
18INR0023 | Menard | Wind | 250 | 2018-12-31
18INR0016 | McCulloch | Wind | 150 | 2018-12-31
18INR0014 | San Patricio | Wind | 200 | 2018-12-31
17INR0037 | Cameron | Wind | 145 | 2018-12-31
17INR0030 | Deaf Smith | Solar | 100 | 2018-12-31
16INR0119 | Crosby | Solar | 150 | 2018-12-31
16INR0106 | Andrews | Solar | 150 | 2018-12-31
16INR0104 | Crockett | Wind | 400 | 2018-12-31
16INR0085 | Mills | Wind | 300 | 2018-12-31
15INR0090 | Travis | Solar | 120 | 2018-12-31
15INR0081 | Mason | Wind | 62 | 2018-12-31
15INR0035 | Kenedy | Wind | 200 | 2018-12-31
13INR0025 | Randall | Wind | 150 | 2018-12-31
13INR0045 | Castro | Wind | 288 | 2018-12-31
10INR0009 | Castro | Wind | 300 | 2018-12-31
15INR0059 | Pecos | Solar | 108 | 2019-01-01
16INR0037c | Floyd | Wind | 280 | 2019-01-15
19INR0020c | Pecos | Solar | 180 | 2019-03-01
19INR0020b | Pecos | Solar | 180 | 2019-03-01
19INR0020 | Pecos | Solar | 180 | 2019-03-01
14INR0009 | Kent | Wind | 248 | 2019-03-29
17INR0013 | Hill | Gas | 800 | 2019-04-01
16INR0010 | Mitchell | Gas | 745 | 2019-04-05
19INR0001 | Kent | Solar | 750 | 2019-05-01
17INR0020b | Pecos | Solar | 200 | 2019-05-16
17INR0002 | Henderson | Gas | 478 | 2019-06-01
19INR0019 | Foard | Wind | 350 | 2019-06-30
19INR0009 | Nolan | Solar | 180 | 2019-07-01
18INR0009 | Cherokee | Gas | 1156 | 2019-08-01
17INR0010 | Mitchell | Gas | 799 | 2019-09-15
19INR0004 | Deaf Smith | Solar | 400 | 2019-10-01
19INR0002 | Upton | Solar | 350 | 2019-12-01
17INR0020c | Pecos | Solar | 100 | 2020-01-01
20INR0003 | Childress | Solar | 200 | 2020-03-01
16INR0006 | Angelina | Gas | 785 | 2020-04-12
20INR0002 | Castro | Solar | 360 | 2020-06-01
17INR0020d | Pecos | Solar | 100 | 2020-07-15
20INR0005 | Childress | Solar | 200 | 2020-10-01
18INR0005 | Grayson | Gas | 543 | 2020-12-01

## Wind Chart
INR | ProjectName | County | Status | Projected Date | IA Signed | Fuel | TypeCode | MWForGrid | Year
14INR0062 | Salt Fork 1 Wind | Gray | PLANNED | 2017-01-30 | 2014-08-27 | WIND | WT | 174 | 2017
15INR0085 | Tyler Bluff Wind | Cooke | PLANNED | 2017-01-30 | 2015-06-18 | WIND | WT | 126 | 2017
13INR0010b | Mariah Del Norte | Parmer | PLANNED | 2017-02-03 | 2013-01-31 | WIND | WT | 230 | 2017
16INR0037 | Cotton Plains Wind | Floyd | PLANNED | 2017-02-05 | 2015-08-03 | WIND | WT | 50 | 2017
16INR0037b | Old Settler Wind | Floyd | PLANNED | 2017-02-05 | 2015-08-03 | WIND | WT | 150 | 2017
14INR0013 | San Roman Wind 1 | Cameron | PLANNED | 2017-02-16 | 2014-12-19 | WIND | WT | 94 | 2017
15INR0074 | Falvez Astra W | Deaf Smith | PLANNED | 2017-05-04 | 2016-08-18 | WIND | WT | 163 | 2017
16INR0055 | Chapman Ranch Wind I | Nueces | PLANNED | 2017-05-31 | 2015-07-16 | WIND | WT | 250 | 2017
11INR0054 | Midway Wind | San Patricio | PLANNED | 2017-08-01 | 2012-09-24 | WIND | WT | 161 | 2017
16INR0082 | Salt Fork 2 Wind | Carson | PLANNED | 2017-08-01 | 2015-08-18 | WIND | WT | 200 | 2017
11INR0062 | Patriot Wind | Nueces | PLANNED | 2017-08-15 | 2016-10-13 | WIND | WT | 180 | 2017
11INR0082a | Val Verde Wind | Val Verde | PLANNED | 2017-08-31 | 2015-08-12 | WIND | WT | 149 | 2017
17INR0027 | Dermott Wind 1 | Scurry | PLANNED | 2017-09-01 | 2016-08-09 | WIND | WT | 250 | 2017
15INR0064 | BearKat Wind A | Glasscock | PLANNED | 2017-09-15 | 2016-12-20 | WIND | WT | 197 | 2017
14INR0060b | Willow Springs Wind | Haskell | PLANNED | 2017-10-01 | 2015-05-01 | WIND | WT | 230 | 2017
16INR0062b | Lockett Wind Farm | Wilbarger | PLANNED | 2017-10-01 | 2015-03-31 | WIND | WT | 184 | 2017
13INR0056 | Fluvanna Renewable 1 | Scurry | PLANNED | 2017-10-17 | 2015-09-24 | WIND | WT | 155 | 2017
12INR0002a | Silver Canyon Wind A | Briscoe | PLANNED | 2017-10-31 | 2016-06-22 | WIND | WT | 200 | 2017
16INR0087 | RTS Wind | McCulloch | PLANNED | 2017-10-31 | 2015-10-14 | WIND | WT | 160 | 2017
14INR0057 | Buckthorn Wind 1 | Erath | PLANNED | 2017-11-01 | 2015-09-10 | WIND | WT | 96 | 2017
15INR0082 | Flat Top Wind I | Comanche | PLANNED | 2017-11-30 | 2016-02-19 | WIND | WT | 200 | 2017
12INR0060 | Infinity Live Oak Wind | Schleicher | PLANNED | 2017-12-01 | 2016-11-03 | WIND | WT | 201 | 2017
14INR0041a | Bruenning's Breeze | Willacy | PLANNED | 2017-12-01 | 2015-08-12 | WIND | WT | 228 | 2017
16INR0121 | Salt Fork Wind Expansion | Carson | PLANNED | 2017-12-01 | 2016-06-28 | WIND | WT | 54 | 2017
13INR0005c | Grandview W 3 | Carson | PLANNED | 2017-12-15 | 2014-04-23 | WIND | WT | 188 | 2017
13INR0038 | Swisher Wind | Swisher | PLANNED | 2017-12-15 | 2015-09-06 | WIND | WT | 300 | 2017
14INR0023b | Longhorn South | Briscoe | PLANNED | 2017-12-15 | 2012-12-10 | WIND | WT | 160 | 2017
14INR0030c | Panhandle Wind 3 | Carson | PLANNED | 2017-12-30 | 2014-08-25 | WIND | WT | 248 | 2017
14INR0045a | Torrecillas Wind A | Webb | PLANNED | 2017-12-31 | 2015-01-30 | WIND | WT | 200 | 2017
14INR0045b | Torrecillas Wind B | Webb | PLANNED | 2017-12-31 | 2015-01-30 | WIND | WT | 200 | 2017
15INR0049 | Javelina 2 Wind | Zapata | PLANNED | 2017-12-31 | 2015-12-30 | WIND | WT | 200 | 2017
16INR0091 | Santa Rita Wind | Reagan | PLANNED | 2017-12-31 | 2017-01-03 | WIND | WT | 300 | 2017
14INR0033 | Goodnight Wind | Armstrong | PLANNED | 2018-03-28 | 2016-08-09 | WIND | WT | 500 | 2018
12INR0018 | Pampa Wind | Gray | PLANNED | 2018-03-31 | 2013-11-12 | WIND | WT | 500 | 2018
13INR0010a | Mariah Del Este | Parmer | PLANNED | 2018-06-01 | 2013-01-31 | WIND | WT | 139 | 2018
13INR0010c | Mariah Del Sur | Parmer | PLANNED | 2018-06-01 | 2013-01-31 | WIND | WT | 230 | 2018
13INR0026 | Canadian Breaks Wind | Oldham | PLANNED | 2018-06-29 | 2016-05-20 | WIND | WT | 201 | 2018
16INR0074 | Chocolate Bayou | Brazoria | PLANNED | 2018-06-30 | 2016-08-05 | WIND | WT | 150 | 2018
15INR0064b | BearKat Wind B | Glasscock | PLANNED | 2018-09-01 | 2016-12-20 | WIND | WT | 129 | 2018
17INR0027b | Coyote Wind | Scurry | PLANNED | 2018-09-01 | 2016-08-09 | WIND | WT | 250 | 2018
13INR0010def | Scandia Wind DEF | Parmer | PLANNED | 2018-10-01 | 2014-04-25 | WIND | WT | 600 | 2018
15INR0050 | Unity Wind | Deaf Smith | PLANNED | 2018-10-01 | 2014-10-03 | WIND | WT | 203 | 2018
15INR0079 | Pullman Road | Randall | PLANNED | 2018-10-31 | 2014-05-29 | WIND | WT | 300 | 2018
10INR0009 | Caprock Wind | Castro | PLANNED | 2018-12-31 | 2014-10-31 | WIND | WT | 300 | 2018
12INR0029 | Comanche Run Wind | Swisher | PLANNED | 2018-12-31 | 2013-07-24 | WIND | WT | 500 | 2018
13INR0045 | Changing Winds | Castro | PLANNED | 2018-12-31 | 2015-02-27 | WIND | WT | 288 | 2018
16INR0037c | Pumpkin Farm Wind | Floyd | PLANNED | 2019-01-15 | 2016-02-26 | WIND | WT | 280 | 2019
13INR0020b | Rattlesnake W 2 | Glasscock | PLANNED | 2020-05-06 | 2013-06-28 | WIND | WT | 158 | 2020

## Solar Chart
INR | ProjectName | County | Status | Projected Date | IA Signed | Fuel | TypeCode | MWForGrid | Year
15INR0070_1 | West Texas Solar | Pecos | PLANNED | 2017-02-01 | 2014-12-17 | SOLAR | PV | 110 | 2017
12INR0059b | Barilla Solar 1B | Pecos | PLANNED | 2017-02-06 | 2013-12-26 | SOLAR | PV | 7 | 2017
16INR0073 | East Pecos Solar | Pecos | PLANNED | 2017-03-01 | 2015-03-06 | SOLAR | PV | 120 | 2017
15INR0061 | SolaireHolman 1 | Brewster | PLANNED | 2017-03-31 | 2015-11-10 | SOLAR | PV | 50 | 2017
16INR0023 | BNB Lamesa Solar (Phase I) | Dawson | PLANNED | 2017-03-31 | 2016-07-28 | SOLAR | PV | 102 | 2017
15INR0070_1b | Pearl Solar | Pecos | PLANNED | 2017-04-28 | 2014-12-17 | SOLAR | PV | 50 | 2017
16INR0065b | SP-TX-12-Phase B | Upton | PLANNED | 2017-08-15 | 2015-10-29 | SOLAR | PV | 120 | 2017
16INR0049 | Nazareth Solar | Castro | PLANNED | 2017-10-01 | 2015-05-15 | SOLAR | PV | 201 | 2017
16INR0019 | Capricorn Ridge Solar | Coke | PLANNED | 2017-12-01 | 2015-08-19 | SOLAR | PV | 100 | 2017
15INR0045 | Riggins Solar | Pecos | PLANNED | 2017-12-22 | 2015-01-26 | SOLAR | PV | 150 | 2017
12INR0059c | Barilla Solar 2 | Pecos | PLANNED | 2017-12-31 | 2013-12-26 | SOLAR | PV | 21 | 2017
16INR0023b | Lamesa Solar B (Phase II) | Dawson | PLANNED | 2018-03-31 | 2015-06-25 | SOLAR | PV | 98 | 2018
17INR0020a | RE Maplewood 2a Solar | Pecos | PLANNED | 2018-10-01 | 2016-02-03 | SOLAR | PV | 100 | 2018
16INR0114 | Upton Solar | Upton | PLANNED | 2018-12-01 | 2015-12-04 | SOLAR | PV | 102 | 2018
15INR0059 | Pecos Solar I | Pecos | PLANNED | 2019-01-01 | 2015-06-09 | SOLAR | PV | 108 | 2019
16INR0065 | Castle Gap Solar | Upton | PLANNED | 2019-01-01 | 2015-09-04 | SOLAR | PV | 150 | 2019
17INR0020b | RE Maplewood 2b Solar | Pecos | PLANNED | 2019-05-16 | 2016-02-03 | SOLAR | PV | 200 | 2019
16INR0065a | Castle Gap Solar 2 | Upton | PLANNED | 2020-01-01 | 2015-09-04 | SOLAR | PV | 30 | 2020
17INR0020c | RE Maplewood 2c Solar | Pecos | PLANNED | 2020-01-01 | 2016-02-03 | SOLAR | PV | 100 | 2020
17INR0020d | RE Maplewood 2d Solar | Pecos | PLANNED | 2020-07-15 | 2016-02-03 | SOLAR | PV | 100 | 2020

## Project Count Chart
Note on CD15: Katheiser, Jenell: Frontera Chillers 5/17/2013
Note on CE15: Katheiser, Jenell: WA Parish Addition, Bryan Solar
Note on CF15: Murray, Douglas: Sandy Creek
Note on CH15: Murray, Douglas: Los vientos