| NPRR Number | 808 | NPRR Title | Three Year CRR Auction |
| --- | --- | --- | --- |
| Impact Analysis Date |  | February 8, 2017 |  |
| Estimated Cost/Budgetary Impact |  | Between $40k and $50k Annual Recurring Operations and Maintenance (O&M) Budget Cost: $130k – $140k (See ERCOT Staffing Impacts) |  |
| Estimated Time Requirements |  | The timeline for implementing this Nodal Protocol Revision Request (NPRR) is dependent upon ERCOT Board prioritization and approval. Please see the Project Priority List (PPL) for additional information. Estimated project duration: 3 to 4 months |  |
| ERCOT Staffing Impacts (across all areas) |  | There will be ongoing operational impacts across the following ERCOT department totaling 0.5 Full-Time Employees (FTE) to support this NPRR: - Market Operations (0.5 FTE) ERCOT has assessed its ability to absorb the ongoing efforts of this NPRR with current staff and concluded the need for one (1) additional FTE: - Market Operations - department requires one (1) additional FTE to support the effort which includes adding four long term auction sequences annually: - 100 hours for building models, input files, and model verification times four auctions annually = 400 hours - 120 hours for building additional allocation models and executing allocations once annually = 120 hours - 15 hours for outage selection and GTC evaluation times four auctions annually = 60 hours - 60 hours for posting model and reports, preparing and executing auctions, auction verifications, posting results times four auctions annually = 240 hours |  |
| ERCOT Computer System Impacts |  | The following ERCOT systems would be impacted: - Credit Monitoring and Management (CMM) |  |
| ERCOT Business Function Impacts |  | ERCOT will update its business processes to implement this NPRR. |  |
| Grid Operations & Practices Impacts |  | No impacts to ERCOT grid operations and practices. |  |

Alternatives for a More Efficient Implementation (include explanation of impacts)

None offered.

Evaluation of Interim Solutions (e.g., manual workarounds)

None offered.

Feasibility of Implementation

Impact on Resource Availability: Not applicable. Impact on Other Projects: The implementation of NPRR808 may have potential impacts to the PR183 CMM Tech Refresh project. ERCOT is currently evaluating whether the target Q2 2018 implementation date would be delayed if NPRR808 is prioritized ahead of the CMM Tech Refresh.

Comments

None.