## Sheet1
TX SET Meeting Notes / Action Items
2017-02-21
Agenda Item: | Decision / Resolution | Action Items :
January 2016 Meeting Notes | Minor changes were made to the notes. | The Texas SET Chair will submit the notes to ERCOT for posting.
RMS Updates
NPRR796, Extended Character Set Clean Up | RMS agreed to leave tabled pending updates to Change Control 2017-805.
144RMGRR-01 Elimination of REP-Specific Switch Hold Lists 121316 | RMS approved the Impact Analysis (IA).
145RMGRR-01 Appendix for a Mass Customer List (MCL) 010617 | RMS approved the initial langauge.
Flight Update | ERCOT Staff presented the 0217 flight update.
Update all Scripts to replace “MCTDSP” with “MOU/EC TDSP” | The ERCOT Flight Administrator reviewed the changes made to the scripts. Texas SET agreed to all the changes. | The ERCOT Flight Administrator will post the updated scripts to the ERCOT website. https://etod.ercot.com/flightscenarios.asp?M=List&FlightNum=V4.0F15. Select Download All Scripts on the top right of the screen.
Update on Sharyland Utilities combined Tariff testing requirements expected for exisiting CRs that are certified in one of the Sharyland territories, but not the other. | Texas SET agreed that the penny test and connectivity test might be the only scripts required, but requested that Sharyland investigate internally what those testing requirements will be. | Sharyland to update Texas SET on the testing requirments at the March 21st meeting.
Change Control Call--10:00 AM
Mass Transition/Default-POLR Rule | • RMS assignment to discuss Mass Transition— Possible POLR Rule change from two days out to one day out.
AMWG Update
Other discussion
Market Test Flight 0214 Update | ERCOT to provide flight update No update received
TX SET Procedures | On Hold-Discuss reline changes sent to the TXSET listserv for review | Leave current issue process in tact and continue to review document to identify where additional process improvements can be made
2017-805, Update all the TX SET Implementation Guides to allow the receiver of the transaction containing Special Characters to determine to either accept the transaction or to respond with a valid rejection. | Texas SET membership reached consensus on the language changes and will review recommend that RMS approve the changes at the March 28th meeting. | ERCOT will post the updated Change Controls to the ERCOT Website. http://www.ercot.com/mktrules/issues/txsetcc
2017-806, Update all the TX SET Implementation Guides to replace “MCTDSP” with “MOU/EC TDSP” | Texas SET membership reached consensus on the language changes and will review recommend that RMS approve the changes at the March 28th meeting. | ERCOT will post the updated Change Controls to the ERCOT Website. http://www.ercot.com/mktrules/issues/txsetcc
Discussion Items
796NPRR-05_ERCOT_Comments_121416, Extended Character Set Clean Up. • 2016-I143, Validation processes when a character is included in the customer name on a switch or MVI transaction – Review ERCOT Options; provide feedback • Option 1: Continue With Existing Manual Workaround—Short Term • Option 2: Update ERCOT’s Systems to Reject Any Transaction Containing Special Language Characters—Long Term • Option 3: Update ERCOT’s Systems to Translate Special Language Characters into Normal Characters • Option 4: Implement Option 3 in the Short Term, Followed by Option 2 During the Next TX SET Release | Texas SET agreed to request RMS to move forward on this NPRR at the March 28th RMS meeting.
Update all Swimlanes to replace “MCTDSP” with “MOU/EC TDSP” | Texas SET reviewed and agreed to all the changes to the Swimlanes. | ERCOT will post the updated Swimlanes to the ERCOT Website. http://www.ercot.com/mktrules/guides/txset/sw
Update Transaction_Names_Inventory_V4_0_02022017 to replace “MCTDSP” with “MOU/EC TDSP” | Texas SET reviewed and agreed to all the changes to the transaction names inventory document. | ERCOT will post the updated Swimlanes to the ERCOT Website. http://www.ercot.com/mktrules/guides/txset
Draft RMGRR - Stand-alone Discretionary Meter Tampering Charges | Texas SET reviewed the changes and reached consensus on the language. | The Texas SET Chair will submit the change to the Revision Request email and request that RMS approve the RMGRR at their March 28th meeting.
CNP Method for grouping SAC segments under the SLN loops within their 810_02 TDSP Invoice transactions. | 1. CNP would like to make a change to the way they group the Guardlight / Streetlight SAC segments under the SLN loops within the 810_02 TDSP Invoice. CNP provided examples at the meeting for review. 2. CenterPoint Energy would like the Competitive Retailer (CR) community to determine if these proposed changes would create any negative impacts in their systems or create an inability for CRs to invoice their Customers for these services. | 1. CNP will send examples to the TX SET Chair to provide to the TX SET membership. 2. CR's are to return with feedback related to any impacts of such a change at the March meeting.
Mass Transition/Default-POLR Rule | • RMS assignment to discuss Mass Transition— Possible POLR Rule change from two days out to one day out.
AMWG Update
Other discussion
Market Test Flight 0214 Update | ERCOT to provide flight update No update received
TX SET Procedures | On Hold-Discuss reline changes sent to the TXSET listserv for review | Leave current issue process in tact and continue to review document to identify where additional process improvements can be made
Issues
2017-I144, Guard Light Type replacement / New MVI, Same Customer | 1. Texas SET reviewed the issue and agreed that several TDSP's systems will only handle one rate class on a single ESI ID at a time. One TDSP's system will allow more than one rate class per ESI ID. | 1. The Submitter agreed to consider the issue closed.
2017-I145, Standardization of all 820_02’s received from CRs and their Banks | 1. TX SET discussed the issue and agreed that the Implementation Guides were clear without any changes. 2. Examples may be added to clarify the banking transaction requirements. 3. CRs to investigate internally and return to the March meeting with feedback. | 1. The Texas SET Chair will provide the information at the March 28th RMS meeting. 2. CNP volunteered to provide examples for Texas SET to review at the March 21st meeting.
2017_I146, Discuss the timing around 814_PCs where the Customer name is present, but the telephone is not. | 1. NRG questioned if we need the phone at the same time as the Customer Name. If not, do we need to remove the requirement from the PER~IC for a phone. 2. TDSPs stated that they would like to see the two (Name and Phone) remain tied together. 3. NRG agreed to consider the issue closed.
2017_I147, Original, cancel, and replacement transactions are being handled differently between TDSPs which is causing exceptions for the CR | TX SET discussed and requested that NRG submit examples to the TDSPs where the 00 code as opposed to the 05 code is received in a replacement that has been changed to a final bill. | NRG to send examples to any TDSP that has sent their transactions this way. TDSP feedback will be provided at the March meeting.
RMS assignments:
New Entrant Documentation—Procedures and Documentation Location Continue New Entrant Outline Document Review and Update As Needed | This items is delayed until the March 21st meeting.
RMG Safety NET Timelines Notes: PUCT to Review Final Draft Prior to TX SET Submitting Changes to RMS Discuss any updates offered from CRs | 1. The CRs provided a brief update up internal discussions. 2. Texas SET will begin looking at language changes to the Retail Market Guide at the March 21st Texas SET meeting. | The Texas SET Chair will send the changes made at the March 23, 2016 meeting to the Texas SET Vice Chair.
Safety-net Spreadsheet Format | 1. Texas SET agreed that the column headings in the Retail Market Guide, Section 9, Appendices, Appendix A1, Competitive Retailer Safety Net Request needs to match the Field Names in the Retail Market Guide, Section 7.4.1.4 Standard and Priority Safety-Net Procedures, table 4b, Safety-Net Spreadsheet Format. 2. AEP volunteered to update the appendix.
Parking Lot
TX SET Release Discussion | On Hold
REP Certification Matrix—Long-term solution | On Hold
Next Meeting--ERCOT MET Center | March 21, 2017 RM 168
Attendees F-T-F
Diana Rehfeldt TNMP | Lindsay Butterfield ERCOT | Rebecca Zerwas NRG
Paul Yockey ERCOT | Kaci Jacobs TXU | Monica Jones NRG
Michael Glass SU | Monsherra Odanga ONCOR
Kathryn Thurman ERCOT | Sam Pak ONCOR
Kyle Patrick NRG | Kathy Scott CNP
Jim Lee AEP | Carolyn Reed CNP
Attendees Webex
Becky Taylor CNP | Stephen Wilson SU
Brent Hurta Austin Energy | Deborah Croce ECInfoSystems
Christy Dvorak Infinite Energy
Deb Belin Aurea
Jasmone Thom CES
Yana Long Infinite Energy
Jennifer Vigil