## Timeline 2017
Date Completed
Due Date* | 2017 Residential Annual Validation Task List | ERCOT | AEP | CNP | ONCOR | SHRY McAllen | SHRY | TNMP | Nueces
2017-04-01 | ERCOT to provide list of ESI IDs to TDSPs
2017-04-10 | TDSPs to provide finalized list of ESI IDs to ERCOT
2017-04-15 | Market Notice announcing lists are available to CR of record
2017-04-15 | TDSPs to begin submitting 814_20 transactions
2017-09-30 | TDSPs to complete submissions of all 814_20 transactions
2017-10-02 | ERCOT completes review of expected database changes
Due Date* | 2017 Business Annual Validation Task List
2017-04-01 | ERCOT to provide list of ESI IDs to TDSPs
2017-04-01 | ERCOT Provides Qtr Validation Lists to TDSPs (BUS Only)
2017-04-10 | TDSPs to provide finalized list of ESI IDs to ERCOT
2017-04-15 | Market Notice announcing lists are available to CR of record
2017-04-15 | TDSPs to begin submitting 814_20 transactions
2017-09-30 | TDSPs to complete submissions of all 814_20 transactions
2016-09-30 | Complete Quarterly Validations
2017-10-02 | ERCOT to review database for expected changes |  | MT | MT | MT | MT | MT | MT | MT
2017-10-02 | All TDSPs have submitted at least 99% of changes
2016-11-02 | Initial Weather Responsiveness Report Produced
2016-01-02 | Weather Responsiveness Overdue Report Produced
Monthly | Continue Overdue Reporting Until All Complete
* If the date falls on a weekend or holiday, please use the following business day as deadline. | [8 empty] | Update:6/29/2016