## Slide 1: Planning Geomagnetic Disturbance Task Force (PGDTF) Update to the ROS
April 6, 2017
Omar Urquidez
PGDTF Chairman
<number>
4/6/2017 ROS Meeting

## Slide 2: Activities of the PGDTF in March
PLWG reviewed 057PGRR Impact Analysis (R1)
Met on March 16, 2017
  GIC model known submission errors and a plan for model validation
  Discussed PGDTF 2017 Goals
  Began discussion on Assessment/Model (TPL-007-1 R2) building timeline and Vulnerability Assessment (TPL-007-1 R4) Scope/Criteria (TPL-007-1 R3)
  Discussed National and State Activities Related to GMD.
    NERC GMD SDT new language for TPL-007-1 including magnetometer data requirements and additional enhanced vulnerability assessment
Established PGDTF Contact List for improved communication and collaboration
PGDTF will meet April 26th
Omar Urquidez – 4/6/2017 ROS Meeting
<number>

## Slide 3: 2017 PGDTF Goals
R1 PGRR Approval
  Target: Board Approval at June Meeting
  NERC Deadline July 1, 2017
PGDTF Contact List
GIC Model Completion & Review
Assessment/Model Building Timeline Recommendation
Vulnerability Assessment Scope/Criteria Recommendation
Procedure Manual Update
Corrective Action Plan development and “approval” process Recommendation
Omar Urquidez – 4/6/2017 ROS Meeting
***Current Active Items

## Slide 4: Schedule for Creating GIC System Model
12/31/2016 – TSP Data for 345 kV System Based on 2021 Summer Peak Case Released on 10/15/2016 Provided to ERCOT. Complete
3/31/2017 – TSP Data for 138 kV and 69 kV Systems and Update to 345 kV System Data Based on 2021 Summer Peak Case Released on 10/15/2016 Due to ERCOT. Complete
6/30/2017 – REs’ Updated RARF with GIC System Model Data Due to ERCOT. Delayed…
6/1/2017 – ERCOT Provides First Pass of GIC System Model for Review to TSPs and REs. Delayed…
7/1/2017 – TSPs and REs Provide GIC Model Changes to ERCOT. Delayed…
Subsequent Model Review Passes Will be Scheduled as Needed.
1/1/2018 – Complete 2021 Summer Peak and 2021 Minimum GIC System Models Using July 2017 SSWG 2021 Summer Peak and 2021 Minimum Base Cases. Possible Delay- NERC Deadline 7/1/2018
Omar Urquidez – 4/6/2017 ROS Meeting
<number>

## Slide 5: Questions and Answers
<number>
Omar Urquidez – 4/6/2017 ROS Meeting