## 2017
PLWG Issues List - 2017
Issue# | Date Entered | From Meeting | Status | Type of issue | Individual Issues | Key Concerns | Leader | Target Date | Resolution
1 |  |  | Closed | Data Collection |  | Initial implementation will retain SSWG/DWG/SPWG reporting to ROS; PLWG might oversee transition to more reporting-based procedure when systems are ready. |  |  | Completed. On 10/28/11, the PLWG was in consensus that there is value in the individual groups and recommends that SSWG, DWG, SPWG continue to report to ROS.
2a |  |  | Closed | Data Consistency | Is there need for an ERCOT coincident Peak Case? | PLWG should consider consistency in load forecast, load coincidence in cases/studies |  |  | PGRR011
2b |  |  | Closed | Market Transperancy | Should each utilities' rating methodology be available for market review? |  |  |  | Section 3.10 (3) of Protocols Updated 09/30/11: Complete.
3 |  |  | Closed | Validation of data accuracy and consistency |  | Each individual data item should be the responsibility of the entity that provided it. Should there be a “check” by TSP, GE or ERCOT of whether the submitted data “makes sense”? Who is responsible (accountable) for checking the modeling of the data (e.g. how the data is converted to bus/branch modeling)? |  |  | Luminant to show case errors from most recent Dataset to ERCOT and owner to explore if there is a validation method that may catch this.
4 |  |  | Closed | Validation of data accuracy and consistency |  | Is the accuracy of the consolidated dataset the responsibility of an entity (ERCOT, TSP, GE) or a group (SSWG/DWG, PLWG)? Is providing valid data part of Protocol auditing process? |  |  | Luminant to show case errors from most recent Dataset to ERCOT and owner to explore if there is a validation method that may catch this.
5 |  |  | Closed | RARF Interface |  | How to allow for corrections submitted by non generation entities. How to revise RARF to meet revised input requirements. Tuning of data used in models (e.g., stability data). Maybe could be included in ERCOT effort to get contractor to work on "total" data process. | Mike (Oncor) |  | On 10/28/11 the PLWG was in consensus that the issue was addressed thru the RARF workshop,except for the need for a process for ERCOT to extract updated information from the RARF and post as interim update to case (idev/PMCR).
6 |  |  | Closed | RPG Interface |  | Refine different focus between the two groups (with PLWG)
7 |  |  | Closed | Information sections of current procedures |  | some TSPs have taken the description of how these ratings are developed out of SSWG procedures and made those descriptions available on demand |  |  | Updated 09/30/11: Complete. Section 3.10 of Protocols
8 |  |  | Closed | Transmission Line System Design |  | a. One argument is that this is an engineering issue, not a planning issue, because it is specific for each design. b. May be some key data that would be useful for market participants. C. If routing has reliability implications (such as paralleling existing lines) may want to include in ERCOT planning activities. Review process for evaluating the contingency of multiple lines in common corridor during the early planning process. | Dan W. (ERCOT) |  | Include that in RPG review process to consider potential common or adjacent ROW
9 |  |  | Closed | Scope of PLWG in specifying parameters |  | PLWG will not review/approve specific projects; may specify level of detail in recommendations (e.g. whether recommendations should include required ampacity in addition to the conductor type assumed in study) through Planning Guides Revisions |  |  | Updated 09/30/11: Complete - PLWG charter was revisisted summer 2011 and duties and responsibilities established.
10 |  |  | Closed | Level of approval for changes |  | Need to consider whether all detailed elements of what is being considered for inclusion in the Planning Guides needs to go to Board for approval or whether there should still be “procedures” that only go to TAC for approval {things like changes to TPIT dates, which cases are built may not need to go to Board) |  |  | Updated 09/30/11: Complete - structure of guide and procedures has been further defined.
11 |  |  | Closed | RPG Scope document |  | RPG may need to develop new “Scope” document to describe what that group does (2-3 pages level of detail) Use 1.2 of Planning Charter as basis. | Dan Woodfin
12 |  |  | Closed | Developing criteria |  | Criteria may need to be developed in a way that is appropriately flexible where that makes sense (non-coincident area loads, e.g.) |  |  | Updated 09/30/11: PGRR05 and PGRR-011 will address this.
13 |  |  | Closed | Update ROS scope: Review of planning studies |  | May need to update ROS scope relative to review of planning studies
14 |  |  | Closed | New technologies |  | Facilitate investigation / implementation of new technologies (where appropriate) for improving the reliability of the electrical system (synchrophasor locations). Current effort is not ERCOT. What should ERCOT, collectively, be doing to implement synchorphasor technology?
15 |  |  | Closed | Congestion Analysis | Develop cases that more closely reflect conditions typically seen in real life | Create UPLAN cases that model normally occurring stressful load conditions such as high transfer conditions and 90th percentile load expectations.
16a |  |  | Closed | Economic Evaluation | 16A. The current UPLAN case assumptions disregard high impact conditions that regularly occur in real life, causing significant congestion costs | Refine economic criteria to include project proposal cost/benefit associated with: 1) transmission maintenance outages 2) transmission forced outages.
16b |  |  | Closed | Economic Evaluation | 16B Revisit the economic Planning Criteria as discussed at the BOD meeting Is probalistic economic planning needed? | The Houston Import Project recently approved by the BOD was the first ERCOT project approved using the Consumer Benefit criteria. Discussions during the approval process through TAC and BOD suggest that it's appropriate for the PLWG to revisit the economic evaluation process of proposed transmission projects. |  |  | Updated 09/30/11: Currently a project at the Commssion.
17 |  |  | Closed | Open Planning Model |  | Require the posting of the full UPLAN Planning Model that is utilized by ERCOT to perform their study case | Dan Woodfin
18 |  |  | Closed | Definitions/Acronyms |  | Pull Acronyms and Definitions to the front and decide at a later date. |  |  | Updated 09/30/11: Complete - Definiton and Acronyms are now in section 2 of the planning guide.
19 |  |  | Closed | Chronic Congestion |  |  |  |  | Updated 09/30/11: Ongoing - NPRR-393. 11/28/2011: This NPRR requires ERCOT to report SCED Irresolvable congestion so that the market has insights, and TSPs can determine if the congestion warrants a project. Additionally, if SCED Irr congestion is determined to be related to an ERCOT approved clearance, ERCOT will review its study method to see if this can be caught in future clearance studies. Sergio to find old language where this used to be.
20 |  |  | Closed | Interconnection Import -Export Evaluation | 1) Should ERCOT be performing economic RAPS, PCAPS etc and if so what should the criteria be. |  | Dan Woodfin |  | Updated 09/30/11: Tie interconncetion procedure produced by ERCOT. Needs to be placed in Planning Gudie.
21 |  |  | Closed |  | 1) Adding white paper on how to analyze asynchronus ties to the Planning Guides
22 |  |  | Closed | Introduction of generation in SSWG cases | What type of commitment must be made by generator proposers before their generator is modeled in the SSWG case | Some generators have gone through the SGIA process and the generator was placed in the SSWG case, just to find out that the generator cancelled the project. This can cause deficient transmission planning in areas where the generator was once expected. | Wayne Kemper |  | Updated 09/30/11: Maybe addressed in PGRR 003? Updated 01/26/12: Maybe addressed in PGRR 015. 12/2012 Update - PGRR 018 addresses this issue
23 |  |  | Closed | Stability of study assumptions that justify major transmission projects | What weight should long term considerations have on the planning of major projects? | Give long-term considerations to appropriately apply cost/benefit and reliability aspects of major transmission lines. |  |  | Updated 09/30/11: Potentially use results of LTSA to assess benefit of longer than five year assessment. Complete assessment of longer term horizon. 11/28/11: 7-year out case will help. Also, study several different assumptions to help ensure that most reasonable outcomes are studied. Examples: Fayetteville - Zenith studied gas & generation build scenarios: Hutto - Clear Springs looked at numerous potential non-related transmission projects as well as several small projects versus a big project. Related to item 8 (dan W)
24 | 2011-08-16 | 2011-04-29 | Closed | Interruptible Load | Interruptible load may not be appropriate to consider as a solution to fixing a system problem |  |  |  | Updated 09/30/11: No interruptible in the ERCOT market. PGRR 005(?) took care of this. Also, look in PGRR011.
25 | 2011-08-16 | 2011-04-29 | Closed | Definition of credible single contingency | Revise the definition to separate the description of the event from the performance. |  |  |  | Updated 09/30/11: PGRR011
26 | 2011-08-16 | 2011-04-29 | Closed | Mothballed Generator | Include the treatment of mothballed generation units in planning studies especially in tests associated wit short circuit.
27 | 2011-08-16 | 2011-04-29 | Closed | Severe contingencies | Add a definition of severe contingency as well as description of required performance. This is consistent with ERCOT's recommendations on parlleling 345 kV lines in CREZ.
28 | 2011-08-16 | 2011-05-26 | Closed | Review ERCOT ALDR procedure | 1)Is ERCOT issuing ALDR to appropriate entities
29 | 2011-08-16 | 2011-05-26 | Closed |  | 2)Need to address how ALDR infromation is getting into DSA and DSB(planning) cases
30 | 2011-08-16 | 2011-05-26 | Closed | Contingency Definition | Is the present category C and D needed in the planning guide in the future
31 | 2011-08-16 | 2011-05-26 | Closed | Wind Generation | Should a procedure for aggregating wind generator collector systems into the model be developed and put into the DWG procedures?
32 | 2011-08-16 | 2011-05-26 | Closed | Tap Changing | Do we need to research Operating Guide or protocol language addressing the changing of taps on GSUs after plant goes in service. |  | Mike (Oncor) |  | Updated 09/30/11: Protocol 3.10.7.1.4 (?)
33 | 2011-08-16 | 2011-07-29 | Closed | PGRR009 | Follow-up PGRR009 to address other matters. | RARF
34 | 2011-08-16 | 2011-07-29 | Closed | PGRR009 | Add “Generator Reactive” capability to issues list. This is a follow up to Centerpoint comments on PGRR009. |  |  |  | Updated 09/30/11: PGRR009 in progress that may address the noted issue.
35 | 2011-10-19 | 2011-09-01 | Closed | Generation Interconnect Procedure |  | At what point does the level of change out in wind turbines at a particular site trigger anew FIS (or should it)?
36 | 2011-11-28 |  | Closed | Simultaneous updates between SSWG, DWG & SPWG | Any change made to a case should be passed along to all 3 working groups, to ensure all participants are using the most recent case | What is the best way to ensure that all participants have access to the most recent models (i.e., case posted and then add idevs). Some companies use ASPEN, so idevs need to have a description so that it can be entered into non PSS/E programs | Peter Belkin |  | Peter will present "straw man" for discussion at the December 16 meeting.
37 | 2011-11-28 |  | Closed | Should there be a "7-year out case" of Dataset B? | Concern about the long-time line associated with major projects. | This helps the make the "need" description more robust. This helps bring LTSA identified lines into the regular planning process. | Sergio Garza |  | Will show presentation given during a TO meeting last year.12/2012 Update - PGRR 026 addresses this issue
38 | 2011-11-28 |  | Closed | What set of cases should be built? | Are the current Dataset A & B cases the most useful cases to build? | what types of base cases should be built to cover "high wind" scenario. Do we really need a Dataset B Fall1 and Fall2 case (for example)
39 | 2011-12-16 |  | Closed | Synchronize generation addition assumptions between CDR, GATF and SSWG base cases. Or are there good reasons to have differences? | Currently only an SGIA or Muni statement for inclusion, however, there may need to be more criteria. Should there be consistency between these groups? Also discuss consistency of other resources such as DC Ties, switchable units… | Future generating units with SGIA, but without financially-binding commitment, are in the CDR (& SARA), and applied to the reserve margin, and are also in the SSWG basecases, but are not on-line in the SSWG cases. |  |  | Dan W. is already working in this area. This impacts base cases (SSWG, etc) as well as GATF, and possibly other. Also consider all resource assumptions (e.g. DC Ties, switchable units, etc)
40 | 2016-02-10 | 2016-01-01 | Pending | Stability | What is the proper resolution of stability issues identified during the FIS? |  | Chad Thompson (ERCOT) |  | -Referred to PLWG by ROS -ROS Narrowed PLWG to review the Interconnection Timeline -NPRR809, PGRR052, PGRR053 and PGRR054 were created to address the issue. -Planning Guide Sections 5.4.2, 5.4.3, 5.4.5, 6.9 changed and 5.9 added
41 | 2016-02-10 | 2016-01-01 | Closed | Analysis Methodology | Load/Generation Scaling in Steady State transmission planning studies (PGRR042) |  | Jeff Billo (ERCOT) | 2016-09-01 | - Referred to PLWG by ROS - PGRR042 addressed issue
42 | 2016-02-10 | 2016-01-01 | Closed | Analysis Methodology | Generation Deliverability |  | Jeff Billo (ERCOT) |  | - Referred to PLWG by ROS. - Provided Market Participant links to past material. - Updated ROS with presentation from ERCOT recommending no additional action required. - ROS considered assignment complete.
43 | 2016-02-10 | 2016-01-01 | Closed | Analysis Methodology | Treatment of DC-Ties in Whitepaper - Ensure proper assumption about DC-Tie used in ERCOT RTP cases |  | Jeff Billo (ERCOT) |  | - ROS approved revisions to whitepaper
44 | 2016-02-10 | 2016-01-01 | Closed | Data Requirements | ERCOT ALDR request management - Ensuring stakeholder review of large annual data requests. |  | Ken Donohoo (ONCOR) |  | ROS referred to SSWG and DWG and implemented annual meeting with ALDR contact list.
45 | 2016-02-10 | 2016-01-01 | Withdrawn | Model Data | DG reporting and modeling |  | Ken Donohoo (ONCOR) |  | Already resolved through other PGRRs
46 | 2016-02-10 | 2016-01-01 | Closed | Analysis Methodology | Generation Interconnection studies consistency of analysis between TSPs |  | Ken Donohoo (ONCOR) |  | Being considered as part of issue# 40.
47 | 2016-02-10 | 2016-01-01 | Withdrawn | Analysis Methodology | N-1-1 definition, application and understanding |  | Ken Donohoo (ONCOR) |  | Already resolved through other PGRRs
48 | 2016-02-10 | 2016-01-01 | Closed | Model Data | Inclusion of Generators meeting Section 6.9 Requirements | Impacts to study results | David Mercado (Centerpoint) | 2016-09-01 | PGRR052 and PGRR053 address the issue
49 | 2016-03-02 | 2016-03-01 | Closed | Model Data | PGRR-046 Addition of Geomagnetically Induced Current (GIC) Model Building Requirements |  |  |  | PGRR-046 addresses issue
50 | 2016-03-23 | 2016-03-01 | Closed | Model Data | Modify Requirement for Full Financial Commitment in Section 6.9 |  | Suzy McLellan |  | PGRR053 addressed the issue Planning Guide Section 6.9 was changed
51 | 2016-03-23 | 2016-03-01 | Withdrawn | Analysis Methodology | Create an ERCOT Planning Guidelines/Philosophy (what are concerns you might have in an analysis) document (cascade analysis; what kind of margin should be designed into a project improvement). Possible legal issues. |  | Brad Woods (TxRE) |  | Is an RPG (RTP Scope) issue
52 | 2016-03-23 | 2016-03-01 | Withdrawn | Oversight | Should PLWG review SSWG, DWG, SPWG procedures? |  | Ken Bowen (CPS Energy) |  | Already resolved, see issue# 1.
53 | 2016-03-23 | 2016-03-01 | Closed | Procedure | ALDR - Document and Process |  |  |  | ROS referred to SSWG and DWG and implemented annual meeting with ALDR contact list.

## 2016-Archive
PLWG Issues List - 2016
Issue# | Date Entered | From Meeting | Status | Type of issue | Individual Issues | Key Concerns | Leader | Target Date | Resolution
1 |  |  | Closed | Data Collection |  | Initial implementation will retain SSWG/DWG/SPWG reporting to ROS; PLWG might oversee transition to more reporting-based procedure when systems are ready. |  |  | Completed. On 10/28/11, the PLWG was in consensus that there is value in the individual groups and recommends that SSWG, DWG, SPWG continue to report to ROS.
2a |  |  | Closed | Data Consistency | Is there need for an ERCOT coincident Peak Case? | PLWG should consider consistency in load forecast, load coincidence in cases/studies |  |  | PGRR011
2b |  |  | Closed | Market Transperancy | Should each utilities' rating methodology be available for market review? |  |  |  | Section 3.10 (3) of Protocols Updated 09/30/11: Complete.
3 |  |  | Closed | Validation of data accuracy and consistency |  | Each individual data item should be the responsibility of the entity that provided it. Should there be a “check” by TSP, GE or ERCOT of whether the submitted data “makes sense”? Who is responsible (accountable) for checking the modeling of the data (e.g. how the data is converted to bus/branch modeling)? |  |  | Luminant to show case errors from most recent Dataset to ERCOT and owner to explore if there is a validation method that may catch this.
4 |  |  | Closed | Validation of data accuracy and consistency |  | Is the accuracy of the consolidated dataset the responsibility of an entity (ERCOT, TSP, GE) or a group (SSWG/DWG, PLWG)? Is providing valid data part of Protocol auditing process? |  |  | Luminant to show case errors from most recent Dataset to ERCOT and owner to explore if there is a validation method that may catch this.
5 |  |  | Closed | RARF Interface |  | How to allow for corrections submitted by non generation entities. How to revise RARF to meet revised input requirements. Tuning of data used in models (e.g., stability data). Maybe could be included in ERCOT effort to get contractor to work on "total" data process. | Mike (Oncor) |  | On 10/28/11 the PLWG was in consensus that the issue was addressed thru the RARF workshop,except for the need for a process for ERCOT to extract updated information from the RARF and post as interim update to case (idev/PMCR).
6 |  |  | Closed | RPG Interface |  | Refine different focus between the two groups (with PLWG)
7 |  |  | Closed | Information sections of current procedures |  | some TSPs have taken the description of how these ratings are developed out of SSWG procedures and made those descriptions available on demand |  |  | Updated 09/30/11: Complete. Section 3.10 of Protocols
8 |  |  | Closed | Transmission Line System Design |  | a. One argument is that this is an engineering issue, not a planning issue, because it is specific for each design. b. May be some key data that would be useful for market participants. C. If routing has reliability implications (such as paralleling existing lines) may want to include in ERCOT planning activities. Review process for evaluating the contingency of multiple lines in common corridor during the early planning process. | Dan W. (ERCOT) |  | Include that in RPG review process to consider potential common or adjacent ROW
9 |  |  | Closed | Scope of PLWG in specifying parameters |  | PLWG will not review/approve specific projects; may specify level of detail in recommendations (e.g. whether recommendations should include required ampacity in addition to the conductor type assumed in study) through Planning Guides Revisions |  |  | Updated 09/30/11: Complete - PLWG charter was revisisted summer 2011 and duties and responsibilities established.
10 |  |  | Closed | Level of approval for changes |  | Need to consider whether all detailed elements of what is being considered for inclusion in the Planning Guides needs to go to Board for approval or whether there should still be “procedures” that only go to TAC for approval {things like changes to TPIT dates, which cases are built may not need to go to Board) |  |  | Updated 09/30/11: Complete - structure of guide and procedures has been further defined.
11 |  |  | Closed | RPG Scope document |  | RPG may need to develop new “Scope” document to describe what that group does (2-3 pages level of detail) Use 1.2 of Planning Charter as basis. | Dan Woodfin
12 |  |  | Closed | Developing criteria |  | Criteria may need to be developed in a way that is appropriately flexible where that makes sense (non-coincident area loads, e.g.) |  |  | Updated 09/30/11: PGRR05 and PGRR-011 will address this.
13 |  |  | Closed | Update ROS scope: Review of planning studies |  | May need to update ROS scope relative to review of planning studies
14 |  |  | Closed | New technologies |  | Facilitate investigation / implementation of new technologies (where appropriate) for improving the reliability of the electrical system (synchrophasor locations). Current effort is not ERCOT. What should ERCOT, collectively, be doing to implement synchorphasor technology?
15 |  |  | Closed | Congestion Analysis | Develop cases that more closely reflect conditions typically seen in real life | Create UPLAN cases that model normally occurring stressful load conditions such as high transfer conditions and 90th percentile load expectations.
16a |  |  | Closed | Economic Evaluation | 16A. The current UPLAN case assumptions disregard high impact conditions that regularly occur in real life, causing significant congestion costs | Refine economic criteria to include project proposal cost/benefit associated with: 1) transmission maintenance outages 2) transmission forced outages.
16b |  |  | Closed | Economic Evaluation | 16B Revisit the economic Planning Criteria as discussed at the BOD meeting Is probalistic economic planning needed? | The Houston Import Project recently approved by the BOD was the first ERCOT project approved using the Consumer Benefit criteria. Discussions during the approval process through TAC and BOD suggest that it's appropriate for the PLWG to revisit the economic evaluation process of proposed transmission projects. |  |  | Updated 09/30/11: Currently a project at the Commssion.
17 |  |  | Closed | Open Planning Model |  | Require the posting of the full UPLAN Planning Model that is utilized by ERCOT to perform their study case | Dan Woodfin
18 |  |  | Closed | Definitions/Acronyms |  | Pull Acronyms and Definitions to the front and decide at a later date. |  |  | Updated 09/30/11: Complete - Definiton and Acronyms are now in section 2 of the planning guide.
19 |  |  | Closed | Chronic Congestion |  |  |  |  | Updated 09/30/11: Ongoing - NPRR-393. 11/28/2011: This NPRR requires ERCOT to report SCED Irresolvable congestion so that the market has insights, and TSPs can determine if the congestion warrants a project. Additionally, if SCED Irr congestion is determined to be related to an ERCOT approved clearance, ERCOT will review its study method to see if this can be caught in future clearance studies. Sergio to find old language where this used to be.
20 |  |  | Closed | Interconnection Import -Export Evaluation | 1) Should ERCOT be performing economic RAPS, PCAPS etc and if so what should the criteria be. |  | Dan Woodfin |  | Updated 09/30/11: Tie interconncetion procedure produced by ERCOT. Needs to be placed in Planning Gudie.
21 |  |  | Closed |  | 1) Adding white paper on how to analyze asynchronus ties to the Planning Guides
22 |  |  | Closed | Introduction of generation in SSWG cases | What type of commitment must be made by generator proposers before their generator is modeled in the SSWG case | Some generators have gone through the SGIA process and the generator was placed in the SSWG case, just to find out that the generator cancelled the project. This can cause deficient transmission planning in areas where the generator was once expected. | Wayne Kemper |  | Updated 09/30/11: Maybe addressed in PGRR 003? Updated 01/26/12: Maybe addressed in PGRR 015. 12/2012 Update - PGRR 018 addresses this issue
23 |  |  | Closed | Stability of study assumptions that justify major transmission projects | What weight should long term considerations have on the planning of major projects? | Give long-term considerations to appropriately apply cost/benefit and reliability aspects of major transmission lines. |  |  | Updated 09/30/11: Potentially use results of LTSA to assess benefit of longer than five year assessment. Complete assessment of longer term horizon. 11/28/11: 7-year out case will help. Also, study several different assumptions to help ensure that most reasonable outcomes are studied. Examples: Fayetteville - Zenith studied gas & generation build scenarios: Hutto - Clear Springs looked at numerous potential non-related transmission projects as well as several small projects versus a big project. Related to item 8 (dan W)
24 | 2011-08-16 | 2011-04-29 | Closed | Interruptible Load | Interruptible load may not be appropriate to consider as a solution to fixing a system problem |  |  |  | Updated 09/30/11: No interruptible in the ERCOT market. PGRR 005(?) took care of this. Also, look in PGRR011.
25 | 2011-08-16 | 2011-04-29 | Closed | Definition of credible single contingency | Revise the definition to separate the description of the event from the performance. |  |  |  | Updated 09/30/11: PGRR011
26 | 2011-08-16 | 2011-04-29 | Closed | Mothballed Generator | Include the treatment of mothballed generation units in planning studies especially in tests associated wit short circuit.
27 | 2011-08-16 | 2011-04-29 | Closed | Severe contingencies | Add a definition of severe contingency as well as description of required performance. This is consistent with ERCOT's recommendations on parlleling 345 kV lines in CREZ.
28 | 2011-08-16 | 2011-05-26 | Closed | Review ERCOT ALDR procedure | 1)Is ERCOT issuing ALDR to appropriate entities
29 | 2011-08-16 | 2011-05-26 | Closed |  | 2)Need to address how ALDR infromation is getting into DSA and DSB(planning) cases
30 | 2011-08-16 | 2011-05-26 | Closed | Contingency Definition | Is the present category C and D needed in the planning guide in the future
31 | 2011-08-16 | 2011-05-26 | Closed | Wind Generation | Should a procedure for aggregating wind generator collector systems into the model be developed and put into the DWG procedures?
32 | 2011-08-16 | 2011-05-26 | Closed | Tap Changing | Do we need to research Operating Guide or protocol language addressing the changing of taps on GSUs after plant goes in service. |  | Mike (Oncor) |  | Updated 09/30/11: Protocol 3.10.7.1.4 (?)
33 | 2011-08-16 | 2011-07-29 | Closed | PGRR009 | Follow-up PGRR009 to address other matters. | RARF
34 | 2011-08-16 | 2011-07-29 | Closed | PGRR009 | Add “Generator Reactive” capability to issues list. This is a follow up to Centerpoint comments on PGRR009. |  |  |  | Updated 09/30/11: PGRR009 in progress that may address the noted issue.
35 | 2011-10-19 | 2011-09-01 | Closed | Generation Interconnect Procedure |  | At what point does the level of change out in wind turbines at a particular site trigger anew FIS (or should it)?
36 | 2011-11-28 |  | Closed | Simultaneous updates between SSWG, DWG & SPWG | Any change made to a case should be passed along to all 3 working groups, to ensure all participants are using the most recent case | What is the best way to ensure that all participants have access to the most recent models (i.e., case posted and then add idevs). Some companies use ASPEN, so idevs need to have a description so that it can be entered into non PSS/E programs | Peter Belkin |  | Peter will present "straw man" for discussion at the December 16 meeting.
37 | 2011-11-28 |  | Closed | Should there be a "7-year out case" of Dataset B? | Concern about the long-time line associated with major projects. | This helps the make the "need" description more robust. This helps bring LTSA identified lines into the regular planning process. | Sergio Garza |  | Will show presentation given during a TO meeting last year.12/2012 Update - PGRR 026 addresses this issue
38 | 2011-11-28 |  | Closed | What set of cases should be built? | Are the current Dataset A & B cases the most useful cases to build? | what types of base cases should be built to cover "high wind" scenario. Do we really need a Dataset B Fall1 and Fall2 case (for example)
39 | 2011-12-16 |  | Closed | Synchronize generation addition assumptions between CDR, GATF and SSWG base cases. Or are there good reasons to have differences? | Currently only an SGIA or Muni statement for inclusion, however, there may need to be more criteria. Should there be consistency between these groups? Also discuss consistency of other resources such as DC Ties, switchable units… | Future generating units with SGIA, but without financially-binding commitment, are in the CDR (& SARA), and applied to the reserve margin, and are also in the SSWG basecases, but are not on-line in the SSWG cases. |  |  | Dan W. is already working in this area. This impacts base cases (SSWG, etc) as well as GATF, and possibly other. Also consider all resource assumptions (e.g. DC Ties, switchable units, etc)
40 | 2016-02-10 | 2016-01-01 | Pending | Stability | What is the proper resolution of stability issues identified during the FIS? |  | Chad Thompson (ERCOT) |  | -Referred to PLWG by ROS -ROS Narrowed PLWG to review the Interconnection Timeline -NPRR809, PGRR052, PGRR053 and PGRR054 were created to address the issue. -Planning Guide Sections 5.4.2, 5.4.3, 5.4.5, 6.9 changed and 5.9 added
41 | 2016-02-10 | 2016-01-01 | Closed | Analysis Methodology | Load/Generation Scaling in Steady State transmission planning studies (PGRR042) |  | Jeff Billo (ERCOT) | 2016-09-01 | - Referred to PLWG by ROS - PGRR042 addressed issue
42 | 2016-02-10 | 2016-01-01 | Closed | Analysis Methodology | Generation Deliverability |  | Jeff Billo (ERCOT) |  | - Referred to PLWG by ROS. - Provided Market Participant links to past material. - Updated ROS with presentation from ERCOT recommending no additional action required. - ROS considered assignment complete.
43 | 2016-02-10 | 2016-01-01 | Closed | Analysis Methodology | Treatment of DC-Ties in Whitepaper - Ensure proper assumption about DC-Tie used in ERCOT RTP cases |  | Jeff Billo (ERCOT) |  | - ROS approved revisions to whitepaper
44 | 2016-02-10 | 2016-01-01 | Closed | Data Requirements | ERCOT ALDR request management - Ensuring stakeholder review of large annual data requests. |  | Ken Donohoo (ONCOR) |  | ROS referred to SSWG and DWG and implemented annual meeting with ALDR contact list.
45 | 2016-02-10 | 2016-01-01 | Withdrawn | Model Data | DG reporting and modeling |  | Ken Donohoo (ONCOR) |  | Already resolved through other PGRRs
46 | 2016-02-10 | 2016-01-01 | Closed | Analysis Methodology | Generation Interconnection studies consistency of analysis between TSPs |  | Ken Donohoo (ONCOR) |  | Being considered as part of issue# 40.
47 | 2016-02-10 | 2016-01-01 | Withdrawn | Analysis Methodology | N-1-1 definition, application and understanding |  | Ken Donohoo (ONCOR) |  | Already resolved through other PGRRs
48 | 2016-02-10 | 2016-01-01 | Pending | Model Data | Inclusion of Generators meeting Section 6.9 Requirements | Impacts to study results | David Mercado (Centerpoint) | 2016-09-01 | PGRR052 and PGRR053 address the issue
49 | 2016-03-02 | 2016-03-01 | Closed | Model Data | PGRR-046 Addition of Geomagnetically Induced Current (GIC) Model Building Requirements |  |  |  | PGRR-046 addresses issue
50 | 2016-03-23 | 2016-03-01 | Closed | Model Data | Modify Requirement for Full Financial Commitment in Section 6.9 |  | Suzy McLellan |  | PGRR053 addressed the issue Planning Guide Section 6.9 was changed
51 | 2016-03-23 | 2016-03-01 | Withdrawn | Analysis Methodology | Create an ERCOT Planning Guidelines/Philosophy (what are concerns you might have in an analysis) document (cascade analysis; what kind of margin should be designed into a project improvement). Possible legal issues. |  | Brad Woods (TxRE) |  | Is an RPG (RTP Scope) issue
52 | 2016-03-23 | 2016-03-01 | Withdrawn | Oversight | Should PLWG review SSWG, DWG, SPWG procedures? |  | Ken Bowen (CPS Energy) |  | Already resolved, see issue# 1.
53 | 2016-03-23 | 2016-03-01 | Closed | Procedure | ALDR - Document and Process |  |  |  | ROS referred to SSWG and DWG and implemented annual meeting with ALDR contact list.

## 2012-Archive
PLWG Issues List - 2012
Issue# | Date Entered | From Meeting | Status | Type of issue | Individual Issues | Key Concerns | Leader | Target Date | Resolution
1 |  |  | Closed | Data Collection |  | Initial implementation will retain SSWG/DWG/SPWG reporting to ROS; PLWG might oversee transition to more reporting-based procedure when systems are ready. |  |  | Completed. On 10/28/11, the PLWG was in consensus that there is value in the individual groups and recommends that SSWG, DWG, SPWG continue to report to ROS.
2a |  |  | Open | Data Consistency | Is there need for a ERCOT coincident Peak Case? | PLWG should consider consistency in load forecast, load coincidence in cases/studies |  |  | Ongoing. Review after disposition of PGRR011.
2b |  |  | Closed |  | Should each utilities' rating methodology be available for market review? |  |  |  | Updated 09/30/11: Complete. Section 3.10(3) of Protocols
3 |  |  | Open | Validation of data accuracy and consistency |  | Each individual data item should be the responsibility of the entity that provided it. Should there be a “check” by TSP, GE or ERCOT of whether the submitted data “makes sense”? Who is responsible (accountable) for checking the modeling of the data (e.g. how the data is converted to bus/branch modeling)? |  |  | Luminant to show case errors from most recent Dataset to ERCOT and owner to explore if there is a validation method that may catch this.
4 |  |  | Open | Validation of data accuracy and consistency |  | Is the accuracy of the consolidated dataset the responsibility of an entity (ERCOT, TSP, GE) or a group (SSWG/DWG, PLWG)? Is providing valid data part of Protocol auditing process? |  |  | Luminant to show case errors from most recent Dataset to ERCOT and owner to explore if there is a validation method that may catch this.
5 |  |  | Assigned | RARF Interface |  | How to allow for corrections submitted by non generation entities. How to revise RARF to meet revised input requirements. Tuning of data used in models (e.g., stabiliyt data). Maybe could be included in ERCOT effort to get contractor to work on "total" data process. | Mike (Oncor) |  | On 10/28 the PLWG was in consensus that the issue was addressed thru the RARF workshop,except for the need for a process for ERCOT to extract updated information from the RARF and post as interim update to case (idev/PMCR).
6 |  |  | Open | RPG Interface |  | refine different focus between the two groups (with PLWG)
7 |  |  | Closed | Information sections of current procedures |  | some TSPs have taken the description of how these ratings are developed out of SSWG procedures and made those descriptions available on demand |  |  | Updated 09/30/11: Complete. Section 3.10 of Protocols
8 |  |  | Assigned | Transmission Line System Design |  | a. One argument is that this is an engineering issue, not a planning issue, because it is specific for each design. b. May be some key data that would be useful for market participants. C. If routing has reliability implications (such as paralleling existing lines) may want to include in ERCOT planning activities. Review process for evaluating the contingency of multiple lines in common corridor during the early planning process. | Dan W. (ERCOT) |  | Include that in RPG review process to consider potential common or adjacent ROW
9 |  |  | Closed | Scope of PLWG in specifying parameters |  | PLWG will not review/approve specific projects; may specify level of detail in recommendations (e.g. whether recommendations should include required ampacity in addition to the conductor type assumed in study) through Planning Guides Revisions |  |  | Updated 09/30/11: Complete - PLWG charter was revisisted summer 2011 and duties and responsibilities established.
10 |  |  | Closed | Level of approval for changes |  | Need to consider whether all detailed elements of what is being considered for inclusion in the Planning Guides needs to go to Board for approval or whether there should still be “procedures” that only go to TAC for approval {things like changes to TPIT dates, which cases are built may not need to go to Board) |  |  | Updated 09/30/11: Complete - structure of guide and procedures has been further defined.
11 |  |  | Assigned | RPG Scope document |  | RPG may need to develop new “Scope” document to describe what that group does (2-3 pages level of detail) Use 1.2 of Planning Charter as basis. | Dan Woodfin
12 |  |  | Open | Developing criteria |  | Criteria may need to be developed in a way that is appropriately flexible where that makes sense (non-coincident area loads, e.g.) |  |  | Updated 09/30/11: PGRR05 and PGRR-011 will address this.
13 |  |  | Open | Update ROS scope: Review of planning studies |  | May need to update ROS scope relative to review of planning studies
14 |  |  | Open | New technologies |  | Facilitate investigation / implementation of new technologies (where appropriate) for improving the reliability of the electrical system (synchrophasor locations). Current effort is not ERCOT. What should ERCOT, collectively, be doing to implement synchorphasor technology?
15 |  |  | Open | Congestion Analysis | Develop cases that more closely reflect conditions typically seen in real life | Create UPLAN cases that model normally occurring stressful load conditions such as high transfer conditions and 90th percentile load expectations.
16a |  |  | Open | Economic Evaluation | 16A. The current UPLAN case assumptions disregard high impact conditions that regularly occur in real life, causing significant congestion costs | Refine economic criteria to include project proposal cost/benefit associated with: 1) transmission maintenance outages 2) transmission forced outages.
16b |  |  | Open | Economic Evaluation | 16B Revisit the economic Planning Criteria as discussed at the BOD meeting Is probalistic economic planning needed? | The Houston Import Project recently approved by the BOD was the first ERCOT project approved using the Consumer Benefit criteria. Discussions during the approval process through TAC and BOD suggest that it's appropriate for the PLWG to revisit the economic evaluation process of proposed transmission projects. |  |  | Updated 09/30/11: Currently a project at the Commssion.
17 |  |  | Assigned | Open Planning Model |  | Require the posting of the full UPLAN Planning Model that is utilized by ERCOT to perform their study case | Dan Woodfin
18 |  |  | Closed | Definitions/Acronyms |  | Pull Acronyms and Definitions to the front and decide at a later date. |  |  | Updated 09/30/11: Complete - Definiton and Acronyms are now in section 2 of the planning guide.
19 |  |  | Open | Chronic Congestion |  |  |  |  | Updated 09/30/11: Ongoing - NPRR-393. 11/28/2011: This NPRR requires ERCOT to report SCED Irresolvable congestion so that the market has insights, and TSPs can determine if the congestion warrants a project. Additionally, if SCED Irr congestion is determined to be related to an ERCOT approved clearance, ERCOT will review its study method to see if this can be caught in future clearance studies. Sergio to find old language where this used to be.
20 |  |  | Assigned | Interconnection Import -Export Evaluation | 1) Should ERCOT be performing economic RAPS, PCAPS etc and if so what should the criteria be. |  | Dan Woodfin |  | Updated 09/30/11: Tie interconncetion procedure produced by ERCOT. Needs to be placed in Planning Gudie.
21 |  |  | Open |  | 1) Adding white paper on how to analyze asynchronus ties to the Planning Guides
22 |  |  | Assigned | Introduction of generation in SSWG cases | What type of commitment must be made by generator proposers before their generator is modeled in the SSWG case | Some generators have gone through the SGIA process and the generator was placed in the SSWG case, just to find out that the generator cancelled the project. This can cause deficient transmission planning in areas where the generator was once expected. | Wayne Kemper |  | Updated 09/30/11: Maybe addressed in PGRR 003? Updated 01/26/12: Maybe addressed in PGRR 015. 12/2012 Update - PGRR 018 addresses this issue
23 |  |  | Open | Stability of study assumptions that justify major transmission projects | What weight should long term considerations have on the planning of major projects? | Give long-term considerations to appropriately apply cost/benefit and reliability aspects of major transmission lines. |  |  | Updated 09/30/11: Potentially use results of LTSA to assess benefit of longer than five year assessment. Complete assessment of longer term horizon. 11/28/11: 7-year out case will help. Also, study several different assumptions to help ensure that most reasonable outcomes are studied. Examples: Fayetteville - Zenith studied gas & generation build scenarios: Hutto - Clear Springs looked at numerous potential non-related transmission projects as well as several small projects versus a big project. Related to item 8 (dan W)
24 | 2011-08-16 | 2011-04-29 | Open | Interruptible Load | Interruptible load may not be appropriate to consider as a solution to fixing a system problem |  |  |  | Updated 09/30/11: No interruptible in the ERCOT market. PGRR 005(?) took care of this. Also, look in PGRR011.
25 | 2011-08-16 | 2011-04-29 | Open | Definition of credible single contingency | Revise the definition to separate the description of the event from the performance. |  |  |  | Updated 09/30/11: PGRR011
26 | 2011-08-16 | 2011-04-29 | Open | Mothballed Generator | Include the treatment of mothballed generation units in planning studies especially in tests associated wit short circuit.
27 | 2011-08-16 | 2011-04-29 | Open | Severe contingencies | Add a definition of severe contingency as well as description of required performance. This is consistent with ERCOT's recommendations on parlleling 345 kV lines in CREZ.
28 | 2011-08-16 | 2011-05-26 | Open | Review ERCOT ALDR procedure | 1)Is ERCOT issuing ALDR to appropriate entities
29 | 2011-08-16 | 2011-05-26 | Open |  | 2)Need to address how ALDR infromation is getting into DSA and DSB(planning) cases
30 | 2011-08-16 | 2011-05-26 | Open | Contingency Definition | Is the present category C and D needed in the planning guide in the future
31 | 2011-08-16 | 2011-05-26 | Open | Wind Generation | Should a procedure for aggregating wind generator collector systems into the model be developed and put into the DWG procedures?
32 | 2011-08-16 | 2011-05-26 | Assigned | Tap Changing | Do we need to research Operating Guide or protocol language addressing the changing of taps on GSUs after plant goes in service. |  | Mike (Oncor) |  | Updated 09/30/11: Protocol 3.10.7.1.4 (?)
33 | 2011-08-16 | 2011-07-29 | Open | PGRR009 | Follow-up PGRR009 to address other matters. | RARF
34 | 2011-08-16 | 2011-07-29 | Open | PGRR009 | Add “Generator Reactive” capability to issues list. This is a follow up to Centerpoint comments on PGRR009. |  |  |  | Updated 09/30/11: PGRR009 in progress that may address the noted issue.
35 | 2011-10-19 | 2011-09-01 | Open | Generation Interconnect Procedure |  | At what point does the level of change out in wind turbines at a particular site trigger anew FIS (or should it)?
36 | 2011-11-28 |  | Assigned | Simultaneous updates between SSWG, DWG & SPWG | Any change made to a case should be passed along to all 3 working groups, to ensure all participants are using the most recent case | What is the best way to ensure that all participants have access to the most recent models (i.e., case posted and then add idevs). Some companies use ASPEN, so idevs need to have a description so that it can be entered into non PSS/E programs | Peter Belkin |  | Peter will present "straw man" for discussion at the December 16 meeting.
37 | 2011-11-28 |  | Assigned | Should there be a "7-year out case" of Dataset B? | Concern about the long-time line associated with major projects. | This helps the make the "need" description more robust. This helps bring LTSA identified lines into the regular planning process. | Sergio Garza |  | Will show presentation given during a TO meeting last year.12/2012 Update - PGRR 026 addresses this issue
38 | 2011-11-28 |  | Open | What set of cases should be built? | Are the current Dataset A & B cases the most useful cases to build? | what types of base cases should be built to cover "high wind" scenario. Do we really need a Dataset B Fall1 and Fall2 case (for example)
39 | 2011-12-16 |  | Assigned | Synchronize generation addition assumptions between CDR, GATF and SSWG base cases. Or are there good reasons to have differences? | Currently only an SGIA or Muni statement for inclusion, however, there may need to be more criteria. Should there be consistency between these groups? Also discuss consistency of other resources such as DC Ties, switchable units… | Future generating units with SGIA, but without financially-binding commitment, are in the CDR (& SARA), and applied to the reserve margin, and are also in the SSWG basecases, but are not on-line in the SSWG cases. |  |  | Dan W. is already working in this area. This impacts base cases (SSWG, etc) as well as GATF, and possibly other. Also consider all resource assumptions (e.g. DC Ties, switchable units, etc)

## 2011-Archive
PLWG Issues List - 2011
Issue# | Date Entered | From Meeting | Status | Type of issue | Individual Issues | Key Concerns | Leader | Target Date | Resolution
1 |  |  | Closed | Data Collection |  | Initial implementation will retain SSWG/DWG/SPWG reporting to ROS; PLWG might oversee transition to more reporting-based procedure when systems are ready. |  |  | Completed. On 10/28/11, the PLWG was in consensus that there is value in the individual groups and recommends that SSWG, DWG, SPWG continue to report to ROS.
2a |  |  | Open | Data Consistency | Is there need for a ERCOT coincident Peak Case? | PLWG should consider consistency in load forecast, load coincidence in cases/studies |  |  | Ongoing. Review after disposition of PGRR011.
2b |  |  | Closed |  | Should each utilities' rating methodology be available for market review? |  |  |  | Updated 09/30/11: Complete. Section 3.10(3) of Protocols
3 |  |  | Open | Validation of data accuracy and consistency |  | Each individual data item should be the responsibility of the entity that provided it. Should there be a “check” by TSP, GE or ERCOT of whether the submitted data “makes sense”? Who is responsible (accountable) for checking the modeling of the data (e.g. how the data is converted to bus/branch modeling)?
4 |  |  | Open | Validation of data accuracy and consistency |  | Is the accuracy of the consolidated dataset the responsibility of an entity (ERCOT, TSP, GE) or a group (SSWG/DWG, PLWG)? Is providing valid data part of Protocol auditing process? |  |  | Ongoing
5 |  |  | Assigned | RARF Interface |  | How to allow for corrections submitted by non generation entities. How to revise RARF to meet revised input requirements. Tuning of data used in models (e.g., stabiliyt date). Maybe could be included in ERCOT effort to get contractor to work on "total" data process. | Mike (Oncor) |  | On 10/28 the PLWG was in consensus that the issue was addressed thru the RARF workshop,except for the need for a process for ERCOT to extract updated information from the RARF and post as interim update to case (idev/PMCR).
6 |  |  | Open | RPG Interface |  | refine different focus between the two groups (with PLWG) |  |  | RPG Scope to be reviewed at November PLWG.
7 |  |  | Closed | Information sections of current procedures |  | some TSPs have taken the description of how these ratings are developed out of SSWG procedures and made those descriptions available on demand |  |  | Updated 09/30/11: Complete. Section 3.10 of Protocols
8 |  |  | Assigned | Transmission Line System Design |  | a. One argument is that this is an engineering issue, not a planning issue, because it is specific for each design. b. May be some key data that would be useful for market participants. C. If routing has reliability implications (such as paralleling existing lines) may want to include in ERCOT planning activities. Review process for evaluating the contingency of multiple lines in common corridor during the early planning process. | Dan W. (ERCOT) |  | Include that in RPG review process to consider potential common or adjacent ROW
9 |  |  | Closed | Scope of PLWG in specifying parameters |  | PLWG will not review/approve specific projects; may specify level of detail in recommendations (e.g. whether recommendations should include required ampacity in addition to the conductor type assumed in study) through Planning Guides Revisions |  |  | Updated 09/30/11: Complete - PLWG charter was revisisted summer 2011 and duties and responsibilities established.
10 |  |  | Closed | Level of approval for changes |  | Need to consider whether all detailed elements of what is being considered for inclusion in the Planning Guides needs to go to Board for approval or whether there should still be “procedures” that only go to TAC for approval {things like changes to TPIT dates, which cases are built may not need to go to Board) |  |  | Updated 09/30/11: Complete - structure of guide and procedures has been further defined.
11 |  |  | Assigned | RPG Scope document |  | RPG may need to develop new “Scope” document to describe what that group does (2-3 pages level of detail) Use 1.2 of Planning Charter as basis. | Dan Woodfin
12 |  |  | Open | Developing criteria |  | Criteria may need to be developed in a way that is appropriately flexible where that makes sense (non-coincident area loads, e.g.) |  |  | Updated 09/30/11: PGRR05 and PGRR-011 will address this.
13 |  |  | Open | Update ROS scope: Review of planning studies |  | May need to update ROS scope relative to review of planning studies
14 |  |  | Open | New technologies |  | Facilitate investigation / implementation of new technologies (where appropriate) for improving the reliability of the electrical system (synchrophasor locations). Current effort is not ERCOT. What should ERCOT, collectively, be doing to implement synchorphasor technology?
15 |  |  | Open | Congestion Analysis | Develop cases that more closely reflect conditions typically seen in real life | Create UPLAN cases that model normally occurring stressful load conditions such as high transfer conditions and 90th percentile load expectations.
16a |  |  | Open | Economic Evaluation | 16A. The current UPLAN case assumptions disregard high impact conditions that regularly occur in real life, causing significant congestion costs | Refine economic criteria to include project proposal cost/benefit associated with: 1) transmission maintenance outages 2) transmission forced outages.
16b |  |  | Open | Economic Evaluation | 16B Revisit the economic Planning Criteria as discussed at the BOD meeting Is probalistic economic planning needed? | The Houston Import Project recently approved by the BOD was the first ERCOT project approved using the Consumer Benefit criteria. Discussions during the approval process through TAC and BOD suggest that it's appropriate for the PLWG to revisit the economic evaluation process of proposed transmission projects. |  |  | Updated 09/30/11: Currently a project at the Commssion.
17 |  |  | Assigned | Open Planning Model |  | Require the posting of the full UPLAN Planning Model that is utilized by ERCOT to perform their study case | Dan Woodfin
18 |  |  | Closed | Definitions/Acronyms |  | Pull Acronyms and Definitions to the front and decide at a later date. |  |  | Updated 09/30/11: Complete - Definiton and Acronyms are now in section 2 of the planning guide.
19 |  |  | Open | Chronic Congestion |  |  |  |  | Updated 09/30/11: Ongoing - NPRR-385(?) at ROS presently (9/30/2011)
20 |  |  | Assigned | Interconnection Import -Export Evaluation | 1) Should ERCOT be performing economic RAPS, PCAPS etc and if so what should the criteria be. |  | Dan Woodfin |  | Updated 09/30/11: Tie interconncetion procedure produced by ERCOT. Needs to be placed in Planning Gudie.
21 |  |  | Open |  | 1) Adding white paper on how to analyze asynchronus ties to the Planning Guides
22 |  |  | Assigned | Introduction of generation in SSWG cases | What type of commitment must be made by generator proposers before their generator is modeled in the SSWG case | Some generators have gone through the SGIA process and the generator was placed in the SSWG case, just to find out that the generator cancelled the project. This can cause deficient transmission planning in areas where the generator was once expected. | Wayne Kemper |  | Updated 09/30/11: Maybe addressed in PGRR 003?
23 |  |  | Open | Stability of study assumptions that justify major transmission projects | What weight should long term considerations have on the planning of major projects? | Give long-term considerations to appropriately apply cost/benefit and reliability aspects of major transmission lines. |  |  | Updated 09/30/11: Potentially use results of LTSA to assess benefit of longer than five year assessment. Complete assessment of longer term horizon.
24 | 2011-08-16 | 2011-04-29 | Open | Interruptible Load | Interruptible load may not be appropriate to consider as a solution to fixing a system problem |  |  |  | Updated 09/30/11: No interruptible in the ERCOT market. PGRR 005(?) took care of this. Also, look in PGRR011.
25 | 2011-08-16 | 2011-04-29 | Open | Definition of credible single contingency | Revise the definition to separate the description of the event from the performance. |  |  |  | Updated 09/30/11: PGRR011
26 | 2011-08-16 | 2011-04-29 | Open | Mothballed Generator | Include the treatment of mothballed generation units in planning studies especially in tests associated wit short circuit.
27 | 2011-08-16 | 2011-04-29 | Open | Severe contingencies | Add a definition of severe contingency as well as description of required performance. This is consistent with ERCOT's recommendations on parlleling 345 kV lines in CREZ.
28 | 2011-08-16 | 2011-05-26 | Open | Review ERCOT ALDR procedure | 1)Is ERCOT issuing ALDR to appropriate entities
29 | 2011-08-16 | 2011-05-26 | Open |  | 2)Need to address how ALDR infromation is getting into DSA and DSB(planning) cases
30 | 2011-08-16 | 2011-05-26 | Open | Contingency Definition | Is the present category C and D needed in the planning guide in the future
31 | 2011-08-16 | 2011-05-26 | Open | Wind Generation | Should a procedure for aggregating wind generator collector systems into the model be developed and put into the DWG procedures?
32 | 2011-08-16 | 2011-05-26 | Assigned | Tap Changing | Do we need to research Operating Guide or protocol language addressing the changing of taps on GSUs after plant goes in service. |  | Mike (Oncor) |  | Updated 09/30/11: Protocol 3.10.7.1.4 (?)
33 | 2011-08-16 | 2011-07-29 | Open | PGRR009 | Follow-up PGRR009 to address other matters.
34 | 2011-08-16 | 2011-07-29 | Open | PGRR009 | Add “Generator Reactive” capability to issues list. This is a follow up to Centerpoint comments on PGRR009. |  |  |  | Updated 09/30/11: PGRR009 in progress that may address the noted issue.
35 | 2011-10-19 | 2011-09-01 | Open | Generation Interconnect Procedure |  | At what point does the level of change out in wind turbines at a particular site trigger anew FIS (or should it)?

## 2010-Archive
PLWG Issues List - 2010
Issue# | Date Entered | From Meeting | Status | Type of issue | Individual Issues | Key Concerns | Leader | Target Date | Resolution
1 |  |  | Open | Data Collection |  | Initial implementation will retain SSWG/DWG/SPWG reporting to ROS; PLWG might oversee transition to more reporting-based procedure when systems are ready.
2 |  |  | Open | Data Consistency | 2A Is there need for a ERCOT coincident Peak Case? | PLWG should consider consistency in load forecast, load coincidence in cases/studies, line ratings
|  |  | Open |  | 2b Each utilities rating methodology-should it be available for market review?
3 |  |  | Open | Validation of data accuracy and consistency |  | Each individual data item should be the responsibility of the entity that provided it. Should there be a “check” by TSP, GE or ERCOT of whether the submitted data “makes sense”? Who is responsible (accountable) for checking the modeling of the data (e.g. how the data is converted to bus/branch modeling)? Is the accuracy of the consolidated dataset the responsibility of an entity (ERCOT, TSP, GE) or a group (SSWG/DWG, PLWG)? Is providing valid data part of Protocol auditing process?
4 |  |  | Open | Data Gaps
5 |  |  | Open | RARF Interface |  | How to allow for corrections submitted by non generation entities. How to revise RARF to meet revised input requirements.
6 |  |  | Open | RPG Interface |  | refine different focus between the two groups
7 |  |  | Open | Information sections of current procedures |  | some TSPs have taken the description of how these ratings are developed out of SSWG procedures and made those descriptions available on demand
8 |  |  | Open | Transmission Line Design |  | a. One argument is that this is an engineering issue, not a planning issue, because it is specific for each design. b. May be some key data that would be useful for market participants. C. If routing has reliability implications (such as paralleling existing lines) may want to include in ERCOT planning activities.
9 |  |  | Open | Scope of PLWG in specifying parameters |  | PLWG will not review/approve specific projects; may specify level of detail in recommendations (e.g. whether recommendations should include required ampacity in addition to the conductor type assumed in study) through Planning Guides Revisions
10 |  |  | Open | Level of approval for changes |  | Need to consider whether all detailed elements of what is being considered for inclusion in the Planning Guides needs to go to Board for approval or whether there should still be “procedures” that only go to TAC for approval {things like changes to TPIT dates, which cases are built may not need to go to Board)
11 |  |  | Open | RPG Scope document |  | RPG may need to develop new “Scope” document to describe what that group does (2-3 pages level of detail) Use 1.2 of Planning Charter as basis.
12 |  |  | Open | Developing criteria |  | Criteria may need to be developed in a way that is appropriately flexible where that makes sense (non-coincident area loads, e.g.)
13 |  |  | Open | Update ROS scope: Review of planning studies |  | May need to update ROS scope relative to review of planning studies
14 |  |  | Open | New technologies |  | Facilitate investigation / implementation of new technologies (where appropriate) for improving the reliability of the electrical system (synchrophasor locations).
15 |  |  | Open | Congestion Analysis | Develop cases that more closely reflect conditions typically seen in real life | Create UPLAN cases that model normally occurring stressful load conditions such as high transfer conditions and 90th percentile load expectations.
16 |  |  | Open | Economic Evaluation | 16A. The current UPLAN case assumptions disregard high impact conditions that regularly occur in real life, causing significant congestion costs | Refine economic criteria to include project proposal cost/benefit associated with: 1) transmission maintenance outages 2) transmission forced outages.
|  |  | Open |  | 16B Revisit the economic Planning Criteria as discussed at the BOD meeting Is probalistic economic planning needed? | The Houston Import Project recently approved by the BOD was the first ERCOT project approved using the Consumer Benefit criteria. Discussions during the approval process through TAC and BOD suggest that it's appropriate for the PLWG to revisit the economic evaluation process of proposed transmission projects.
17 |  |  | Open | Open Planning Model |  | Require the posting of the full UPLAN Planning Model that is utilized by ERCOT to perform their study case
18 |  |  | Open | Definitions/Acronyms |  | Pull Acronyms and Definitions to the front and decide at a later date.
19 |  |  | Open | Chronic Congestion
20 |  |  | Open | Interconnection Import -Export Evaluation | 1) Should ERCOT be performing economic RAPS, PCAPS etc and if so what should the criteria be.