## Slide 1
Project Update and Summary of
Project Priority List (PPL) Activity
April 13, 2016

## Slide 2
Project Portfolio Update p. 3-8
  Recent / Upcoming Project Implementations
  2017 Release Targets
  2018 Release Targets
  2017 Project Spending Forecast
  Revision Request Funding Placeholder Status
  Impact Analysis Results Review
  Priority/Rank Options for Revision Requests with Impacts
Appendix
  Project Portfolio Gantt Chart p. 9-17
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index
Project Update Agenda

## Slide 3: Recent / Upcoming Project Implementations
2017 May Release – 5/1/2017-5/11/2017 In Flight
  SCR790 – Wind Resource Power Production and Forecast Transparency
  NPRR746 – Adjustments Due to Negative Load
  NPRR786 – Consumption Data Adjustments for Negative Load
  NPRR792 – Changing Special Protection System (SPS) to Remedial Action Scheme (RAS)
  NOGRR164 – Alignment with NPRR792, Removing SPS and adding (RAS)
  PGRR051 – Alignment with NPRR792, Changing SPS to RAS
2017 May Off-Cycle Release – 5/15/2017 In Flight
  RRGRR003 – Modifications to Improve Wind Forecasting
  RRGRR006 – Clarification of Descriptions and Alignment with RARF Forms
  RRGRR007 – Adding Solar Resource Registration Inputs
  RRGRR009 – Adding Voltage Limit Sets, Relay Loadability, MLSE, and GMD Data
  PGRR046 – Addition of Geomagnetically Induced Current (GIC) Model Building Reqs
Go-Live date in Q2 2017 In Flight
  NMMS Upgrade project
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2017 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
(a), (b), etc. indicates multiple phases
March 3/7 – 3/9 | May 5/1 – 5/11 | June 6/27 – 6/29 | August 8/29 – 8/31 | October 10/31 – 11/2 | December 12/5 – 12/7
NPRR272 NPRR649 NPRR753 NPRR764 NPRR785 RMGRR134 NPRR790 | SCR790 NPRR746 NPRR786 NPRR792 NOGRR164 PGRR051 RRGRR003 RRGRR006 RRGRR007 RRGRR009 PGRR046 | NPRR573 NPRR744 NPRR782 NPRR789 NPRR797 NPRR801 NPRR744 | NPRR758 NPRR775 NPRR782 SCR777 | NPRR778 | SCR789
7 | 11 | 5 | 3 | 1 | 1
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold
TBD Items (and point at which they became “TBD”)
2014 | 2015 | 2016 | 2017
NOGRR084, NPRR664 | None | SCR781 P | NPRR702 P, NPRR776, NPRR808, NPRR809, NPRR810, NPRR812, PGRR052
12/9 – 12/10 (Retail)
10/2 – 10/3
(Off-Cycle)
Q2 – NMMS Upgrade
5/15
6/1
11/11 – 11/12 (Retail)
E
E
E
E
E
E
E
E
E
E
E
E
E
E
P
NS
NS
9/16 – 9/17
(Retail)
2/1
E
E
E
E
E
ü
ü
ü
ü
ü
ü
ü
Moved to 2018-R1

## Slide 5: 2018 Release Targets – Board Approved NPRRs / SCRs / xGRRs
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
APPENDIX
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
(a), (b), etc. indicates multiple phases
March Dates TBD | May Dates TBD | June Dates TBD | August Dates TBD | October Dates TBD | December Dates TBD
NPRR749 SCR777 | NPRR519 NPRR620 NPRR683 NPRR741 NPRR743 NPRR755 NPRR760 NPRR800 |  |  |  | 
2 | 8 | 0 | 0 | 0 | 0
Dates TBD
(Retail)
Dates TBD
(Retail)
Dates TBD
(Retail)
Dates TBD
(Retail)
E
E
E
E
E
E
E
E
Dates TBD
(Retail)
NS
E
Dates TBD
(Retail)
CMM Release 1
Project Status Codes
NS = Not Started
I = Initiation
P = Planning
E = Execution
H = On Hold

## Slide 6: 2017 Project Spending
2017 PPL Budget = $20.5M
“Potential Demand” represents internal ERCOT projects that have not been fully approved

## Slide 7: Revision Request Funding Placeholder Status
In 2017, ERCOT forecasted $4.0M for Revision Request work
Yearly Revision Request Spending Forecast Summary
Project Status | 2017
YTD Actuals | $0.39M
Approved – In-Flight / Complete | $1.87M
Approved – On Hold | $0.00M
Approved – Not Started | $0.15M
Remaining Funding | $1.98M
Total Allocation | $4.00M
As of 2/28/2017

## Slide 8: Impact Analysis Results Review
Annual review of Impact Analysis Results
Three years of data
  2016 added / 2013 removed
  51 Revision Requests implemented in 2014-2016
This year duration estimation performance is also included
See final slide for legend
Observations / Notes
  Process improvements implemented in 2016 won’t appear until next year
  Cost Estimates
    Continued evidence that historical IA cost ranges have been too narrow
  Duration Estimates
    Note: Bundled projects compare against the sum of the individual durations
    Tendency to under-estimate project durations

## Slide 9: Variance from IA Cost Range – Revision Request Projects
Chart: 
| $0 | $0 | $20,350 | -$771 | -$102,412 | $0 | $0 | -$44,756 | -$15,669 | $0 | -$9,429 | -$22,356 | -$4,033 | -$90,557 | $0 | -$35,983 | $233,095 | $130,550 | -$11,824 | -$3,391 | $49,955 | -$12,318 | $0 | $0 | -$70,697 | $43,734 | $72,991 | $102,533 | $104,868 | Yes | Yes | No | No | No | Yes | Yes | No | No | Yes | No | No | No | No | Yes | No | No | No | No | No | No | No | Yes | Yes | No | No | No | No | No | $38,341 | $48,900 | $70,350 | $99,230 | $147,588 | $252,453 | $1,631,461 | $15,244 | $24,331 | $25,807 | $40,571 | $57,644 | $60,967 | $119,443 | $153,152 | $189,017 | $533,095 | $840,550 | $18,176 | $21,609 | $79,955 | $87,682 | $93,731 | $104,965 | $114,303 | $153,734 | $357,991 | $367,533 | $1,329,868 | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | No | No | Yes, 2 change controls. Added scope | Yes, one change control. Two NPRRs removed from scope | No | No | No | No | No | No | No | No | No | No | No | 1 - Less than $50k | 2 - $50k to $100k | 1 - Less than $50k | 3 - $100k to $250k | 4 - $250k to $500k | 4 - $250k to $500k | 6 - $1M to $5M | 2 - $50k to $100k | 2 - $50k to $100k | 1 - Less than $50k | 2 - $50k to $100k | 2 - $50k to $100k | 2 - $50k to $100k | 4 - $250k to $500k | 3 - $100k to $250k | 4 - $250k to $500k | 4 - $250k to $500k | 5 - $500k to $1M | 1 - Less than $50k | 1 - Less than $50k | 1 - Less than $50k | 3 - $100k to $250k | 2 - $50k to $100k | 2 - $50k to $100k | 3 - $100k to $250k | 2 - $50k to $100k | 4 - $250k to $500k | 3 - $100k to $250k | 6 - $1M to $5M | $10,000 | $15,000 | $15,000 | $10,000 | $100,000 | $35,000 | $460,000 | $15,000 | $20,000 | $10,000 | $25,000 | $10,000 | $30,000 | $90,000 | $60,000 | $50,000 | $50,000 | $230,000 | $20,000 | $20,000 | $5,000 | $50,000 | $30,000 | $40,000 | $50,000 | $30,000 | $25,000 | $80,000 | $310,000 | $40,000 | $60,000 | $50,000 | $110,000 | $350,000 | $280,000 | $1,935,000 | $75,000 | $60,000 | $30,000 | $75,000 | $90,000 | $95,000 | $300,000 | $180,000 | $275,000 | $300,000 | $710,000 | $50,000 | $45,000 | $30,000 | $150,000 | $100,000 | $120,000 | $235,000 | $110,000 | $285,000 | $265,000 | $1,225,000 | $35,000 | $52,500 | $42,500 | $105,000 | $300,000 | $262,500 | $1,705,000 | $67,500 | $50,000 | $25,000 | $62,500 | $85,000 | $80,000 | $255,000 | $150,000 | $250,000 | $275,000 | $595,000 | $40,000 | $35,000 | $27,500 | $125,000 | $85,000 | $100,000 | $210,000 | $95,000 | $272,500 | $225,000 | $1,070,000 | $30,000 | $45,000 | $35,000 | $100,000 | $250,000 | $245,000 | $1,475,000 | $60,000 | $40,000 | $20,000 | $50,000 | $80,000 | $65,000 | $210,000 | $120,000 | $225,000 | $250,000 | $480,000 | $30,000 | $25,000 | $25,000 | $100,000 | $70,000 | $80,000 | $185,000 | $80,000 | $260,000 | $185,000 | $915,000 | Market | Market | Market | Market | ERCOT | Market | Both | Market | Market | ERCOT | Market | Market | Market | Both | Both | ERCOT | Market | Both | Market | ERCOT | ERCOT | Market | Market | Market | Both | Market | ERCOT | Market | Both | NOGRR105 | NPRR476 | NPRR586 | SCR769 | NPRR425 | NPRR416 NPRR575 | NPRR240, NPRR555, NPRR532, NPRR598, NPRR564, NPRR568 | NPRR500 | NPRR543 | NPRR680 | SCR775 | SCR772 | NPRR556 | NPRR698, NPRR595, NPRR706, NPRR710 | NPRR559, NPRR597, NPRR601, NPRR639, SCR778 | SCR779 | SCR756 | NPRR665, NPRR626, OBD, NPRR645 | SCR788 | NPRR754 | NPRR419 | SCR786 | NOGRR147, SCR787 | NPRR662 | NPRR495, NPRR736, NPRR770 | NPRR617, NPRR700 | NPRR515 | NPRR588, NPRR615 | NPRR219, SCR783, NOGRR050 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | No | No | No | No | Yes | Yes | No | No | No | No | No | No | Yes | Yes | No | No | Yes | No | No | No | No | Yes | No | Yes | Yes | No | Yes | Yes | Generation Resource Frequency Response Test Procedure | Market Submitted Energy Offer Curves Disclosures | Align Credit Lock for CRR Auctions with Transaction Submission Deadline | CRRAH Digital Certificate New Role for Read Only Access | Creation of a WGR Group for GREDP and Base Point Deviation Evaluation | PR078-01 | 2014 Market System Enhancements | Posting of Generation that is Off but Available | Message for Confirmed E-Tags | Allow QSEs to Self-Arrange AS Quantities Greater Than Their AS Obligation | Posting Results of Real-Time Data in a Display Format | New Extract for Five Minute Interval Settlement Data | Resource Adequacy During Transmission Equipment Outage | Clarifications to NPRR595, RRS Load Resource Treatment In ORDC | 2014 CMM NPRRs and SCRs | Increase to the CRR Auction Transaction Limit | MarkeTrak Enhancements - Remaining SCR756 Items | Market System Enhancements 2015 | SCR788 Addition of Integral ACE Feedback to GTBD Calculation | Revise Load Distribution Factors Report Posting Frequency | NPRR419 Revise Real Time Energy Imbalance and RMR Adjustment Charge | Retail Market Test Environment | NOGRR147 and SCR787 NDCRC Enhancement | NPRR662 Proxy Energy Offer Curves | NPRR495 and NPRR736 Changes to Ancillary Services Capacity Monitor | NPRR617 and 700 Implementation | NPRR515 Day-Ahead Market Self-Commitment of Generation Resources | NPRRs 588 and 615 | 2015 Outage Scheduler Enhancements | 112-01 | 093-01 | 136-01 | 124-01 | 087-01 | 078-01 | 117-01 | 151-01 | 152-01 | 178-01 | 160-01 | 126-01 | 176-01 | 149-02 | 154-01 | 138-01 | 010-03 | 149-01 | 208-01 | 204-01 | 182-01 | 192-01 | 199-01 | 186-01 | 195-01 | 184-01 | 175-01 | 161-01 | 174-01 | 2014 | 2014 | 2014 | 2014 | 2014 | 2014 | 2014 | 2015 | 2015 | 2015 | 2015 | 2015 | 2015 | 2015 | 2015 | 2015 | 2015 | 2015 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016
Actual Variance from IA Estimate Range | 0 | 0 | 20350 | -770.5 | -102411.54 | 0 | 0 | -44756.07 | -15668.75 | 0 | -9429.49 | -22356.25 | -4033 | -90556.94 | 0 | -35982.81 | 233094.58 | 130549.98 | -11823.53 | -3391.34 | 49954.86 | -12318 | 0 | 0 | -70696.8 | 43734.23 | 72990.8 | 102533.38 | 104867.87
Exceeds IA Range
8 Projects
Below IA Range
12 Projects
Within IA Range
9 Projects
If actual spend falls within the IA range the variance is 0
9
Actual $ Variance from IA Range
2014
7 Projects
12 Revision Requests
2015
11 Projects
21 Revision Requests
2016
11 Projects
18 Revision Requests
Note: Graph compares the posted IA cost range with the actual project spend
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
Exceeds = 1
Within = 5
Below = 1
Exceeds = 2
Within = 2
Below = 7
Exceeds = 5
Within = 2
Below = 4

## Slide 10: Variance from IA Duration Range – Revision Request Projects
Chart: 
| 2 | 3 | 5 | 12 | 16 | 18 | 28 | 29 | 30 | 31 | 32 | 34 | 37 | 39 | 42 | 47 | 52 | 56 | 57 | 60 | 61 | 63 | 65 | 66 | 67 | 70 | 72 | 78 | $0 | $0 | $20,350 | -$771 | -$102,412 | $0 | -$44,756 | -$15,669 | $0 | -$9,429 | -$22,356 | -$4,033 | -$90,557 | $0 | -$35,983 | $233,095 | $130,550 | -$11,824 | -$3,391 | $49,955 | -$12,318 | $0 | $0 | -$70,697 | $43,734 | $72,991 | $102,533 | $104,868 | Yes | Yes | No | No | No | Yes | No | No | Yes | No | No | No | No | Yes | No | No | No | No | No | No | No | Yes | Yes | No | No | No | No | No | $38,341 | $48,900 | $70,350 | $99,230 | $147,588 | $252,453 | $15,244 | $24,331 | $25,807 | $40,571 | $57,644 | $60,967 | $119,443 | $153,152 | $189,017 | $533,095 | $840,550 | $18,176 | $21,609 | $79,955 | $87,682 | $93,731 | $104,965 | $114,303 | $153,734 | $357,991 | $367,533 | $1,329,868 | No | No | No | No | No | No | No | No | No | No | No | No | Yes | No | No | Yes, 2 change controls. Added scope | Yes, one change control. Two NPRRs removed from scope | No | No | No | No | No | No | No | No | No | No | No | 1 - Less than $50k | 2 - $50k to $100k | 1 - Less than $50k | 3 - $100k to $250k | 4 - $250k to $500k | 4 - $250k to $500k | 2 - $50k to $100k | 2 - $50k to $100k | 1 - Less than $50k | 2 - $50k to $100k | 2 - $50k to $100k | 2 - $50k to $100k | 4 - $250k to $500k | 3 - $100k to $250k | 4 - $250k to $500k | 4 - $250k to $500k | 5 - $500k to $1M | 1 - Less than $50k | 1 - Less than $50k | 1 - Less than $50k | 3 - $100k to $250k | 2 - $50k to $100k | 2 - $50k to $100k | 3 - $100k to $250k | 2 - $50k to $100k | 4 - $250k to $500k | 3 - $100k to $250k | 6 - $1M to $5M | $10,000 | $15,000 | $15,000 | $10,000 | $100,000 | $35,000 | $15,000 | $20,000 | $10,000 | $25,000 | $10,000 | $30,000 | $90,000 | $60,000 | $50,000 | $50,000 | $230,000 | $20,000 | $20,000 | $5,000 | $50,000 | $30,000 | $40,000 | $50,000 | $30,000 | $25,000 | $80,000 | $310,000 | $40,000 | $60,000 | $50,000 | $110,000 | $350,000 | $280,000 | $75,000 | $60,000 | $30,000 | $75,000 | $90,000 | $95,000 | $300,000 | $180,000 | $275,000 | $300,000 | $710,000 | $50,000 | $45,000 | $30,000 | $150,000 | $100,000 | $120,000 | $235,000 | $110,000 | $285,000 | $265,000 | $1,225,000 | $35,000 | $52,500 | $42,500 | $105,000 | $300,000 | $262,500 | $67,500 | $50,000 | $25,000 | $62,500 | $85,000 | $80,000 | $255,000 | $150,000 | $250,000 | $275,000 | $595,000 | $40,000 | $35,000 | $27,500 | $125,000 | $85,000 | $100,000 | $210,000 | $95,000 | $272,500 | $225,000 | $1,070,000 | $30,000 | $45,000 | $35,000 | $100,000 | $250,000 | $245,000 | $60,000 | $40,000 | $20,000 | $50,000 | $80,000 | $65,000 | $210,000 | $120,000 | $225,000 | $250,000 | $480,000 | $30,000 | $25,000 | $25,000 | $100,000 | $70,000 | $80,000 | $185,000 | $80,000 | $260,000 | $185,000 | $915,000 | Market | Market | Market | Market | ERCOT | Market | Market | Market | ERCOT | Market | Market | Market | Both | Both | ERCOT | Market | Both | Market | ERCOT | ERCOT | Market | Market | Market | Both | Market | ERCOT | Market | Both | NOGRR105 | NPRR476 | NPRR586 | SCR769 | NPRR425 | NPRR416 NPRR575 | NPRR500 | NPRR543 | NPRR680 | SCR775 | SCR772 | NPRR556 | NPRR698, NPRR595, NPRR706, NPRR710 | NPRR559, NPRR597, NPRR601, NPRR639, SCR778 | SCR779 | SCR756 | NPRR665, NPRR626, OBD, NPRR645 | SCR788 | NPRR754 | NPRR419 | SCR786 | NOGRR147, SCR787 | NPRR662 | NPRR495, NPRR736, NPRR770 | NPRR617, NPRR700 | NPRR515 | NPRR588, NPRR615 | NPRR219, SCR783, NOGRR050 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | No | No | No | No | Yes | No | No | No | No | No | No | Yes | Yes | No | No | Yes | No | No | No | No | Yes | No | Yes | Yes | No | Yes | Yes | Generation Resource Frequency Response Test Procedure | Market Submitted Energy Offer Curves Disclosures | Align Credit Lock for CRR Auctions with Transaction Submission Deadline | CRRAH Digital Certificate New Role for Read Only Access | Creation of a WGR Group for GREDP and Base Point Deviation Evaluation | PR078-01 | Posting of Generation that is Off but Available | Message for Confirmed E-Tags | Allow QSEs to Self-Arrange AS Quantities Greater Than Their AS Obligation | Posting Results of Real-Time Data in a Display Format | New Extract for Five Minute Interval Settlement Data | Resource Adequacy During Transmission Equipment Outage | Clarifications to NPRR595, RRS Load Resource Treatment In ORDC | 2014 CMM NPRRs and SCRs | Increase to the CRR Auction Transaction Limit | MarkeTrak Enhancements - Remaining SCR756 Items | Market System Enhancements 2015 | SCR788 Addition of Integral ACE Feedback to GTBD Calculation | Revise Load Distribution Factors Report Posting Frequency | NPRR419 Revise Real Time Energy Imbalance and RMR Adjustment Charge | Retail Market Test Environment | NOGRR147 and SCR787 NDCRC Enhancement | NPRR662 Proxy Energy Offer Curves | NPRR495 and NPRR736 Changes to Ancillary Services Capacity Monitor | NPRR617 and 700 Implementation | NPRR515 Day-Ahead Market Self-Commitment of Generation Resources | NPRRs 588 and 615 | 2015 Outage Scheduler Enhancements | 112-01 | 093-01 | 136-01 | 124-01 | 087-01 | 078-01 | 151-01 | 152-01 | 178-01 | 160-01 | 126-01 | 176-01 | 149-02 | 154-01 | 138-01 | 010-03 | 149-01 | 208-01 | 204-01 | 182-01 | 192-01 | 199-01 | 186-01 | 195-01 | 184-01 | 175-01 | 161-01 | 174-01 | 2014 | 2014 | 2014 | 2014 | 2014 | 2014 | 2015 | 2015 | 2015 | 2015 | 2015 | 2015 | 2015 | 2015 | 2015 | 2015 | 2015 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016
Actual Variance from IA Duration Range | 1.6 | 2.8667 | 0 | 3.4667 | 3.8333 | 0 | 0.83333 | 2.6667 | 0 | 4.3667 | 7.9667 | 0 | -8.0667 | -7.9333 | 3.3667 | 2.8 | -6.7333 | 0 | 0 | 0.33333 | 2.7667 | -2.3667 | 0 | -5.6667 | -0.46667 | 3.6333 | 4.6 | 0
Exceeds IA Range
14 Projects
Below IA Range
7 Projects
Within IA Range
8 Projects
10
2014
7 Projects
12 Revision Requests
2015
11 Projects
21 Revision Requests
2016
11 Projects
18 Revision Requests
If actual duration falls within the IA range the variance is 0.
Note: Graph compares the posted IA duration range with the actual project duration
Number of Months from IA Range
PR117-01 2014 Market System Enhancements came in below the IA Range (completed 2014).
1
2
3
4
5
6
7.
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
Exceeds = 4
Within = 2
Below = 1
Exceeds = 6
Within = 2
Below = 3
Exceeds = 4
Within = 4
Below = 3

## Slide 11: Revision Request Project Legend
PR112-01 Generation Resource Frequency Response Test Procedure, NOGRR105 (M)
PR093-01 Market Submitted Energy Offer Curves Disclosures, NPRR476 (M)
PR136-01 Align Credit Lock for CRR Auctions with Transaction Submission Deadline, NPRR586 (M)
PR124-01 CRRAH Digital Certificate New Role for Read Only Access, SCR769 (M)
PR087-01 Creation of a WGR Group for GREDP and Base Point Deviation Evaluation, NPRR425 (E)
PR078-01, NPRR416NPRR575 (M)
PR117-01 2014 Market System Enhancements, NPRR240, NPRR555, NPRR532, NPRR598, NPRR564, NPRR568 (V)
PR151-01 Posting of Generation that is Off but Available, NPRR500 (M)
PR152-01 Message for Confirmed E-Tags, NPRR543 (M)
PR178-01 Allow QSEs to Self-Arrange AS Quantities Greater Than Their AS Obligation, NPRR680 (E)
PR160-01 Posting Results of Real-Time Data in a Display Format, SCR775 (M)
PR126-01 New Extract for Five Minute Interval Settlement Data, SCR772 (M)
PR176-01 Resource Adequacy During Transmission Equipment Outage, NPRR556 (M)
PR149-02 Clarifications to NPRR595, RRS Load Resource Treatment In ORDC, NPRR698, NPRR595, NPRR706, NPRR710 (V)
PR154-01 2014 CMM NPRRs and SCRs, NPRR559, NPRR597, NPRR601, NPRR639, SCR778 (V)
PR138-01 Increase to the CRR Auction Transaction Limit, SCR779 (E)
PR010-03 MarkeTrak Enhancements - Remaining SCR756 Items, SCR756 (M)
PR149-01 Market System Enhancements 2015, NPRR665, NPRR626, OBD, NPRR645 (V)
PR208-01 SCR788 Addition of Integral ACE Feedback to GTBD Calculation, SCR788 (M)
PR204-01 Revise Load Distribution Factors Report Posting Frequency, NPRR754 (E)
PR182-01 NPRR419 Revise Real Time Energy Imbalance and RMR Adjustment Charge, NPRR419 (E)
PR192-01 Retail Market Test Environment, SCR786 (M)
PR199-01 NOGRR147 and SCR787 NDCRC Enhancement, NOGRR147, SCR787 (M)
PR186-01 NPRR662 Proxy Energy Offer Curves, NPRR662 (M)
PR195-01 NPRR495 and NPRR736 Changes to Ancillary Services Capacity Monitor, NPRR495, NPRR736, NPRR770 (V)
PR184-01 NPRR617 and 700 Implementation, NPRR617, NPRR700 (M)
PR175-01 NPRR515 Day-Ahead Market Self-Commitment of Generation Resources, NPRR515 (E)
PR161-01 NPRRs 588 and 615, NPRR588, NPRR615 (M)
PR174-01 2015 Outage Scheduler Enhancements, NPRR219, SCR783, NOGRR050 (V)
(E) ERCOT Sponsored
(M) Market Sponsored
(V) Various

## Slide 12: Priority / Rank Options for Revision Requests with Impacts
Revision Request | Description | Priority | Rank | Comments
NPRR562 | Subsynchronous Resonance | 2017 | 1990 | Small project with minor system impacts Add to end of project list – work into the plan without disrupting in-flight projects
PGRR057 | Responsibilities for Performing Geomagnetic Disturbance (GMD) Vulnerability Assessments | 2017 | 150 | REGULATORY Recommend this not be tracked against market Revision Request funding
Options for…

## Slide 13
Appendix
  3/31/2017 Project Gantt
    In-flight items sorted by Project End Date
    “On Hold” projects listed separately
      None at this time
    “Not Started” items sorted by Project Start Date

## Slide 14: Project Portfolio Status – as of 3/31/2017

## Slide 15: Project Portfolio Status – as of 3/31/2017

## Slide 16: Project Portfolio Status – as of 3/31/2017

## Slide 17: Project Portfolio Status – as of 3/31/2017

## Slide 18: Project Portfolio Status – as of 3/31/2017

## Slide 19: Project Portfolio Status – as of 3/31/2017

## Slide 20: Project Portfolio Status – as of 3/31/2017

## Slide 21: Project Portfolio Status – as of 3/31/2017